## 01 Start Here
Northbridge Citizens Services ¦ Start Here
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Launch screen for the command pack. Start with set-up, then use the guided sheet map to move through dashboards, inputs and outputs.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  | Back to Start
Quick start | [6 empty] | Workbook zones
1. Configure organisation identity, dates and thresholds on 02 Branding & Setup. | [6 empty] | Onboarding | 01–04 ¦ Set-up, guidance and overview
2. Review the guidance and overview before replacing dummy records. | [6 empty] | Dashboards | 05–08 ¦ Executive, operational, stakeholder and options
3. Use the dashboards for sponsor, team, stakeholder and options conversations. | [6 empty] | Inputs | 09–25 ¦ Plans, registers, logs, analysis and recommendations
4. Update the core input sheets; dashboards refresh from the underlying data. | [6 empty] | Output | 26–27 ¦ Outcome summary and Agile requirements export
5. Finalise the recommendation, then use 27 Agile Requirements Export to hand off selected outputs into the StratForge Agile Requirements Planner. | [6 empty] | Admin | Hidden by default ¦ Change log, QA, lists and dashboard logic
Sheet map
Onboarding |  |  | Dashboards |  |  | Core inputs |  |  | Outputs
Home |  |  | Executive Dashboard |  |  | Discovery Plan |  |  | Option Assessment
Set Up |  |  | Operational Dashboard |  |  | Stakeholder Register |  |  | Recommendations
Guidance |  |  | Stakeholder & Evidence |  |  | Pain Point Register |  |  | Outcome Summary
Overview |  |  | Opportunity & Options |  |  | Opportunity Register |  |  | Agile Requirements Export
Release controls | [6 empty] | White-label deployment note
Workbook version | V2.1 Production | [5 empty] | This workbook is designed for internal white-label deployment. Keep or hide 90 About & Attribution according to your licence terms. Hidden admin sheets hold dropdown lists, dashboard logic, QA and change control.
Discovery lead | Aisha Khan
Primary contact | discovery.office@example.org
Macro usage | None ¦ workbook is macro-free
Protection | Visible sheets protected; admin sheets hidden by default

## 02 Branding & Setup
Northbridge Citizens Services ¦ Branding & Setup
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Configure organisation identity, dates, thresholds and controlled lists before replacing demo content with live discovery data.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  | Back to Start
Core identity inputs | [6 empty] | Deployment notes
Organisation name | Northbridge Citizens Services | [5 empty] | Use this file as the production command pack baseline. Configure the identity cells, check the release checklist, then duplicate the workbook before replacing demo records. Hidden admin sheets control lists, QA and dashboard logic.
Programme / initiative | Citizen Services Transformation
Discovery stream | Case & Contact Service Discovery
Report date | 2026-02-12
Discovery start date | 2026-01-15
Target recommendation date | 2026-02-28 | [5 empty] | Branding guardrails • Use Deep Navy, Slate and Electric Blue only. • Keep headings crisp and practical. • Avoid adding decorative shapes or noisy colour treatments.
Primary contact | discovery.office@example.org
Executive sponsor | Chloe Morgan
Discovery lead | Aisha Khan
Thresholds and tolerances | [6 empty] | Release checklist
Stakeholder engagement amber threshold | 60% | [5 empty] | Update organisation, initiative and report date |  |  | Done
Stakeholder engagement green threshold | 85% | [5 empty] | Review business area and dropdown values |  |  | Done
Evidence coverage amber threshold | 50% | [5 empty] | Review threshold settings |  |  | Done
Evidence coverage green threshold | 75% | [5 empty] | Hide About tab if not needed internally |  |  | Pending
Recommendation amber threshold | 60% | [5 empty] | Clear demo data for live deployment |  |  | Pending
Recommendation green threshold | 85%
Open high risk tolerance | 3 | [7 empty] | V2.1 Production

## 03 User Guidance
Northbridge Citizens Services ¦ User Guidance
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Working guidance for analysts and discovery leads. Use these notes to keep evidence capture, analysis and recommendation quality consistent.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  | Back to Start
Purpose | [6 empty] | What good looks like
Discovery should reduce ambiguity, not just collect opinions. Use the command pack to connect problem framing, stakeholder evidence, opportunity analysis and recommendation quality. | [6 empty] | Evidence is explicit, confidence is visible, stakeholder coverage is intentional, hypotheses are testable and recommendations can be traced back to real problems.
Working principles | [6 empty] | Evidence standard
• Start with the problem, not the solution. • Separate evidence from assumption. • Link every major conclusion to a source. • Record risks, dependencies and unresolved decisions as you go. • Keep language concise enough for sponsors to absorb quickly. | [6 empty] | Prefer evidence that can be cited: interviews, workshops, process data, policy, MI or user feedback. Low-confidence observations can stay in play, but mark them clearly and revisit before recommendation.
Recommended rhythm | [6 empty] | Outputs to leave discovery with
1. Configure the workbook and confirm scope. 2. Baseline stakeholders and plan evidence capture. 3. Capture current state, pain points and evidence. 4. Shape opportunities, hypotheses and concepts. 5. Assess options, decisions, risks and recommendations. 6. Finalise the outcome summary and next steps. | [6 empty] | • Agreed scope and discovery plan • Stakeholder baseline and evidence register • Evidence-backed pain points and opportunities • Shortlisted concepts and option assessment • Risks, decisions, actions and a decision-ready recommendation
Common failure modes
Do not allow dashboards to become decorative. If stakeholder engagement is weak, evidence is patchy or recommendation readiness is low, stop and investigate the quality of the underlying inputs before moving into design or delivery planning.
Agile requirements hand-off
Use 27 Agile Requirements Export after the discovery recommendation has been reviewed. The sheet consolidates concepts, opportunities, recommendations, hypotheses and high-priority pain points into the exact import structure required by the StratForge Agile Requirements Planner.
Copy the export table as values only. Avoid live links between the Discovery workbook and the Agile workbook so files remain portable when renamed, emailed, sold or stored in different locations.
White-Label Deployment Guidance
Before live use, duplicate the workbook, confirm your internal status values and business areas, clear dummy data and update the identity tab. Keep the hidden helper sheets intact so formulas, validations and dashboards continue to work.

## 04 Discovery Overview
Northbridge Citizens Services ¦ Discovery Overview
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Sponsor-ready narrative summary of scope, progress, current position and the expected route to recommendation.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  | Back to Start
33.33% |  |  | 85% |  |  |  | 100% |  | 25%
Discovery progress |  |  | Stakeholder engagement |  |  |  | Evidence coverage |  | Recommendation readiness
Initiative snapshot | [6 empty] | Scope and objectives
Organisation | Northbridge Citizens Services | [5 empty] | Scope: contact centre, case management, appointments, payments, digital self-service and operational reporting for citizen services. Objectives: • Define the real service and control problems. • Capture evidence from stakeholders, users, workshops and MI. • Prioritise opportunities and hypotheses. • Prepare a decision-ready recommendation.
Programme / initiative | Citizen Services Transformation
Discovery stream | Case & Contact Service Discovery
Discovery lead | Aisha Khan
Executive sponsor | Chloe Morgan
Target recommendation date | 28-Feb-2026
Current discovery position | [6 empty] | Watchpoints
Mobilisation and current-state analysis are complete. The remaining emphasis is on validating medium-confidence evidence, confirming the option direction and preparing the recommendation pack for sponsor decision. | [6 empty] | • High opportunity pressure still needs disciplined prioritisation. • Security and partner integration constraints may influence final phasing. • Recommendation readiness should not exceed evidence maturity.
Recommended demonstration path
1. Open 05 Executive Dashboard for sponsor-level progress and recommendation signals. 2. Move to 07 Stakeholder & Evidence to demonstrate engagement and evidence quality. 3. Use 08 Opportunity & Options to show convergence from pain points to options. 4. Finish on 26 Outcome Summary to present the decision ask and next steps.

## 05 Executive Dashboard
Northbridge Citizens Services ¦ Executive Dashboard
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Decision cockpit for sponsors. Use it to assess progress, evidence maturity, recommendation readiness and immediate watchouts.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  |  | Back to Start
33.33% |  |  | 85% |  |  |  | 100% |  |  | 25%
Discovery progress |  |  | Stakeholder engagement |  |  |  | Evidence coverage |  |  | Recommendation readiness
What this means | [8 empty] | Immediate watchouts
Progress should only be read as credible when stakeholder engagement and evidence coverage are also strong. Recommendation readiness should trail evidence maturity, not run ahead of it. | [8 empty] | High-priority opportunities and open high risks still need sponsor scrutiny before the route is locked.
Phase completion | [6 empty] | Opportunity priority
Option comparison | [6 empty] | Recommendation status
What to investigate next
• Why recommendation readiness remains lower than opportunity pressure. • Which critical dependencies could change the phasing decision. • Whether sponsor appetite still supports the balanced phased route.

## 06 Operational Dashboard
Northbridge Citizens Services ¦ Operational Dashboard
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Working-team dashboard showing delivery cadence, evidence flow, operational pressure and overdue follow-through.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  |  | Back to Start
80% |  |  | 75% |  |  |  | 40% |  |  | 0
Interviews completed |  |  | Workshops completed |  |  |  | Validated hypotheses |  |  | Open overdue actions
Operational focus | [8 empty] | Immediate watchouts
Use this view to test whether the discovery cadence is healthy. Evidence and activity should flow steadily, with overdue actions reducing rather than accumulating. | [8 empty] | Open overdue actions or a rising open-risk profile usually signal that the team is converging more slowly than the dashboards imply.
Evidence capture by week | [6 empty] | Pain points by business area
Action tracker status | [6 empty] | Open risk profile
What to investigate next
• Which overdue actions are genuinely decision-critical. • Whether evidence capture is balanced across the weeks or bunching late. • Which business areas are still generating disproportionate operational pain.

## 07 Stakeholder & Evidence
Northbridge Citizens Services ¦ Stakeholder & Evidence
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Coverage dashboard for engagement breadth, interview and workshop status, and evidence quality by source.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  |  | Back to Start
85% |  |  | 100% |  |  |  | 80% |  |  | 20
Stakeholder engagement |  |  | High-influence engaged |  |  |  | Interviews completed |  |  | Accepted evidence items
Coverage insight | [8 empty] | Immediate watchouts
This dashboard shows whether the discovery has enough breadth and enough evidence quality to support recommendation-making. | [8 empty] | Unbalanced stakeholder coverage or low-confidence evidence should trigger targeted follow-up before option decisions are finalised.
Stakeholder type coverage | [6 empty] | Interview status
Workshop status | [6 empty] | Evidence source mix
What to investigate next
• Which high-influence stakeholders are still only partially engaged. • Where interview or workshop gaps are creating weak evidence coverage. • Whether accepted evidence is concentrated too heavily in a small number of source types.

## 08 Opportunity & Options
Northbridge Citizens Services ¦ Opportunity & Options
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Convergence dashboard showing how pain points are turning into opportunities, hypotheses, concepts and options.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  |  | Back to Start
25 |  |  | 23 |  |  |  | 40% |  |  | 5
Total opportunities |  |  | High-priority opportunities |  |  |  | Validated hypotheses |  |  | Shortlisted concepts
Decision signal | [8 empty] | Immediate watchouts
This view tests whether the discovery is converging sensibly from pain points to validated opportunities, hypotheses, concepts and scored options. | [8 empty] | A large opportunity backlog with limited validation or weak option separation usually means more evidence is still required.
Opportunity priority | [6 empty] | Opportunity status
Hypothesis status | [6 empty] | Option comparison
What to investigate next
• Which high-priority opportunities still lack validated hypotheses. • Whether shortlisted concepts are sufficiently distinct. • Which option assumptions need explicit sponsor confirmation before recommendation.

## 09 Discovery Plan
Northbridge Citizens Services ¦ Discovery Plan
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Use this sheet to maintain the master discovery milestone plan. Track planned and actual dates, owners, dependencies, slippage and whether each milestone is complete, in progress, at risk or not started. The days-slip and late-flag columns are formula-driven using the report date on Branding & Setup.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  |  | Back to Start
Phase | Workstream | Milestone | Description | Planned Date | Actual Date | Owner | Status | Dependency | Comments | Days Slip | Late Flag
Mobilise | Core | Discovery brief approved | Agree purpose, scope, objectives and sponsorship | 2026-01-15 | 2026-01-15 | Aisha Khan | Complete | None | Initial brief approved | 0 | No
Mobilise | Core | Stakeholder map baselined | Identify sponsors, operational leads, SMEs and users | 2026-01-18 | 2026-01-19 | Aisha Khan | Complete | Brief approved | Updated after sponsor review | 1 | No
Frame | Current State | Problem statement drafted | Capture symptoms, drivers and evidence sources | 2026-01-22 | 2026-01-24 | Aisha Khan | Complete | Stakeholder map | Needed extra sponsor review | 2 | No
Frame | Current State | Current-state workshops complete | Document core journeys and pain points | 2026-01-29 | 2026-02-01 | Nadia Shah | Complete | Problem statement | Additional appointment team session added | 3 | No
Explore | Evidence | Stakeholder interviews complete | Capture frontline, operational and enabling views | 2026-02-05 |  | Aisha Khan | In Progress | Current-state workshops | Two technology interviews still to run | 7 | Yes
Explore | Evidence | Evidence register quality reviewed | Confirm evidence confidence and follow-ups | 2026-02-07 |  | Daniel Green | In Progress | Interviews | Awaiting MI extracts | 5 | Yes
Analyse | Analysis | Opportunities scored | Assess value, feasibility, complexity and fit | 2026-02-10 |  | Aisha Khan | In Progress | Evidence review | Initial scoring complete | 2 | Yes
Analyse | Analysis | Hypotheses prioritised | Agree validation focus for shortlist | 2026-02-12 |  | Nadia Shah | In Progress | Opportunities scored | Sponsor review scheduled | 0 | No
Recommend | Options | Concept shortlist reviewed | Challenge options, dependencies and assumptions | 2026-02-18 |  | Chloe Morgan | Not Started | Hypotheses prioritised | Planned after design authority | -6 | No
Recommend | Options | Option assessment complete | Score options and recommendation rationale | 2026-02-21 |  | Aisha Khan | Not Started | Concept shortlist | Pending validation evidence | -9 | No
Recommend | Outputs | Recommendation pack drafted | Prepare outcome summary and decision ask | 2026-02-24 |  | Aisha Khan | Not Started | Option assessment |  | -12 | No
Recommend | Outputs | Sponsor decision checkpoint | Review recommendation and confirm next phase | 2026-02-28 |  | Chloe Morgan | Not Started | Recommendation pack |  | -16 | No

## 10 Stakeholder Register
Northbridge Citizens Services ¦ Stakeholder Register
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Maintain the discovery stakeholder model here. Capture who matters, why they matter, how they are engaged, whether interviews and workshops are complete and what next action is required.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked | [7 empty] | Back to Start
Stakeholder ID | Name | Role | Team | Stakeholder Type | Influence | Interest | Engagement Strategy | Interview Status | Workshop Participation | Decision Forum | Business Area | Owner | Next Action | Engaged?
STK-001 | Chloe Morgan | Executive Sponsor | Transformation Office | Sponsor | High | High | Manage Closely | Completed | Attended | Steering Group | Contact Centre | Aisha Khan | Review recommendation pack | Yes
STK-002 | Aisha Khan | Discovery Lead | Business Analysis | Business Lead | High | High | Manage Closely | Completed | Co-Facilitator | Programme Board | Case Management | Aisha Khan | Confirm option scoring assumptions | Yes
STK-003 | Nadia Shah | Service Design Lead | Service Design | Business Lead | High | High | Manage Closely | Completed | Attended | Service Design Authority | Digital Self-Service | Aisha Khan | Validate target-state assumptions | Yes
STK-004 | Tom Patel | Operations Manager | Operations | Operations | High | High | Manage Closely | Completed | Attended | Working Group | Contact Centre | Aisha Khan | Review agent pain points | Yes
STK-005 | Priya Nair | Casework Lead | Operations | Operations | High | High | Manage Closely | Completed | Attended | Working Group | Case Management | Aisha Khan | Confirm case routing issues | Yes
STK-006 | Jessica Reed | Appointments Lead | Operations | Operations | Medium | High | Keep Satisfied | Completed | Attended | Working Group | Appointments | Aisha Khan | Validate booking exceptions | Yes
STK-007 | Marcus Bell | Finance Manager | Finance | Business Lead | Medium | Medium | Keep Satisfied | Completed | Invited | Programme Board | Payments | Aisha Khan | Review payment reconciliation findings | Yes
STK-008 | Sophie Lewis | Digital Product Owner | Digital | Product | High | High | Manage Closely | Completed | Attended | Service Design Authority | Digital Self-Service | Aisha Khan | Refine self-service opportunity list | Yes
STK-009 | Daniel Green | Data Lead | Data & MI | Data | Medium | Medium | Keep Informed | Completed | Invited | Working Group | Reporting & Insight | Aisha Khan | Confirm reporting dependencies | Yes
STK-010 | Amira Yusuf | Technology Lead | IT | IT | High | Medium | Keep Satisfied | Completed | Invited | Programme Board | Case Management | Aisha Khan | Review integration constraints | Yes
STK-011 | Liam Foster | Security Manager | Security | Security | Medium | Medium | Keep Satisfied | Scheduled | Invited | Service Design Authority | Digital Self-Service | Aisha Khan | Confirm identity and access constraints | No
STK-012 | Emma Grant | PMO Lead | PMO | PMO | Medium | Low | Keep Informed | Completed | Invited | Programme Board | Reporting & Insight | Aisha Khan | Track decision actions | Yes
STK-013 | Noah Price | Frontline Adviser | Customer Services | Frontline User | Low | High | Keep Informed | Completed | Attended | None | Contact Centre | Aisha Khan | Capture adviser workaround details | Yes
STK-014 | Grace Hall | Senior Caseworker | Operations | Frontline User | Low | High | Keep Informed | Completed | Attended | None | Case Management | Aisha Khan | Validate hand-off pain points | Yes
STK-015 | Owen Clarke | Booking Administrator | Operations | Frontline User | Low | High | Keep Informed | Completed | Attended | None | Appointments | Aisha Khan | Confirm rebooking failure modes | Yes
STK-016 | Maya Singh | Payments Analyst | Finance | SME | Low | Medium | Keep Informed | Completed | Invited | Working Group | Payments | Aisha Khan | Confirm refund controls | Yes
STK-017 | Ethan Wood | Reporting Analyst | Data & MI | Data | Low | Medium | Keep Informed | Scheduled | Invited | Working Group | Reporting & Insight | Aisha Khan | Review MI gaps | No
STK-018 | Ruby Cooper | Partner Services Manager | Partner Ops | Partner | Medium | Medium | Monitor | Scheduled | Invited | Working Group | Appointments | Aisha Khan | Confirm partner booking process | No
STK-019 | Ben Carter | Policy Manager | Policy | SME | Medium | Medium | Keep Satisfied | Completed | Invited | Steering Group | Case Management | Aisha Khan | Check statutory constraints | Yes
STK-020 | Lena Brooks | Change Lead | Change & Training | Business Lead | Medium | High | Keep Satisfied | Completed | Attended | Programme Board | Contact Centre | Aisha Khan | Define adoption implications | Yes

## 11 Problem Canvas
Northbridge Citizens Services ¦ Problem Canvas
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Define the real problem, not just symptoms. Use evidence-backed statements and revisit as confidence improves.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  | Back to Start
Current Situation | [5 empty] | Strategic Context
Citizen services are delivered across phone, casework, appointment, payment and digital channels, but the current operating model relies on fragmented workflow, uneven reporting and significant manual workarounds. | [5 empty] | The transformation programme aims to reduce avoidable demand, improve citizen experience, strengthen operational control and create a more scalable service model without losing compliance and audit confidence.
Symptoms | [5 empty] | Root Causes
Customers repeat information, appointment issues generate avoidable contact, teams hold inconsistent backlog figures, and staff spend time compensating for workflow and guidance gaps. | [5 empty] | Core causes include fragmented systems, limited integration, inconsistent workflow design, weak taxonomy / data standards, low-quality guidance ownership and incomplete governance controls.
Affected Users | [5 empty] | Constraints & Dependencies
Frontline advisers, caseworkers, booking teams, finance analysts, managers, digital teams and citizens all experience different forms of friction in the current model. | [5 empty] | Partner calendar integration, security review, policy constraints, platform capability and sponsor appetite for phasing all shape what is realistic in the near term.
Risks of Doing Nothing | [5 empty] | Evidence Sources
Operational demand will remain avoidably high, control issues will persist, staff workarounds will continue to absorb capacity and leaders will keep making decisions on inconsistent information. | [5 empty] | Interviews, workshops, MI extracts, policy review, user feedback and system reports have all contributed to the problem framing. Evidence confidence is tracked explicitly elsewhere in the workbook.
Problem Statement Draft
Northbridge citizen services are constrained by fragmented workflow, inconsistent service control and weak cross-channel continuity. This creates avoidable customer effort, manual operational workarounds and unreliable management information. Discovery must determine the most feasible phased improvements that improve control and experience together.

## 12 Current State Analysis
Northbridge Citizens Services ¦ Current State Analysis
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Use this sheet to capture the current operating model across process areas. The improvement-need column is formula-driven using severity, cycle time and manual touchpoints as simple indicators.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  |  | Back to Start
Process Area | Business Area | Systems Involved | User Group | Pain Point Ref | Cycle Time (days) | Manual Touchpoints | Volume / Week | Pain Severity | Evidence Ref | Improvement Need | Notes
Enquiry Intake | Contact Centre | Telephony, CRM, Shared Mailbox | Frontline Advisers | PP-001 | 4 | 2 | 120 | High | EVD-001 | Medium
Enquiry Intake | Contact Centre | Telephony, CRM, Shared Mailbox | Frontline Advisers | PP-002 | 6 | 4 | 240 | High | EVD-002 | Medium
Enquiry Intake | Contact Centre | Telephony, CRM, Shared Mailbox | Frontline Advisers | PP-003 | 10 | 6 | 80 | Critical | EVD-003 | High
Case Creation | Case Management | CRM, Case Workflow, Shared Mailbox | Caseworkers | PP-004 | 3 | 3 | 160 | High | EVD-004 | Medium
Case Creation | Case Management | CRM, Case Workflow, Shared Mailbox | Caseworkers | PP-005 | 7 | 5 | 60 | High | EVD-005 | High
Case Creation | Case Management | CRM, Case Workflow, Shared Mailbox | Caseworkers | PP-006 | 4 | 2 | 300 | Medium | EVD-006 | Medium
Case Triage | Case Management | CRM, Case Workflow, Shared Mailbox | Caseworkers | PP-007 | 4 | 4 | 120 | High | EVD-007 | Medium
Case Handover | Case Management | CRM, Case Workflow, Shared Mailbox | Caseworkers | PP-008 | 7 | 6 | 240 | Critical | EVD-008 | High
Appointment Booking | Appointments | Booking Tool, Partner Calendars, CRM | Booking Administrators | PP-009 | 10 | 3 | 80 | Critical | EVD-009 | High
Appointment Booking | Appointments | Booking Tool, Partner Calendars, CRM | Booking Administrators | PP-010 | 2 | 5 | 160 | Medium | EVD-010 | High
Appointment Booking | Appointments | Booking Tool, Partner Calendars, CRM | Booking Administrators | PP-011 | 7 | 2 | 60 | High | EVD-011 | High
Appointment Attendance | Appointments | Booking Tool, Partner Calendars, CRM | Booking Administrators | PP-012 | 4 | 4 | 300 | Medium | EVD-012 | Medium
Payment Collection | Payments | Payment Gateway, Finance Ledger, CRM | Finance Analysts | PP-013 | 4 | 6 | 120 | High | EVD-013 | High
Payment Collection | Payments | Payment Gateway, Finance Ledger, CRM | Finance Analysts | PP-014 | 6 | 3 | 240 | High | EVD-014 | Medium
Payment Reconciliation | Payments | Payment Gateway, Finance Ledger, CRM | Finance Analysts | PP-015 | 9 | 5 | 80 | High | EVD-015 | High
Payment Exceptions | Payments | Payment Gateway, Finance Ledger, CRM | Finance Analysts | PP-016 | 2 | 2 | 160 | Medium | EVD-016 | Low
Portal Submission | Digital Self-Service | Portal, Identity Service, CRM | Citizens / Digital Team | PP-017 | 8 | 4 | 60 | Critical | EVD-017 | High
Portal Submission | Digital Self-Service | Portal, Identity Service, CRM | Citizens / Digital Team | PP-018 | 4 | 6 | 300 | Medium | EVD-018 | High
Portal Status | Digital Self-Service | Portal, Identity Service, CRM | Citizens / Digital Team | PP-019 | 4 | 3 | 120 | High | EVD-019 | Medium
Portal Access | Digital Self-Service | Portal, Identity Service, CRM | Citizens / Digital Team | PP-020 | 6 | 5 | 240 | High | EVD-020 | High
Reporting | Reporting & Insight | Data Warehouse, Excel MI Packs, CRM | Managers / Analysts | PP-021 | 10 | 2 | 80 | Critical | EVD-021 | High
Reporting | Reporting & Insight | Data Warehouse, Excel MI Packs, CRM | Managers / Analysts | PP-022 | 3 | 4 | 160 | High | EVD-022 | Medium
Reporting | Reporting & Insight | Data Warehouse, Excel MI Packs, CRM | Managers / Analysts | PP-023 | 6 | 6 | 60 | Medium | EVD-023 | High
Cross-Channel Journey | Contact Centre | Telephony, CRM, Shared Mailbox | Frontline Advisers | PP-024 | 6 | 3 | 300 | Critical | EVD-024 | High

## 13 Pain Point Register
Northbridge Citizens Services ¦ Pain Point Register
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Capture specific pain points, their severity, frequency, root-cause hypothesis and evidence. The score and priority columns are formula-driven so the register immediately highlights the biggest problems.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked | [5 empty] | Back to Start
Pain Point ID | Process Area | Business Area | Description | Severity | Frequency | Affected Users | Root Cause Hypothesis | Impact Type | Evidence Ref | Score | Priority | Action Needed
PP-001 | Enquiry Intake | Contact Centre | Advisers re-key caller details from email summaries into the case system. | High | Daily | Frontline Advisers | Channel hand-off is not integrated | Time / Quality | EVD-001 | 12 | High | Confirm integration options
PP-002 | Enquiry Intake | Contact Centre | Knowledge articles are outdated, so advisers improvise responses. | High | Daily | Frontline Advisers | Content ownership is unclear | Quality / Compliance | EVD-002 | 12 | High | Define content governance
PP-003 | Enquiry Intake | Contact Centre | Call queues do not distinguish vulnerable customers consistently. | Critical | Daily | Frontline Advisers | Routing rules are too broad | Customer Risk | EVD-003 | 16 | High | Prioritise routing criteria review
PP-004 | Case Creation | Case Management | Case categories are interpreted differently across teams. | High | Weekly | Caseworkers | Taxonomy is ambiguous | Quality / Rework | EVD-004 | 9 | Medium | Standardise category definitions
PP-005 | Case Creation | Case Management | Duplicate cases are created when customers follow up through multiple channels. | High | Daily | Caseworkers | No duplicate detection at intake | Efficiency | EVD-005 | 12 | High | Assess duplicate matching options
PP-006 | Case Creation | Case Management | Mandatory data fields are bypassed using free-text workarounds. | Medium | Daily | Caseworkers | Validation rules are incomplete | Data Quality | EVD-006 | 8 | Medium | Review validation rule set
PP-007 | Case Triage | Case Management | Priority rules are inconsistent between service teams. | High | Weekly | Team Leaders | Local spreadsheets override standard rules | Control | EVD-007 | 9 | Medium | Baseline triage logic
PP-008 | Case Handover | Case Management | Internal hand-offs rely on email and are not visible end to end. | Critical | Daily | Caseworkers | Workflow tasking is not configured | Delay / Visibility | EVD-008 | 16 | High | Design task-based routing
PP-009 | Appointment Booking | Appointments | Agents cannot see real-time slot availability for partner calendars. | Critical | Daily | Booking Administrators | Partner integration is batch-based | Customer Experience | EVD-009 | 16 | High | Explore near real-time integration
PP-010 | Appointment Booking | Appointments | Rebooking generates duplicate notifications to citizens. | Medium | Weekly | Booking Administrators | Notification logic does not suppress superseded messages | Customer Experience | EVD-010 | 6 | Low | Fix notification trigger logic
PP-011 | Appointment Booking | Appointments | Failed bookings are not captured with useful failure reasons. | High | Weekly | Booking Administrators | Error handling is generic | Operational Insight | EVD-011 | 9 | Medium | Improve failure reason capture
PP-012 | Appointment Attendance | Appointments | No-shows are recorded late, affecting slot reuse. | Medium | Weekly | Operations Managers | Attendance updates depend on manual end-of-day checks | Capacity | EVD-012 | 6 | Low | Assess same-day attendance updates
PP-013 | Payment Collection | Payments | Agents leave the case screen to take payments in a separate tool. | High | Daily | Payments Analysts | Payment tool is not embedded in workflow | Efficiency | EVD-013 | 12 | High | Evaluate embedded payment experience
PP-014 | Payment Collection | Payments | Refund approvals are tracked in email, not in the case record. | High | Weekly | Finance Managers | Approval workflow is off-system | Control / Audit | EVD-014 | 9 | Medium | Define on-platform approval trail
PP-015 | Payment Reconciliation | Payments | Daily reconciliation takes too long because references are inconsistent. | High | Weekly | Finance Analysts | Reference data is incomplete | Time / Control | EVD-015 | 9 | Medium | Improve payment reference design
PP-016 | Payment Exceptions | Payments | Chargeback cases are managed outside the main service process. | Medium | Monthly | Finance Analysts | Exception handling is not integrated | Control | EVD-016 | 4 | Low | Map exception path into core design
PP-017 | Portal Submission | Digital Self-Service | Customers abandon the portal because the save-and-resume flow is unreliable. | Critical | Daily | Citizens | Session persistence is weak | Customer Experience | EVD-017 | 16 | High | Investigate save-and-resume redesign
PP-018 | Portal Submission | Digital Self-Service | Supporting documents can be uploaded only one at a time. | Medium | Daily | Citizens | Upload component is limited | Efficiency | EVD-018 | 8 | Medium | Review multi-file upload capability
PP-019 | Portal Status | Digital Self-Service | Citizens cannot see meaningful case progress updates online. | High | Daily | Citizens | Status model is too generic | Customer Experience | EVD-019 | 12 | High | Design clearer customer-facing statuses
PP-020 | Portal Access | Digital Self-Service | Identity verification failures generate high avoidable contact. | High | Weekly | Citizens | Error messages do not explain remediation | Demand / Customer Experience | EVD-020 | 9 | Medium | Improve identity failure journeys
PP-021 | Reporting | Reporting & Insight | Leaders receive different backlog figures from different teams. | Critical | Weekly | Managers | Definitions and cut-off rules differ | Decision Quality | EVD-021 | 12 | High | Define common reporting logic
PP-022 | Reporting | Reporting & Insight | Operational MI is refreshed too slowly for daily decision-making. | High | Daily | Managers | Refresh cadence is overnight only | Timeliness | EVD-022 | 12 | High | Assess intraday reporting options
PP-023 | Reporting | Reporting & Insight | Root-cause reporting is manual and inconsistent. | Medium | Weekly | Analysts | Case fields do not support consistent coding | Insight Quality | EVD-023 | 6 | Low | Improve root-cause fields
PP-024 | Cross-Channel Journey | Contact Centre | Customers repeat information when moving from web to phone. | Critical | Daily | Citizens / Advisers | Interaction context is not shared across channels | Customer Experience | EVD-024 | 16 | High | Prioritise cross-channel context sharing
PP-025 | Knowledge & Guidance | Contact Centre | Supervisors spend too much time answering repeat process questions. | Medium | Daily | Supervisors | Guidance is scattered across shared drives | Efficiency | EVD-025 | 8 | Medium | Consolidate operational guidance
PP-026 | Case Closure | Case Management | Closure reasons are too broad to support meaningful analysis. | Medium | Weekly | Caseworkers | Closure taxonomy is under-designed | Insight Quality | EVD-026 | 6 | Low | Refine closure reasons
PP-027 | Appointment Confirmations | Appointments | Outbound reminders cannot be tailored by appointment type. | Low | Weekly | Booking Team | Template logic is too simple | Customer Experience | EVD-027 | 3 | Low | Assess rule-based reminders
PP-028 | Payments | Payments | Staff cannot easily see whether a payment relates to multiple cases. | Medium | Weekly | Payments Analysts | Payment-to-case mapping is one-to-one only | Control | EVD-028 | 6 | Low | Assess multi-case payment mapping
PP-029 | Digital Accessibility | Digital Self-Service | Accessibility issues are logged but not prioritised into improvements. | High | Monthly | Digital Team | Accessibility backlog is not linked to service priorities | Compliance | EVD-029 | 6 | Low | Establish prioritisation model
PP-030 | Management Oversight | Reporting & Insight | Actions raised in governance meetings are not tracked centrally. | High | Weekly | Programme Leads | Actions are scattered across decks and emails | Governance | EVD-030 | 9 | Medium | Introduce single action tracker

## 14 Interview Log
Northbridge Citizens Services ¦ Interview Log
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Use this sheet to capture stakeholder interviews, themes, follow-up actions and evidence confidence. The overdue flag checks follow-up due dates against the report date.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked | [6 empty] | Back to Start
Interview ID | Stakeholder | Role | Business Area | Interview Date | Status | Key Themes | Insight Summary | Confidence | Follow-up Required | Follow-up Owner | Follow-up Due | Overdue? | Source Ref
INT-001 | Chloe Morgan | Executive Sponsor | Contact Centre | 2026-01-16 | Completed | Strategic outcomes; avoidable demand; governance | Sponsor wants fewer repeat contacts and better operational visibility. | High | Yes | Aisha Khan | 2026-01-22 | Yes | EVD-001
INT-002 | Tom Patel | Operations Manager | Contact Centre | 2026-01-20 | Completed | Queue management; routing; knowledge gaps | Advisers compensate for weak routing and outdated guidance every day. | High | Yes | Aisha Khan | 2026-01-24 | Yes | EVD-002
INT-003 | Priya Nair | Casework Lead | Case Management | 2026-01-21 | Completed | Case creation; triage; hand-off | Case hand-offs are opaque and duplicate cases are common. | High | No | Aisha Khan | 2026-01-28 | No | EVD-004
INT-004 | Jessica Reed | Appointments Lead | Appointments | 2026-01-23 | Completed | Booking failures; partner calendars | Appointment failures are hidden behind generic errors. | High | Yes | Aisha Khan | 2026-01-29 | Yes | EVD-009
INT-005 | Marcus Bell | Finance Manager | Payments | 2026-01-24 | Completed | Payment controls; refunds; reconciliation | Refund approval and reconciliation lack auditable workflow support. | High | No | Aisha Khan | 2026-01-30 | No | EVD-014
INT-006 | Sophie Lewis | Digital Product Owner | Digital Self-Service | 2026-01-25 | Completed | Portal friction; save and resume; status visibility | Customers lose trust because the portal gives weak progress feedback. | High | Yes | Aisha Khan | 2026-02-02 | Yes | EVD-017
INT-007 | Daniel Green | Data Lead | Reporting & Insight | 2026-01-27 | Completed | MI refresh; backlog definitions | Leaders are comparing inconsistent numbers from different teams. | Medium | Yes | Aisha Khan | 2026-02-04 | Yes | EVD-021
INT-008 | Noah Price | Frontline Adviser | Contact Centre | 2026-01-28 | Completed | Channel context; workarounds | Advisers ask customers to repeat context because web interactions are invisible. | High | No | Aisha Khan | 2026-02-05 | No | EVD-024
INT-009 | Grace Hall | Senior Caseworker | Case Management | 2026-01-29 | Completed | Hand-offs; closure reasons | Closure coding is too broad to support improvement work. | Medium | No | Aisha Khan | 2026-02-06 | No | EVD-026
INT-010 | Owen Clarke | Booking Administrator | Appointments | 2026-01-30 | Completed | Rebooking; reminder logic | Manual rebooking creates duplicate notifications and avoidable calls. | Medium | No | Aisha Khan | 2026-02-06 | No | EVD-010
INT-011 | Maya Singh | Payments Analyst | Payments | 2026-02-03 | Completed | Chargebacks; payment mapping | Staff use spreadsheets to understand payment exceptions and case relationships. | Medium | Yes | Aisha Khan | 2026-02-10 | Yes | EVD-028
INT-012 | Liam Foster | Security Manager | Digital Self-Service | 2026-02-06 | Scheduled | Identity verification; access controls | Security review is needed before portal improvements can be recommended. | Medium | Yes | Aisha Khan | 2026-02-14 | No | EVD-020
INT-013 | Ruby Cooper | Partner Services Manager | Appointments | 2026-02-07 | Scheduled | Partner booking integration | Partner calendars drive a large share of booking failures. | Medium | Yes | Aisha Khan | 2026-02-15 | No | EVD-009
INT-014 | Ethan Wood | Reporting Analyst | Reporting & Insight | 2026-02-09 | Scheduled | Intraday reporting and root-cause coding | Analysts need better case fields before MI can support root-cause insight. | Medium | Yes | Aisha Khan | 2026-02-16 | No | EVD-023
INT-015 | Lena Brooks | Change Lead | Contact Centre | 2026-02-10 | Completed | Adoption; training; guidance | Supervisors need fewer scattered guidance sources and clearer ownership. | Medium | No | Aisha Khan | 2026-02-18 | No | EVD-025

## 15 Workshop Planner
Northbridge Citizens Services ¦ Workshop Planner
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Plan and track discovery workshops here. Maintain objectives, dates, participants, status and whether outputs have been captured in the supporting notes and registers.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  |  | Back to Start
Workshop ID | Workshop Title | Objective | Facilitator | Planned Date | Actual Date | Participants | Status | Outputs Captured | Follow-up Actions | Overdue? | Notes
WS-001 | Discovery Kick-off | Align objectives, scope, roles and cadence | Aisha Khan | 2026-01-17 | 2026-01-17 | Sponsor, Lead BA, Operations, Product | Complete | Yes | 3 actions raised | No
WS-002 | Current-State Contact Centre | Map intake, routing and adviser workarounds | Nadia Shah | 2026-01-22 | 2026-01-22 | Contact Centre Ops, Advisers, Change | Complete | Yes | 5 actions raised | No
WS-003 | Current-State Case Management | Map case creation, triage and hand-offs | Nadia Shah | 2026-01-26 | 2026-01-26 | Case Leads, Policy, BA | Complete | Yes | 4 actions raised | No
WS-004 | Appointments Journey | Review booking, rebooking and partner calendars | Nadia Shah | 2026-01-30 | 2026-01-30 | Appointments Team, Partners, BA | Complete | Yes | 4 actions raised | No
WS-005 | Payments and Controls | Review payment flow, exceptions and reconciliation | Aisha Khan | 2026-02-03 | 2026-02-03 | Finance, Ops, BA | Complete | Yes | 3 actions raised | No
WS-006 | Portal and Customer Experience | Review portal drop-off, status and identity | Sophie Lewis | 2026-02-05 | 2026-02-05 | Digital, Service Design, Security | Complete | Yes | 4 actions raised | No
WS-007 | Opportunity Prioritisation | Score opportunities and shape shortlist | Aisha Khan | 2026-02-13 |  | In Progress | No | Follow-up scoring session pending | No | Sponsor availability issue
WS-008 | Recommendation Review | Challenge options, risks and recommendation | Chloe Morgan | 2026-02-20 |  | Planned | No | Planned after option scoring | No

## 16 Workshop Notes
Northbridge Citizens Services ¦ Workshop Notes
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Capture workshop notes in a structured format. Link insights back to pain points and opportunities so the discovery trail remains traceable and reusable.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  | Back to Start
Note ID | Workshop ID | Topic | Insight | Pain Point Ref | Opportunity Ref | Evidence Quality | Owner | Action Required | Comments
NOTE-001 | WS-002 | Enquiry Intake | Advisers re-key caller details from email summaries into the case system. | PP-001 | OPP-001 | High | Aisha Khan | Yes
NOTE-002 | WS-003 | Enquiry Intake | Knowledge articles are outdated, so advisers improvise responses. | PP-002 | OPP-002 | High | Nadia Shah | Yes
NOTE-003 | WS-004 | Enquiry Intake | Call queues do not distinguish vulnerable customers consistently. | PP-003 | OPP-003 | Medium | Tom Patel | No
NOTE-004 | WS-005 | Case Creation | Case categories are interpreted differently across teams. | PP-004 |  | High | Priya Nair | Yes | Follow-up needed with enabling teams.
NOTE-005 | WS-006 | Case Creation | Duplicate cases are created when customers follow up through multiple channels. | PP-005 | OPP-004 | Very High | Jessica Reed | Yes
NOTE-006 | WS-007 | Case Creation | Mandatory data fields are bypassed using free-text workarounds. | PP-006 | OPP-025 | Medium | Marcus Bell | No
NOTE-007 | WS-002 | Case Triage | Priority rules are inconsistent between service teams. | PP-007 |  | High | Aisha Khan | Yes
NOTE-008 | WS-003 | Case Handover | Internal hand-offs rely on email and are not visible end to end. | PP-008 | OPP-005 | High | Nadia Shah | Yes | Follow-up needed with enabling teams.
NOTE-009 | WS-004 | Appointment Booking | Agents cannot see real-time slot availability for partner calendars. | PP-009 | OPP-006 | Medium | Tom Patel | No
NOTE-010 | WS-005 | Appointment Booking | Rebooking generates duplicate notifications to citizens. | PP-010 | OPP-007 | High | Priya Nair | Yes
NOTE-011 | WS-006 | Appointment Booking | Failed bookings are not captured with useful failure reasons. | PP-011 | OPP-008 | Very High | Jessica Reed | Yes
NOTE-012 | WS-007 | Appointment Attendance | No-shows are recorded late, affecting slot reuse. | PP-012 |  | Medium | Marcus Bell | No
NOTE-013 | WS-002 | Payment Collection | Agents leave the case screen to take payments in a separate tool. | PP-013 | OPP-009 | High | Aisha Khan | Yes
NOTE-014 | WS-003 | Payment Collection | Refund approvals are tracked in email, not in the case record. | PP-014 | OPP-010 | High | Nadia Shah | Yes
NOTE-015 | WS-004 | Payment Reconciliation | Daily reconciliation takes too long because references are inconsistent. | PP-015 | OPP-011 | Medium | Tom Patel | No
NOTE-016 | WS-005 | Payment Exceptions | Chargeback cases are managed outside the main service process. | PP-016 |  | High | Priya Nair | Yes | Follow-up needed with enabling teams.
NOTE-017 | WS-006 | Portal Submission | Customers abandon the portal because the save-and-resume flow is unreliable. | PP-017 | OPP-012 | Very High | Jessica Reed | Yes
NOTE-018 | WS-007 | Portal Submission | Supporting documents can be uploaded only one at a time. | PP-018 | OPP-013 | Medium | Marcus Bell | No
NOTE-019 | WS-002 | Portal Status | Citizens cannot see meaningful case progress updates online. | PP-019 | OPP-014 | High | Aisha Khan | Yes
NOTE-020 | WS-003 | Portal Access | Identity verification failures generate high avoidable contact. | PP-020 | OPP-015 | High | Nadia Shah | Yes | Follow-up needed with enabling teams.
NOTE-021 | WS-004 | Reporting | Leaders receive different backlog figures from different teams. | PP-021 | OPP-016 | Medium | Tom Patel | No
NOTE-022 | WS-005 | Reporting | Operational MI is refreshed too slowly for daily decision-making. | PP-022 | OPP-017 | High | Priya Nair | Yes
NOTE-023 | WS-006 | Reporting | Root-cause reporting is manual and inconsistent. | PP-023 | OPP-018 | Very High | Jessica Reed | Yes
NOTE-024 | WS-007 | Cross-Channel Journey | Customers repeat information when moving from web to phone. | PP-024 | OPP-019 | Medium | Marcus Bell | No
NOTE-025 | WS-002 | Knowledge & Guidance | Supervisors spend too much time answering repeat process questions. | PP-025 | OPP-020 | High | Aisha Khan | Yes
NOTE-026 | WS-003 | Case Closure | Closure reasons are too broad to support meaningful analysis. | PP-026 | OPP-021 | High | Nadia Shah | Yes
NOTE-027 | WS-004 | Appointment Confirmations | Outbound reminders cannot be tailored by appointment type. | PP-027 |  | Medium | Tom Patel | No
NOTE-028 | WS-005 | Payments | Staff cannot easily see whether a payment relates to multiple cases. | PP-028 | OPP-022 | High | Priya Nair | Yes | Follow-up needed with enabling teams.
NOTE-029 | WS-006 | Digital Accessibility | Accessibility issues are logged but not prioritised into improvements. | PP-029 | OPP-023 | Very High | Jessica Reed | Yes
NOTE-030 | WS-007 | Management Oversight | Actions raised in governance meetings are not tracked centrally. | PP-030 | OPP-024 | Medium | Marcus Bell | No

## 17 Evidence Register
Northbridge Citizens Services ¦ Evidence Register
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Maintain the evidence register to show where insights come from and how reliable they are. Confidence and acceptance are explicit so recommendation quality can be challenged transparently.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked | [5 empty] | Back to Start
Evidence ID | Source Type | Source Name | Date Captured | Business Area | Topic | Summary | Confidence | Linked Pain Points | Linked Opportunities | Owner | Accepted? | Quality Score
EVD-001 | Interview | Interview pack 1 | 2026-01-18 | Contact Centre | Enquiry Intake | Advisers re-key caller details from email summaries into the case system. | High | PP-001 | OPP-001 | Aisha Khan | Yes | 4
EVD-002 | Workshop | Workshop notes batch 2 | 2026-01-20 | Contact Centre | Enquiry Intake | Knowledge articles are outdated, so advisers improvise responses. | Very High | PP-002 | OPP-002 | Nadia Shah | Yes | 5
EVD-003 | Process Data | Operational MI extract | 2026-01-22 | Contact Centre | Enquiry Intake | Call queues do not distinguish vulnerable customers consistently. | High | PP-003 | OPP-003 | Aisha Khan | Yes | 4
EVD-004 | Policy | Policy / guidance review | 2026-01-24 | Case Management | Case Creation | Case categories are interpreted differently across teams. | Medium | PP-004 |  | Nadia Shah | No | 2
EVD-005 | User Feedback | Citizen feedback sample | 2026-01-26 | Case Management | Case Creation | Duplicate cases are created when customers follow up through multiple channels. | High | PP-005 | OPP-004 | Aisha Khan | Yes | 4
EVD-006 | System Report | System usage report | 2026-01-28 | Case Management | Case Creation | Mandatory data fields are bypassed using free-text workarounds. | Medium | PP-006 | OPP-025 | Nadia Shah | No | 2
EVD-007 | Interview | Interview pack 2 | 2026-01-30 | Case Management | Case Triage | Priority rules are inconsistent between service teams. | High | PP-007 |  | Aisha Khan | Yes | 4
EVD-008 | Workshop | Workshop notes batch 4 | 2026-02-01 | Case Management | Case Handover | Internal hand-offs rely on email and are not visible end to end. | Very High | PP-008 | OPP-005 | Nadia Shah | Yes | 5
EVD-009 | Process Data | Operational MI extract | 2026-02-03 | Appointments | Appointment Booking | Agents cannot see real-time slot availability for partner calendars. | High | PP-009 | OPP-006 | Aisha Khan | Yes | 4
EVD-010 | Policy | Policy / guidance review | 2026-02-05 | Appointments | Appointment Booking | Rebooking generates duplicate notifications to citizens. | Medium | PP-010 | OPP-007 | Nadia Shah | No | 2
EVD-011 | User Feedback | Citizen feedback sample | 2026-02-07 | Appointments | Appointment Booking | Failed bookings are not captured with useful failure reasons. | High | PP-011 | OPP-008 | Aisha Khan | Yes | 4
EVD-012 | System Report | System usage report | 2026-02-09 | Appointments | Appointment Attendance | No-shows are recorded late, affecting slot reuse. | Medium | PP-012 |  | Nadia Shah | No | 2
EVD-013 | Interview | Interview pack 3 | 2026-02-11 | Payments | Payment Collection | Agents leave the case screen to take payments in a separate tool. | High | PP-013 | OPP-009 | Aisha Khan | Yes | 4
EVD-014 | Workshop | Workshop notes batch 2 | 2026-02-13 | Payments | Payment Collection | Refund approvals are tracked in email, not in the case record. | Very High | PP-014 | OPP-010 | Nadia Shah | Yes | 5
EVD-015 | Process Data | Operational MI extract | 2026-01-16 | Payments | Payment Reconciliation | Daily reconciliation takes too long because references are inconsistent. | High | PP-015 | OPP-011 | Aisha Khan | Yes | 4
EVD-016 | Policy | Policy / guidance review | 2026-01-18 | Payments | Payment Exceptions | Chargeback cases are managed outside the main service process. | Medium | PP-016 |  | Nadia Shah | No | 2
EVD-017 | User Feedback | Citizen feedback sample | 2026-01-20 | Digital Self-Service | Portal Submission | Customers abandon the portal because the save-and-resume flow is unreliable. | High | PP-017 | OPP-012 | Aisha Khan | Yes | 4
EVD-018 | System Report | System usage report | 2026-01-22 | Digital Self-Service | Portal Submission | Supporting documents can be uploaded only one at a time. | Medium | PP-018 | OPP-013 | Nadia Shah | No | 2
EVD-019 | Interview | Interview pack 4 | 2026-01-24 | Digital Self-Service | Portal Status | Citizens cannot see meaningful case progress updates online. | High | PP-019 | OPP-014 | Aisha Khan | Yes | 4
EVD-020 | Workshop | Workshop notes batch 4 | 2026-01-26 | Digital Self-Service | Portal Access | Identity verification failures generate high avoidable contact. | Very High | PP-020 | OPP-015 | Nadia Shah | Yes | 5
EVD-021 | Process Data | Operational MI extract | 2026-01-28 | Reporting & Insight | Reporting | Leaders receive different backlog figures from different teams. | High | PP-021 | OPP-016 | Aisha Khan | Yes | 4
EVD-022 | Policy | Policy / guidance review | 2026-01-30 | Reporting & Insight | Reporting | Operational MI is refreshed too slowly for daily decision-making. | Medium | PP-022 | OPP-017 | Nadia Shah | No | 2
EVD-023 | User Feedback | Citizen feedback sample | 2026-02-01 | Reporting & Insight | Reporting | Root-cause reporting is manual and inconsistent. | High | PP-023 | OPP-018 | Aisha Khan | Yes | 4
EVD-024 | System Report | System usage report | 2026-02-03 | Contact Centre | Cross-Channel Journey | Customers repeat information when moving from web to phone. | Medium | PP-024 | OPP-019 | Nadia Shah | No | 2
EVD-025 | Interview | Interview pack 5 | 2026-02-05 | Contact Centre | Knowledge & Guidance | Supervisors spend too much time answering repeat process questions. | High | PP-025 | OPP-020 | Aisha Khan | Yes | 4
EVD-026 | Workshop | Workshop notes batch 2 | 2026-02-07 | Case Management | Case Closure | Closure reasons are too broad to support meaningful analysis. | Very High | PP-026 | OPP-021 | Nadia Shah | Yes | 5
EVD-027 | Process Data | Operational MI extract | 2026-02-09 | Appointments | Appointment Confirmations | Outbound reminders cannot be tailored by appointment type. | High | PP-027 |  | Aisha Khan | Yes | 4
EVD-028 | Policy | Policy / guidance review | 2026-02-11 | Payments | Payments | Staff cannot easily see whether a payment relates to multiple cases. | Medium | PP-028 | OPP-022 | Nadia Shah | No | 2
EVD-029 | User Feedback | Citizen feedback sample | 2026-02-13 | Digital Self-Service | Digital Accessibility | Accessibility issues are logged but not prioritised into improvements. | High | PP-029 | OPP-023 | Aisha Khan | Yes | 4
EVD-030 | System Report | System usage report | 2026-01-16 | Reporting & Insight | Management Oversight | Actions raised in governance meetings are not tracked centrally. | Medium | PP-030 | OPP-024 | Nadia Shah | No | 2

## 18 Opportunity Register
Northbridge Citizens Services ¦ Opportunity Register
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Use this register to move from pain points to structured improvement opportunities. Score, priority and recommendation flags are formula-driven to support consistent triage.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked | [6 empty] | Back to Start
Opportunity ID | Pain Point Ref | Business Area | Description | Value | Feasibility | Complexity | Strategic Alignment | Priority | Owner | Evidence Ref | Score | Status | Recommended?
OPP-001 | PP-001 | Contact Centre | Introduce channel context hand-off so adviser screens are pre-populated when customers move from web or email to phone. | Very High | Medium | Medium | High | High | Aisha Khan | EVD-001 | 4.2 | Assessed | No
OPP-002 | PP-002 | Contact Centre | Establish owned knowledge articles with review cadence and operational quality metrics. | High | High | Low | High | Critical | Lena Brooks | EVD-002 | 4.7 | Assessed | No
OPP-003 | PP-003 | Contact Centre | Refine routing rules and customer segmentation for vulnerable callers. | Very High | Medium | Medium | High | High | Tom Patel | EVD-003 | 4.2 | Shortlisted | No
OPP-004 | PP-005 | Case Management | Add duplicate detection and merge guidance at intake. | High | High | Medium | High | Critical | Priya Nair | EVD-005 | 4.4 | Shortlisted | No
OPP-005 | PP-008 | Case Management | Introduce task-based workflow for internal hand-offs with audit trail. | Very High | Medium | High | High | High | Priya Nair | EVD-008 | 3.9 | Shortlisted | No
OPP-006 | PP-009 | Appointments | Integrate partner calendar availability into the core booking experience. | Very High | Low | High | High | Medium | Jessica Reed | EVD-009 | 3.4 | Recommended | Yes
OPP-007 | PP-010 | Appointments | Suppress obsolete appointment notifications during rebooking. | Medium | High | Low | Medium | High | Jessica Reed | EVD-010 | 3.8 | Assessed | No
OPP-008 | PP-011 | Appointments | Capture structured booking failure reasons for analysis and recovery. | High | High | Low | High | Critical | Jessica Reed | EVD-011 | 4.7 | Assessed | No
OPP-009 | PP-013 | Payments | Embed payments within the case flow to remove context switching. | High | Medium | Medium | High | High | Marcus Bell | EVD-013 | 3.9 | Assessed | No
OPP-010 | PP-014 | Payments | Move refund approvals into an auditable workflow with role-based controls. | High | Medium | Medium | High | High | Marcus Bell | EVD-014 | 3.9 | Shortlisted | No
OPP-011 | PP-015 | Payments | Standardise payment references to improve reconciliation speed and accuracy. | High | High | Medium | Medium | High | Maya Singh | EVD-015 | 3.9 | Assessed | No
OPP-012 | PP-017 | Digital Self-Service | Redesign save-and-resume with resilient session persistence and visible draft state. | Very High | Medium | High | High | High | Sophie Lewis | EVD-017 | 3.9 | Recommended | Yes
OPP-013 | PP-018 | Digital Self-Service | Enable multi-file document upload in the portal. | Medium | High | Low | Medium | High | Sophie Lewis | EVD-018 | 3.8 | Assessed | No
OPP-014 | PP-019 | Digital Self-Service | Provide customer-facing status updates that reflect real journey stages. | Very High | Medium | Medium | High | High | Sophie Lewis | EVD-019 | 4.2 | Recommended | Yes
OPP-015 | PP-020 | Digital Self-Service | Improve identity-verification remediation journeys and error messaging. | High | Medium | Medium | High | High | Liam Foster | EVD-020 | 3.9 | Shortlisted | No
OPP-016 | PP-021 | Reporting & Insight | Define a single backlog measure and service-wide cut-off rules. | Very High | High | Low | High | Critical | Daniel Green | EVD-021 | 5 | Recommended | Yes
OPP-017 | PP-022 | Reporting & Insight | Introduce intraday operational MI for demand and backlog management. | High | Medium | Medium | High | High | Daniel Green | EVD-022 | 3.9 | Assessed | No
OPP-018 | PP-023 | Reporting & Insight | Improve root-cause coding and analysis guidance. | Medium | High | Low | Medium | High | Ethan Wood | EVD-023 | 3.8 | Assessed | No
OPP-019 | PP-024 | Contact Centre | Share digital interaction context with advisers for cross-channel journeys. | Very High | Medium | High | High | High | Noah Price | EVD-024 | 3.9 | Shortlisted | No
OPP-020 | PP-025 | Contact Centre | Consolidate operational guidance with ownership and review workflow. | Medium | High | Low | Medium | High | Lena Brooks | EVD-025 | 3.8 | Assessed | No
OPP-021 | PP-026 | Case Management | Refine closure reasons and case outcome taxonomy. | Medium | High | Low | Medium | High | Grace Hall | EVD-026 | 3.8 | Assessed | No
OPP-022 | PP-028 | Payments | Support one payment against multiple linked cases where appropriate. | Medium | Medium | Medium | Medium | Medium | Maya Singh | EVD-028 | 3 | New | No
OPP-023 | PP-029 | Digital Self-Service | Prioritise accessibility issues against service outcomes and risk. | High | High | Low | High | Critical | Sophie Lewis | EVD-029 | 4.7 | Assessed | No
OPP-024 | PP-030 | Reporting & Insight | Adopt a single action tracker for governance and discovery follow-through. | High | High | Low | High | Critical | Emma Grant | EVD-030 | 4.7 | Recommended | Yes
OPP-025 | PP-006 | Case Management | Tighten mandatory field validation and remove free-text workarounds. | High | High | Medium | High | Critical | Priya Nair | EVD-006 | 4.4 | Assessed | No

## 19 Hypothesis Backlog
Northbridge Citizens Services ¦ Hypothesis Backlog
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Maintain the discovery hypothesis backlog here. A hypothesis should be testable and linked to an opportunity. The validated flag is formula-driven from the status column.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  |  | Back to Start
Hypothesis ID | Opportunity ID | Hypothesis Statement | Expected Outcome | Validation Method | Owner | Confidence | Status | Target Date | Validation Result | Next Step | Validated?
HYP-001 | OPP-003 | If routing rules use vulnerability and contact-intent signals, then vulnerable customers will reach the right queue first time more often. | Reduced transfer rate and shorter time to assistance | Workshop + MI analysis | Aisha Khan | High | In Validation | 2026-02-14 | Routing criteria shortlist drafted | Review MI baseline | No
HYP-002 | OPP-004 | If duplicate detection is surfaced at intake, then avoidable duplicate cases will fall materially. | Lower duplicate case volume | Process data + prototyping | Priya Nair | High | Validated | 2026-02-10 | Ops leads agree duplicate prompts would address common repeat-contact patterns | Prepare concept detail | Yes
HYP-003 | OPP-005 | If task-based hand-offs are embedded, then teams will no longer rely on email for internal transfer. | Improved visibility and lower hand-off delay | Workshop playback | Priya Nair | Medium | In Validation | 2026-02-17 | Workflow concept needs IT review | Assess technical constraint | No
HYP-004 | OPP-006 | If partner calendar data is available in near real time, then failed bookings and follow-up contact will reduce. | Lower failed bookings | Partner workshop + integration review | Jessica Reed | High | In Validation | 2026-02-18 | Partner availability API confirmed but latency unknown | Confirm partner data quality | No
HYP-005 | OPP-010 | If refund approvals are tracked in workflow, then audit confidence and turnaround speed will improve. | Better control and shorter approval time | Finance SME review | Marcus Bell | High | Validated | 2026-02-09 | Finance confirms email is current audit weakness | Incorporate into shortlist | Yes
HYP-006 | OPP-012 | If save-and-resume preserves context clearly, then portal abandonment will decrease. | Lower abandonment | User feedback + prototype review | Sophie Lewis | High | In Validation | 2026-02-19 | Strong user demand signal; design effort still unclear | Estimate design effort | No
HYP-007 | OPP-014 | If customer-facing statuses reflect real milestones, then status-chasing contact will reduce. | Lower avoidable demand | Contact centre workshop | Sophie Lewis | High | Validated | 2026-02-11 | Operations and digital teams aligned on principle | Design target status set | Yes
HYP-008 | OPP-015 | If identity-verification failures give clearer recovery steps, then avoidable phone calls will decrease. | Lower support demand | Security review + analytics | Liam Foster | Medium | Backlog | 2026-02-21 | Awaiting security review | Schedule validation session | No
HYP-009 | OPP-016 | If backlog reporting uses one definition and cut-off, then leaders will make faster and more consistent prioritisation decisions. | Better governance | MI review | Daniel Green | Very High | Validated | 2026-02-08 | Agreement reached across services | Carry into recommendation | Yes
HYP-010 | OPP-017 | If intraday MI is available, then operations can respond to demand spikes within the same day. | Improved operational control | Data feasibility assessment | Daniel Green | Medium | In Validation | 2026-02-20 | Feasible for core metrics; full MI scope still open | Define MVP MI set | No
HYP-011 | OPP-019 | If channel context is shared, then advisers will ask customers to repeat less information. | Improved customer experience | Frontline interview + design workshop | Noah Price | High | Validated | 2026-02-12 | Strong frontline support and direct evidence | Include in option pack | Yes
HYP-012 | OPP-020 | If operational guidance is consolidated with named owners, then supervisor support demand will drop. | Improved consistency | Change lead review | Lena Brooks | Medium | In Validation | 2026-02-15 | Needs content owner model | Define governance model | No
HYP-013 | OPP-024 | If one action tracker is used in governance, then decision follow-through will improve. | Better governance discipline | PMO review | Emma Grant | High | Validated | 2026-02-07 | PMO confirms current fragmentation is a control gap | Carry into recommendation | Yes
HYP-014 | OPP-023 | If accessibility issues are prioritised by service risk, then compliance improvements will focus on the right journeys first. | Better accessibility prioritisation | Accessibility backlog review | Sophie Lewis | Medium | Backlog | 2026-02-22 | Needs agreed prioritisation model | Schedule backlog triage | No
HYP-015 | OPP-025 | If mandatory field validation is tightened, then downstream MI quality and triage accuracy will improve. | Better data quality | Casework SME review | Priya Nair | High | In Validation | 2026-02-16 | Supportive feedback but exception handling needs review | Define allowed exceptions | No

## 20 Solution Concepts
Northbridge Citizens Services ¦ Solution Concepts
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Use this sheet to describe candidate solution concepts that combine multiple opportunities into something sponsors can understand and compare.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked | [5 empty] | Back to Start
Concept ID | Concept Name | Linked Opportunities | Description | Feasibility | Cost Band | Complexity | Benefits Summary | Risks Summary | Maturity | Owner | Shortlist Status | Weighted View
CON-001 | Service Experience Foundation | OPP-001, OPP-003, OPP-019 | Improve intake, routing and cross-channel context for customer-facing interactions. | Medium | High | Medium | Fewer transfers, better customer experience, lower repeat contact | Requires integration and data model changes | Outline | Aisha Khan | Shortlisted | 7
CON-002 | Caseflow Control Layer | OPP-004, OPP-005, OPP-025 | Strengthen case creation, tasking and data validation in the case workflow. | High | Medium | Medium | Lower duplicate cases, clearer hand-offs, better case quality | Workflow design and policy alignment required | Validated | Priya Nair | Shortlisted | 11
CON-003 | Booking & Partner Integration | OPP-006, OPP-007, OPP-008 | Improve appointment booking flow, error capture and partner availability visibility. | Medium | High | High | Lower booking failure, better capacity use | Partner integration and dependency risk | Outline | Jessica Reed | Shortlisted | 5
CON-004 | Payments Control Upgrade | OPP-009, OPP-010, OPP-011 | Embed payments and approvals within service workflow. | Medium | Medium | Medium | Better auditability and lower handling time | Payment platform constraints remain | Outline | Marcus Bell | Watchlist | 9
CON-005 | Digital Journey Upgrade | OPP-012, OPP-014, OPP-015, OPP-023 | Improve save-and-resume, customer status and identity remediation. | Medium | High | High | Lower abandonment and avoidable contact | Security and design effort need validation | Concept | Sophie Lewis | Shortlisted | 5
CON-006 | Governance & MI Baseline | OPP-016, OPP-017, OPP-018, OPP-024 | Standardise reporting, action tracking and insight capture. | High | High | Low | Faster decision-making and clearer control | Needs definition alignment across teams | Validated | Daniel Green | Shortlisted | 11

## 21 Option Assessment
Northbridge Citizens Services ¦ Option Assessment
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Compare option shapes here. The weighted score and rank are formula-driven, making this sheet useful for governance conversations and recommendation drafting.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked | [5 empty] | Back to Start
Option ID | Option Name | Summary | Scope Coverage | User Value | Feasibility | Delivery Speed | Risk Profile | Strategic Fit | Cost Efficiency | Total Score | Rank | Recommendation
OPT-001 | Operational Control First | Focus on caseflow, governance, MI and refund controls first. | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 4.2 | 2 | Preferred
OPT-002 | Customer Experience First | Prioritise digital journey, appointment booking and channel context improvements. | 5 | 5 | 3 | 3 | 3 | 4 | 3 | 4 | 3 | Consider
OPT-003 | Balanced MVP | Combine the highest-value operational and customer improvements in one phased recommendation. | 5 | 5 | 4 | 4 | 4 | 5 | 4 | 4.6 | 1 | Preferred
OPT-004 | Do Minimum | Address only urgent control fixes and defer broader change. | 2 | 2 | 5 | 5 | 2 | 2 | 5 | 3.1 | 4 | Not Recommended

## 22 Risk & Assumptions
Northbridge Citizens Services ¦ Risk & Assumptions
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Track discovery risks, assumptions, constraints and dependencies here. Score, RAG and overdue flags are formula-driven so governance pressure is visible.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked | [6 empty] | Back to Start
Item ID | Type | Category | Description | Probability (1-5) | Impact (1-5) | Score | RAG | Owner | Due Date | Status | Mitigation / Response | Overdue? | Notes
RSK-001 | Risk | Partner Integration | Partner calendar access may not support required booking latency. | 4 | 4 | 16 | Red | Jessica Reed | 2026-02-20 | Open | Confirm integration constraints and fallback options | No
RSK-002 | Risk | Security | Identity improvements may need additional assurance review. | 3 | 4 | 12 | Amber | Liam Foster | 2026-02-19 | Mitigating | Schedule security review before recommendation finalisation | No
RSK-003 | Assumption | Operating Model | Service teams will align to one backlog definition if recommended. | 3 | 3 | 9 | Amber | Daniel Green | 2026-02-18 | Accepted | Validate with leaders in recommendation checkpoint | No
RSK-004 | Constraint | Budget | Any option with large platform change will need phased investment approval. | 4 | 3 | 12 | Amber | Chloe Morgan | 2026-02-27 | Open | Make phasing explicit in option pack | No
RSK-005 | Dependency | Data | MI recommendations depend on data-quality remediation decisions. | 3 | 3 | 9 | Amber | Daniel Green | 2026-02-22 | Open | Link MI changes to data quality actions | No
RSK-006 | Risk | Operations | Frontline availability for validation workshops may reduce due to seasonal demand. | 4 | 3 | 12 | Amber | Tom Patel | 2026-02-16 | Mitigating | Hold short focused sessions and use asynchronous review | No
RSK-007 | Assumption | Change | Operational guidance can be consolidated under one owner model. | 2 | 3 | 6 | Green | Lena Brooks | 2026-02-21 | Open | Confirm ownership approach | No
RSK-008 | Risk | Technology | Cross-channel context sharing may require integration not yet funded. | 4 | 4 | 16 | Red | Amira Yusuf | 2026-02-23 | Open | Clarify with architecture and sponsor | No
RSK-009 | Constraint | Policy | Certain statutory case steps cannot be redesigned without policy input. | 3 | 4 | 12 | Amber | Ben Carter | 2026-02-24 | Open | Capture non-negotiable policy constraints | No
RSK-010 | Risk | Accessibility | Accessibility backlog size may exceed current discovery horizon. | 3 | 3 | 9 | Amber | Sophie Lewis | 2026-02-25 | Open | Propose prioritised accessibility tranche | No
RSK-011 | Dependency | PMO | Decision actions require tighter PMO follow-through than current practice. | 3 | 2 | 6 | Green | Emma Grant | 2026-02-14 | Open | Adopt single action tracker immediately | No
RSK-012 | Assumption | Delivery | A phased MVP can be agreed without full end-state design detail. | 2 | 4 | 8 | Amber | Aisha Khan | 2026-02-27 | Accepted | Make unknowns explicit in recommendation | No

## 23 Decision Log
Northbridge Citizens Services ¦ Decision Log
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Use this log to capture the important discovery decisions, why they were made and what actions remain open. It creates a clear trail from evidence to governance outcome.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  |  | Back to Start
Decision ID | Date | Decision Title | Context | Decision Owner | Forum | Outcome | Rationale | Linked Option / Risk | Actions Required | Status
DEC-001 | 2026-01-17 | Discovery scope confirmed | Sponsor agreed discovery will cover contact, case, appointments, payments and digital. | Chloe Morgan | Steering Group | Approved scope and cadence | Needed to align teams before evidence capture | All options | Create integrated plan | Closed
DEC-002 | 2026-01-24 | Use common pain point taxonomy | Discovery team agreed a shared pain point structure across business areas. | Aisha Khan | Working Group | Approved | Supports consistent analysis | Pain points | Update registers | Closed
DEC-003 | 2026-01-30 | Partner booking retained in scope | Partner appointment flow confirmed as a core pain point. | Jessica Reed | Working Group | Approved | High customer impact | OPT-002 | Engage partner team | Closed
DEC-004 | 2026-02-03 | Evidence confidence to be explicit | All evidence items will carry confidence ratings. | Aisha Khan | Working Group | Approved | Improves recommendation quality | All | Complete evidence review | Closed
DEC-005 | 2026-02-05 | One backlog definition needed | Leaders agreed inconsistent backlog MI is a critical decision blocker. | Daniel Green | Programme Board | Approved | Needed for governance improvement | OPT-001 / OPT-003 | Draft common definition | In Progress
DEC-006 | 2026-02-07 | Action tracker centralised | PMO agreed to use this workbook as the single discovery action log. | Emma Grant | Programme Board | Approved | Improves follow-through | Governance | Migrate open actions | In Progress
DEC-007 | 2026-02-10 | Balanced MVP to be assessed | Sponsor requested a balanced phased option rather than single-theme recommendation. | Chloe Morgan | Steering Group | Approved | Supports pragmatic recommendation | OPT-003 | Complete option scoring | Open
DEC-008 | 2026-02-12 | Accessibility to remain visible | Digital lead requested accessibility is explicit in shortlist criteria. | Sophie Lewis | Service Design Authority | Approved | Compliance and user impact | OPT-002 / OPT-003 | Add accessibility assessment | Open
DEC-009 | 2026-02-13 | Security review required for identity fixes | Identity-related changes cannot be recommended without security input. | Liam Foster | Service Design Authority | Pending | Security dependency | OPP-015 | Complete security session | Open
DEC-010 | 2026-02-14 | Recommendation checkpoint date held | Sponsor confirmed 28-Feb decision checkpoint remains target date. | Chloe Morgan | Steering Group | Confirmed | Keeps recommendation plan on track | All | Prepare pack | Open

## 24 Action Tracker
Northbridge Citizens Services ¦ Action Tracker
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Maintain one integrated action tracker for the discovery. This helps avoid fragmented follow-through across emails, decks and meeting notes. The overdue flag is formula-driven from due date and status.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  | Back to Start
Action ID | Source | Description | Owner | Priority | Due Date | Status | Linked Sheet Ref | Overdue? | Comments
ACT-001 | Kick-off | Confirm sponsor review dates for option shortlist | Emma Grant | High | 2026-02-15 | In Progress | Executive Dashboard | No
ACT-002 | Interview Log | Complete Liam Foster interview and capture security constraints | Aisha Khan | High | 2026-02-14 | Open | Interview Log | No
ACT-003 | Interview Log | Complete Ruby Cooper partner booking interview | Aisha Khan | High | 2026-02-15 | Open | Interview Log | No
ACT-004 | Workshop Planner | Run opportunity prioritisation scoring session | Aisha Khan | High | 2026-02-13 | In Progress | Workshop Planner | No
ACT-005 | Evidence Register | Review medium-confidence evidence and decide follow-up | Nadia Shah | Medium | 2026-02-16 | Open | Evidence Register | No
ACT-006 | Opportunity Register | Confirm shortlist inclusion criteria with sponsor | Chloe Morgan | High | 2026-02-18 | Open | Opportunity Register | No
ACT-007 | Hypothesis Backlog | Validate portal save-and-resume effort with design team | Sophie Lewis | Medium | 2026-02-19 | Open | Hypothesis Backlog | No
ACT-008 | Risk & Assumptions | Clarify architecture constraint for cross-channel context sharing | Amira Yusuf | High | 2026-02-17 | Open | Risk & Assumptions | No
ACT-009 | Option Assessment | Complete scoring pack for balanced MVP option | Aisha Khan | High | 2026-02-20 | Open | Option Assessment | No
ACT-010 | Recommendations | Draft recommendation narrative for backlog and MI baseline | Daniel Green | Medium | 2026-02-21 | Open | Recommendations | No
ACT-011 | Recommendations | Draft recommendation narrative for digital journey improvements | Sophie Lewis | Medium | 2026-02-21 | Open | Recommendations | No
ACT-012 | Action Tracker | Migrate legacy actions from email to workbook | Emma Grant | Medium | 2026-02-12 | In Progress | Action Tracker | No
ACT-013 | Stakeholder Register | Confirm sponsor attendees for decision checkpoint | Emma Grant | Medium | 2026-02-24 | Open | Stakeholder Register | No
ACT-014 | Workshop Notes | Confirm outstanding pain point evidence for payment exceptions | Marcus Bell | Low | 2026-02-18 | Open | Workshop Notes | No
ACT-015 | Decision Log | Close decisions with completed actions and archive rationale | Emma Grant | Low | 2026-02-27 | Open | Decision Log | No

## 25 Recommendations
Northbridge Citizens Services ¦ Recommendations
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Capture the recommended actions emerging from discovery. This sheet is intended to bridge from discovery outputs into roadmap or backlog planning.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  |  | Back to Start
Recommendation ID | Theme | Description | Why It Matters | Priority | Owner | Target Horizon | Dependency | Status | Included in Outcome?
REC-001 | Operational Control | Adopt a single backlog definition and governance action tracker as an immediate control improvement. | Leaders need one version of operational truth before broader redesign. | High | Daniel Green | 0-3 months | PMO and leadership agreement | Agreed | Yes
REC-002 | Caseflow | Design task-based hand-offs and duplicate detection for case creation and transfer. | Case quality and internal visibility are constrained by manual workarounds. | High | Priya Nair | 3-6 months | Workflow and policy alignment | Draft | Yes
REC-003 | Customer Experience | Improve partner booking visibility and portal save-and-resume reliability. | Booking failures and digital abandonment drive avoidable demand. | High | Jessica Reed | 3-6 months | Partner integration and design | Draft | Yes
REC-004 | Digital Service | Introduce clearer customer-facing status updates and identity remediation journeys. | Customers need better progress visibility and clearer recovery guidance. | Medium | Sophie Lewis | 3-6 months | Security review | Draft | Yes
REC-005 | Payments Control | Move refund approvals and payment context into workflow over time. | Auditability and efficiency improve when controls are in-process. | Medium | Marcus Bell | 6-12 months | Platform capability decision | Draft | No
REC-006 | Insight & Improvement | Improve root-cause coding and accessibility prioritisation. | Better insight supports ongoing service improvement and compliance. | Medium | Ethan Wood | 3-6 months | Data model changes | Draft | Yes
REC-007 | Change Readiness | Consolidate operational guidance ownership before rollout. | Adoption risk falls when staff guidance is clear and maintained. | Low | Lena Brooks | 0-3 months | Content owner model | Draft | No
REC-008 | Phasing | Use a balanced phased MVP that combines critical control fixes with high-value experience changes. | A phased route balances value, feasibility and sponsor appetite. | High | Aisha Khan | 0-3 months | Option approval | Agreed | Yes

## 26 Outcome Summary
Northbridge Citizens Services ¦ Outcome Summary
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Presentation-ready summary of the discovery conclusion, recommended direction, decisions required and immediate next steps.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  | Back to Start
Discovery conclusion | [5 empty] | Recommended direction
The evidence points to a service with both operational control weaknesses and customer experience friction. The discovery supports a phased route that stabilises governance and caseflow first, while also progressing the highest-value service improvements. | [5 empty] | Pursue a balanced phased MVP. Combine immediate governance, MI and workflow-control improvements with targeted experience improvements that reduce avoidable demand and improve visibility for customers and staff.
Decisions required | [5 empty] | Immediate next steps
• Confirm sponsor approval for the phased MVP direction. • Endorse the common backlog, governance and action-tracking baseline. • Confirm whether dependency-sensitive improvements should proceed to detailed design now or after enabling constraints are resolved. | [5 empty] | 1. Baseline immediate governance and MI improvements. 2. Shape detailed design for caseflow, partner booking and digital journey improvements. 3. Resolve key security and partner integration dependencies. 4. Convert validated opportunities into a delivery-ready backlog.
Delivery implications
The recommended route requires disciplined governance, explicit phasing and early agreement on data and taxonomy standards. Several improvements can start as low-regret foundation actions while more dependency-sensitive items are refined.
Executive summary / decision ask
Approve a balanced phased MVP recommendation that combines critical control fixes with high-value customer improvements. Endorse the common backlog and governance baseline immediately, and commission the next design tranche for the shortlisted operational and digital opportunities.

## 90 About & Attribution
Northbridge Citizens Services ¦ About & Attribution
Citizen Services Transformation ¦ Case & Contact Service Discovery ¦ Report date: 12-Feb-2026
Home | Set Up | Guidance | Overview | Exec Dash | Ops Dash | Stakeholders | Options | Outcome
Admin / legal note. Hidden by default for white-label internal deployments.
Legend | Editable | Formula | Locked | Complete | In progress | Overdue / blocked |  |  | Back to Start
Minimal attribution / licensing note
Source / original concept: StratForge.
This reference is intentionally isolated to a single tab so the workbook can be white-labelled for internal use.
The workbook contains no VBA, no macros, and no external links.
Before live use, replace demo data, review thresholds, and confirm internal policy / legal requirements for redistribution.
If your licence terms permit, this tab may be hidden for internal deployment.

## 96 Admin - QA
Release QA
Check | Status | Note
Launch sheet | PASS | 01 Start Here set as active workbook tab
Navigation | PASS | Visible sheets have internal navigation and Back to Start link
Protection | PASS | Visible sheets protected; intended inputs unlocked
Admin separation | PASS | About, QA, change log, lists and dashboard data hidden
Data validation | PASS | Controlled-list dropdowns restored on input sheets
Freeze panes | PASS | Narrative sheets freeze title block; input sheets freeze row 8 and first column
Chart readability | PASS | Busy doughnut charts removed; dashboards use bar/line visuals
Print setup | PASS | Visible sheets have print area and page setup configured

## 97 Change Log
Version | Date | Change | Owner
V2.0 Production | 20-Apr-2026 | Full UX/UI rebuild: launch screen, navigation, dashboard redesign, protection, tab grouping, validations restored and admin sheets hidden. | OpenAI
V2.1 Production | 20-Apr-2026 | Final production hardening: interactive navigation on all visible sheets, legends, freeze panes, editable inputs unlocked, visible sheets protected, print setup defined, and admin sheets re-hidden and protected. | OpenAI
V2.2 Agile Export | 08-Jun-2026 | Added 27 Agile Requirements Export, aligned to the StratForge Agile Requirements Planner Discovery Import schema, with source traceability, suggested Agile work item types and include sequencing. | OpenAI

## 98 Admin - Lists
YesNo | MilestoneStatus | InterviewStatus | WorkshopStatus | StakeholderType | Influence | Interest | EngagementStrategy | WorkshopParticipation | DecisionForum | BusinessArea | PainSeverity | Frequency | Confidence | ValueRating | Feasibility | Complexity | Alignment | OpportunityStatus | HypothesisStatus | CostBand | Maturity | RiskType | RiskStatus | ActionStatus | RecommendationStatus | Priority4 | Priority3 | EvidenceSourceType | EvidenceAccepted | PainPriority | ConceptShortlist | OptionRecommendation | OutcomeStatus | SetupStatus | AgileInclude | AgileWorkItemType | AgileSourceType | AgilePriority | AgileImportAction
Yes | Complete | Completed | Complete | Sponsor | High | High | Manage Closely | Attended | Steering Group | Contact Centre | Critical | Daily | Very High | Very High | High | Low | High | New | Backlog | Low | Concept | Risk | Open | Open | Draft | Critical | High | Interview | Yes | High | Shortlisted | Preferred | Draft | Done | Yes | Theme | Solution Concept | Critical | Copy as values
No | In Progress | Scheduled | In Progress | Business Lead | Medium | Medium | Keep Satisfied | Invited | Service Design Authority | Case Management | High | Weekly | High | High | Medium | Medium | Medium | Assessed | In Validation | Medium | Outline | Assumption | Mitigating | In Progress | Agreed | High | Medium | Workshop | No | Medium | Watchlist | Consider | Under Review | Pending | No | Epic | Discovery Opportunity | High | Triage candidate
| At Risk | Rescheduled | Planned | Operations | Low | Low | Keep Informed | Co-Facilitator | Programme Board | Appointments | Medium | Monthly | Medium | Medium | Low | High | Low | Shortlisted | Validated | High | Validated | Constraint | Accepted | Blocked | In Delivery | Medium | Low | Process Data |  | Low | Rejected | Not Recommended | Final |  |  | Feature | Recommendation | Medium | Promote to catalogue
| Not Started | Cancelled | Cancelled | Product |  |  | Monitor | Not Required | Working Group | Payments | Low | Occasional | Low | Low |  |  |  | Recommended | Rejected | Very High | Ready | Dependency | Closed | Closed | Closed | Low |  | Policy | [7 empty] | User Story | Hypothesis | Low | Hold
|  | Not Needed |  | SME |  |  |  |  | None | Digital Self-Service | [7 empty] | Rejected | Parked | [8 empty] | User Feedback | [7 empty] | Spike | Pain Point |  | Reject
|  |  |  | IT | [5 empty] | Reporting & Insight | [17 empty] | System Report | [7 empty] | Enabler
Data
Security
PMO
Partner
Frontline User

## 99 Admin - Dashboard Data
Discovery progress % | 33.33% | Phase | Completion % | Opportunity Priority | Count | Recommendation Status | Count | Option | Score | Stakeholder Type | Count | Interview Status | Count | Workshop Status | Count | Evidence Source | Count | Week Start | Interviews Completed | Workshops Completed | Business Area | Pain Points | Action Status | Count | Risk RAG | Open Count | Opportunity Status | Count | Hypothesis Status | Count
Stakeholder engagement % | 85% | Mobilise | 100% | Critical | 7 | Draft | 6 | Operational Control First | 4.2 | Sponsor | 1 | Completed | 12 | Complete | 6 | Interview | 5 | 2026-01-15 | 3 | 1 | Contact Centre | 5 | Open | 12 | Red | 2 | New | 1 | Backlog | 2
Evidence coverage % | 100% | Frame | 100% | High | 16 | Agreed | 2 | Customer Experience First | 4 | Business Lead | 4 | Scheduled | 3 | In Progress | 0 | Workshop | 5 | 2026-01-22 | 5 | 2 | Case Management | 6 | In Progress | 3 | Amber | 8 | Assessed | 13 | In Validation | 7
Interview completion % | 80% | Explore | 0% | Medium | 2 | In Delivery | 0 | Balanced MVP | 4.6 | Operations | 3 | Rescheduled | 0 | Planned | 0 | Process Data | 5 | 2026-01-29 | 3 | 2 | Appointments | 5 | Blocked | 0 | Green | 2 | Shortlisted | 6 | Validated | 6
High-priority opportunities | 23 | Analyse | 0% | Low | 0 | Closed | 0 | Do Minimum | 3.1 | Product | 1 | Cancelled | 0 | Cancelled | 0 | Policy | 5 | 2026-02-05 | 1 | 1 | Payments | 5 | Closed | 0 |  |  | Recommended | 5 | Rejected | 0
Open high risks | 2 | Recommend | 0% | [6 empty] | SME | 2 | Not Needed | 0 |  |  | User Feedback | 5 | 2026-02-12 | 0 | 0 | Digital Self-Service | 5 |  |  |  |  | Rejected | 0 | Parked | 0
Recommendation readiness % | 25% | [8 empty] | IT | 1 |  |  |  |  | System Report | 5 | 2026-02-19 | 0 | 0 | Reporting & Insight | 4
Workshops completed % | 75% | [8 empty] | Data | 2
Validated hypotheses % | 40% | [8 empty] | Security | 1
Open actions overdue | 0 | [8 empty] | PMO | 1
Total pain points | 30 | [8 empty] | Partner | 1
Total opportunities | 25 | [8 empty] | Frontline User | 3
Shortlisted concepts | 5
Leading option score | 4.6
Discovery momentum % | 74.67%
Average evidence quality | 3.5
High severity pain points | 20
Open decisions | 6
Accepted evidence items | 20
High-influence engaged % | 100%

## 27 Agile Requirements Export
Northbridge Citizens Services ¦ Agile Requirements Export | [16 empty] | Export Method
Citizen Services Transformation ¦ Discovery-to-Agile hand-off ¦ Compatible with StratForge Agile Requirements Planner | [16 empty] | 1 | Complete the Discovery workbook inputs.
Home | Guidance | Pain Points | Evidence | Opportunities | Hypotheses | Concepts | Recommendations | Outcome | [8 empty] | 2 | Review the export rows and amend Include? where required.
Use this sheet to convert completed discovery outputs into a copy-ready Agile import. Review Include?, Suggested Work Item Type and Priority, then copy columns A:Q into the Agile Requirements Planner > Discovery Import sheet using Paste Values. | [16 empty] | 3 | Check Suggested Work Item Type before import.
Legend | Editable / Review | Formula-driven | Source-linked | Included by default | Review before import | Do not use live workbook links | Copy A:Q as values | [9 empty] | 4 | Copy A8:Q92 and paste values into Agile Planner > Discovery Import.
[17 empty] | 5 | Triage promoted items in Backlog Candidates.
Included rows | 55 | Epics | 6 | Features | 25 | User Stories | 12 | Spikes | 6 | High / Critical | 50 | Review required | 0
Include? | Import ID | Source Workbook | Source Sheet | Source Type | Source ID | Suggested Work Item Type | Suggested Title | Description | Business Area | Process Area | Priority | Owner | Evidence ID | Linked Source ID | Candidate Notes | Helper Include Seq | Conversion Rules
Yes | IMP-001 | Discovery_Command_Pack_White_Label_v1.xlsx | 20 Solution Concepts | Solution Concept | CON-001 | Epic | Service Experience Foundation | Improve intake, routing and cross-channel context for customer-facing interactions. |  |  | High | Aisha Khan |  | OPP-001, OPP-003, OPP-019 | Benefits: Fewer transfers, better customer experience, lower repeat contact; Risks: Requires integration and data model changes | 1 | Solution Concepts | Epic | Roadmap-level container
Yes | IMP-002 | Discovery_Command_Pack_White_Label_v1.xlsx | 20 Solution Concepts | Solution Concept | CON-002 | Epic | Caseflow Control Layer | Strengthen case creation, tasking and data validation in the case workflow. |  |  | High | Priya Nair |  | OPP-004, OPP-005, OPP-025 | Benefits: Lower duplicate cases, clearer hand-offs, better case quality; Risks: Workflow design and policy alignment required | 2 | Opportunities | Feature | Backlog capability candidate
Yes | IMP-003 | Discovery_Command_Pack_White_Label_v1.xlsx | 20 Solution Concepts | Solution Concept | CON-003 | Epic | Booking & Partner Integration | Improve appointment booking flow, error capture and partner availability visibility. |  |  | High | Jessica Reed |  | OPP-006, OPP-007, OPP-008 | Benefits: Lower booking failure, better capacity use; Risks: Partner integration and dependency risk | 3 | Recommendations | Theme | Strategic grouping / roadmap theme
Yes | IMP-004 | Discovery_Command_Pack_White_Label_v1.xlsx | 20 Solution Concepts | Solution Concept | CON-004 | Epic | Payments Control Upgrade | Embed payments and approvals within service workflow. |  |  | Medium | Marcus Bell |  | OPP-009, OPP-010, OPP-011 | Benefits: Better auditability and lower handling time; Risks: Payment platform constraints remain | 4 | Validated Hypotheses | Spike | Learning or validation item
Yes | IMP-005 | Discovery_Command_Pack_White_Label_v1.xlsx | 20 Solution Concepts | Solution Concept | CON-005 | Epic | Digital Journey Upgrade | Improve save-and-resume, customer status and identity remediation. |  |  | High | Sophie Lewis |  | OPP-012, OPP-014, OPP-015, OPP-023 | Benefits: Lower abandonment and avoidable contact; Risks: Security and design effort need validation | 5 | High-priority Pain Points | User Story | Potential story or rationale
Yes | IMP-006 | Discovery_Command_Pack_White_Label_v1.xlsx | 20 Solution Concepts | Solution Concept | CON-006 | Epic | Governance & MI Baseline | Standardise reporting, action tracking and insight capture. |  |  | High | Daniel Green |  | OPP-016, OPP-017, OPP-018, OPP-024 | Benefits: Faster decision-making and clearer control; Risks: Needs definition alignment across teams | 6
Yes | IMP-007 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-001 | Feature | Introduce channel context hand-off so adviser screens are pre-populated when customers move from web or email to phone. | Introduce channel context hand-off so adviser screens are pre-populated when customers move from web or email to phone. | Contact Centre | Enquiry Intake | High | Aisha Khan | EVD-001 | PP-001 | Value=Very High; Feasibility=Medium; Score=4.2 | 7
Yes | IMP-008 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-002 | Feature | Establish owned knowledge articles with review cadence and operational quality metrics. | Establish owned knowledge articles with review cadence and operational quality metrics. | Contact Centre | Enquiry Intake | Critical | Lena Brooks | EVD-002 | PP-002 | Value=High; Feasibility=High; Score=4.7 | 8
Yes | IMP-009 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-003 | Feature | Refine routing rules and customer segmentation for vulnerable callers. | Refine routing rules and customer segmentation for vulnerable callers. | Contact Centre | Enquiry Intake | High | Tom Patel | EVD-003 | PP-003 | Value=Very High; Feasibility=Medium; Score=4.2 | 9
Yes | IMP-010 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-004 | Feature | Add duplicate detection and merge guidance at intake. | Add duplicate detection and merge guidance at intake. | Case Management | Case Creation | Critical | Priya Nair | EVD-005 | PP-005 | Value=High; Feasibility=High; Score=4.4 | 10
Yes | IMP-011 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-005 | Feature | Introduce task-based workflow for internal hand-offs with audit trail. | Introduce task-based workflow for internal hand-offs with audit trail. | Case Management | Case Handover | High | Priya Nair | EVD-008 | PP-008 | Value=Very High; Feasibility=Medium; Score=3.9 | 11
Yes | IMP-012 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-006 | Feature | Integrate partner calendar availability into the core booking experience. | Integrate partner calendar availability into the core booking experience. | Appointments | Appointment Booking | Medium | Jessica Reed | EVD-009 | PP-009 | Value=Very High; Feasibility=Low; Score=3.4 | 12
Yes | IMP-013 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-007 | Feature | Suppress obsolete appointment notifications during rebooking. | Suppress obsolete appointment notifications during rebooking. | Appointments | Appointment Booking | High | Jessica Reed | EVD-010 | PP-010 | Value=Medium; Feasibility=High; Score=3.8 | 13
Yes | IMP-014 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-008 | Feature | Capture structured booking failure reasons for analysis and recovery. | Capture structured booking failure reasons for analysis and recovery. | Appointments | Appointment Booking | Critical | Jessica Reed | EVD-011 | PP-011 | Value=High; Feasibility=High; Score=4.7 | 14
Yes | IMP-015 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-009 | Feature | Embed payments within the case flow to remove context switching. | Embed payments within the case flow to remove context switching. | Payments | Payment Collection | High | Marcus Bell | EVD-013 | PP-013 | Value=High; Feasibility=Medium; Score=3.9 | 15
Yes | IMP-016 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-010 | Feature | Move refund approvals into an auditable workflow with role-based controls. | Move refund approvals into an auditable workflow with role-based controls. | Payments | Payment Collection | High | Marcus Bell | EVD-014 | PP-014 | Value=High; Feasibility=Medium; Score=3.9 | 16
Yes | IMP-017 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-011 | Feature | Standardise payment references to improve reconciliation speed and accuracy. | Standardise payment references to improve reconciliation speed and accuracy. | Payments | Payment Reconciliation | High | Maya Singh | EVD-015 | PP-015 | Value=High; Feasibility=High; Score=3.9 | 17
Yes | IMP-018 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-012 | Feature | Redesign save-and-resume with resilient session persistence and visible draft state. | Redesign save-and-resume with resilient session persistence and visible draft state. | Digital Self-Service | Portal Submission | High | Sophie Lewis | EVD-017 | PP-017 | Value=Very High; Feasibility=Medium; Score=3.9 | 18
Yes | IMP-019 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-013 | Feature | Enable multi-file document upload in the portal. | Enable multi-file document upload in the portal. | Digital Self-Service | Portal Submission | High | Sophie Lewis | EVD-018 | PP-018 | Value=Medium; Feasibility=High; Score=3.8 | 19
Yes | IMP-020 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-014 | Feature | Provide customer-facing status updates that reflect real journey stages. | Provide customer-facing status updates that reflect real journey stages. | Digital Self-Service | Portal Status | High | Sophie Lewis | EVD-019 | PP-019 | Value=Very High; Feasibility=Medium; Score=4.2 | 20
Yes | IMP-021 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-015 | Feature | Improve identity-verification remediation journeys and error messaging. | Improve identity-verification remediation journeys and error messaging. | Digital Self-Service | Portal Access | High | Liam Foster | EVD-020 | PP-020 | Value=High; Feasibility=Medium; Score=3.9 | 21
Yes | IMP-022 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-016 | Feature | Define a single backlog measure and service-wide cut-off rules. | Define a single backlog measure and service-wide cut-off rules. | Reporting & Insight | Reporting | Critical | Daniel Green | EVD-021 | PP-021 | Value=Very High; Feasibility=High; Score=5 | 22
Yes | IMP-023 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-017 | Feature | Introduce intraday operational MI for demand and backlog management. | Introduce intraday operational MI for demand and backlog management. | Reporting & Insight | Reporting | High | Daniel Green | EVD-022 | PP-022 | Value=High; Feasibility=Medium; Score=3.9 | 23
Yes | IMP-024 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-018 | Feature | Improve root-cause coding and analysis guidance. | Improve root-cause coding and analysis guidance. | Reporting & Insight | Reporting | High | Ethan Wood | EVD-023 | PP-023 | Value=Medium; Feasibility=High; Score=3.8 | 24
Yes | IMP-025 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-019 | Feature | Share digital interaction context with advisers for cross-channel journeys. | Share digital interaction context with advisers for cross-channel journeys. | Contact Centre | Cross-Channel Journey | High | Noah Price | EVD-024 | PP-024 | Value=Very High; Feasibility=Medium; Score=3.9 | 25
Yes | IMP-026 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-020 | Feature | Consolidate operational guidance with ownership and review workflow. | Consolidate operational guidance with ownership and review workflow. | Contact Centre | Knowledge & Guidance | High | Lena Brooks | EVD-025 | PP-025 | Value=Medium; Feasibility=High; Score=3.8 | 26
Yes | IMP-027 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-021 | Feature | Refine closure reasons and case outcome taxonomy. | Refine closure reasons and case outcome taxonomy. | Case Management | Case Closure | High | Grace Hall | EVD-026 | PP-026 | Value=Medium; Feasibility=High; Score=3.8 | 27
Yes | IMP-028 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-022 | Feature | Support one payment against multiple linked cases where appropriate. | Support one payment against multiple linked cases where appropriate. | Payments | Payments | Medium | Maya Singh | EVD-028 | PP-028 | Value=Medium; Feasibility=Medium; Score=3 | 28
Yes | IMP-029 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-023 | Feature | Prioritise accessibility issues against service outcomes and risk. | Prioritise accessibility issues against service outcomes and risk. | Digital Self-Service | Digital Accessibility | Critical | Sophie Lewis | EVD-029 | PP-029 | Value=High; Feasibility=High; Score=4.7 | 29
Yes | IMP-030 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-024 | Feature | Adopt a single action tracker for governance and discovery follow-through. | Adopt a single action tracker for governance and discovery follow-through. | Reporting & Insight | Management Oversight | Critical | Emma Grant | EVD-030 | PP-030 | Value=High; Feasibility=High; Score=4.7 | 30
Yes | IMP-031 | Discovery_Command_Pack_White_Label_v1.xlsx | 18 Opportunity Register | Discovery Opportunity | OPP-025 | Feature | Tighten mandatory field validation and remove free-text workarounds. | Tighten mandatory field validation and remove free-text workarounds. | Case Management | Case Creation | Critical | Priya Nair | EVD-006 | PP-006 | Value=High; Feasibility=High; Score=4.4 | 31
Yes | IMP-032 | Discovery_Command_Pack_White_Label_v1.xlsx | 25 Recommendations | Recommendation | REC-001 | Theme | Operational Control | Adopt a single backlog definition and governance action tracker as an immediate control improvement. |  |  | High | Daniel Green |  | PMO and leadership agreement | Leaders need one version of operational truth before broader redesign. | 32
Yes | IMP-033 | Discovery_Command_Pack_White_Label_v1.xlsx | 25 Recommendations | Recommendation | REC-002 | Theme | Caseflow | Design task-based hand-offs and duplicate detection for case creation and transfer. |  |  | High | Priya Nair |  | Workflow and policy alignment | Case quality and internal visibility are constrained by manual workarounds. | 33
Yes | IMP-034 | Discovery_Command_Pack_White_Label_v1.xlsx | 25 Recommendations | Recommendation | REC-003 | Theme | Customer Experience | Improve partner booking visibility and portal save-and-resume reliability. |  |  | High | Jessica Reed |  | Partner integration and design | Booking failures and digital abandonment drive avoidable demand. | 34
Yes | IMP-035 | Discovery_Command_Pack_White_Label_v1.xlsx | 25 Recommendations | Recommendation | REC-004 | Theme | Digital Service | Introduce clearer customer-facing status updates and identity remediation journeys. |  |  | Medium | Sophie Lewis |  | Security review | Customers need better progress visibility and clearer recovery guidance. | 35
No | IMP-036 | Discovery_Command_Pack_White_Label_v1.xlsx | 25 Recommendations | Recommendation | REC-005 | Theme | Payments Control | Move refund approvals and payment context into workflow over time. |  |  | Medium | Marcus Bell |  | Platform capability decision | Auditability and efficiency improve when controls are in-process.
Yes | IMP-037 | Discovery_Command_Pack_White_Label_v1.xlsx | 25 Recommendations | Recommendation | REC-006 | Theme | Insight & Improvement | Improve root-cause coding and accessibility prioritisation. |  |  | Medium | Ethan Wood |  | Data model changes | Better insight supports ongoing service improvement and compliance. | 36
No | IMP-038 | Discovery_Command_Pack_White_Label_v1.xlsx | 25 Recommendations | Recommendation | REC-007 | Theme | Change Readiness | Consolidate operational guidance ownership before rollout. |  |  | Low | Lena Brooks |  | Content owner model | Adoption risk falls when staff guidance is clear and maintained.
Yes | IMP-039 | Discovery_Command_Pack_White_Label_v1.xlsx | 25 Recommendations | Recommendation | REC-008 | Theme | Phasing | Use a balanced phased MVP that combines critical control fixes with high-value experience changes. |  |  | High | Aisha Khan |  | Option approval | A phased route balances value, feasibility and sponsor appetite. | 37
No | IMP-040 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-001 | Spike | If routing rules use vulnerability and contact-intent signals, then vulnerable customers will reach the right queue first time more often. | If routing rules use vulnerability and contact-intent signals, then vulnerable customers will reach the right queue first time more often. | Contact Centre | Enquiry Intake | High | Aisha Khan | EVD-003 | OPP-003 | Validation method: Workshop + MI analysis; Validated: No
Yes | IMP-041 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-002 | Spike | If duplicate detection is surfaced at intake, then avoidable duplicate cases will fall materially. | If duplicate detection is surfaced at intake, then avoidable duplicate cases will fall materially. | Case Management | Case Creation | High | Priya Nair | EVD-005 | OPP-004 | Validation method: Process data + prototyping; Validated: Yes | 38
No | IMP-042 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-003 | Spike | If task-based hand-offs are embedded, then teams will no longer rely on email for internal transfer. | If task-based hand-offs are embedded, then teams will no longer rely on email for internal transfer. | Case Management | Case Handover | Medium | Priya Nair | EVD-008 | OPP-005 | Validation method: Workshop playback; Validated: No
No | IMP-043 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-004 | Spike | If partner calendar data is available in near real time, then failed bookings and follow-up contact will reduce. | If partner calendar data is available in near real time, then failed bookings and follow-up contact will reduce. | Appointments | Appointment Booking | High | Jessica Reed | EVD-009 | OPP-006 | Validation method: Partner workshop + integration review; Validated: No
Yes | IMP-044 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-005 | Spike | If refund approvals are tracked in workflow, then audit confidence and turnaround speed will improve. | If refund approvals are tracked in workflow, then audit confidence and turnaround speed will improve. | Payments | Payment Collection | High | Marcus Bell | EVD-014 | OPP-010 | Validation method: Finance SME review; Validated: Yes | 39
No | IMP-045 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-006 | Spike | If save-and-resume preserves context clearly, then portal abandonment will decrease. | If save-and-resume preserves context clearly, then portal abandonment will decrease. | Digital Self-Service | Portal Submission | High | Sophie Lewis | EVD-017 | OPP-012 | Validation method: User feedback + prototype review; Validated: No
Yes | IMP-046 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-007 | Spike | If customer-facing statuses reflect real milestones, then status-chasing contact will reduce. | If customer-facing statuses reflect real milestones, then status-chasing contact will reduce. | Digital Self-Service | Portal Status | High | Sophie Lewis | EVD-019 | OPP-014 | Validation method: Contact centre workshop; Validated: Yes | 40
No | IMP-047 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-008 | Spike | If identity-verification failures give clearer recovery steps, then avoidable phone calls will decrease. | If identity-verification failures give clearer recovery steps, then avoidable phone calls will decrease. | Digital Self-Service | Portal Access | Medium | Liam Foster | EVD-020 | OPP-015 | Validation method: Security review + analytics; Validated: No
Yes | IMP-048 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-009 | Spike | If backlog reporting uses one definition and cut-off, then leaders will make faster and more consistent prioritisation decisions. | If backlog reporting uses one definition and cut-off, then leaders will make faster and more consistent prioritisation decisions. | Reporting & Insight | Reporting | High | Daniel Green | EVD-021 | OPP-016 | Validation method: MI review; Validated: Yes | 41
No | IMP-049 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-010 | Spike | If intraday MI is available, then operations can respond to demand spikes within the same day. | If intraday MI is available, then operations can respond to demand spikes within the same day. | Reporting & Insight | Reporting | Medium | Daniel Green | EVD-022 | OPP-017 | Validation method: Data feasibility assessment; Validated: No
Yes | IMP-050 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-011 | Spike | If channel context is shared, then advisers will ask customers to repeat less information. | If channel context is shared, then advisers will ask customers to repeat less information. | Contact Centre | Cross-Channel Journey | High | Noah Price | EVD-024 | OPP-019 | Validation method: Frontline interview + design workshop; Validated: Yes | 42
No | IMP-051 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-012 | Spike | If operational guidance is consolidated with named owners, then supervisor support demand will drop. | If operational guidance is consolidated with named owners, then supervisor support demand will drop. | Contact Centre | Knowledge & Guidance | Medium | Lena Brooks | EVD-025 | OPP-020 | Validation method: Change lead review; Validated: No
Yes | IMP-052 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-013 | Spike | If one action tracker is used in governance, then decision follow-through will improve. | If one action tracker is used in governance, then decision follow-through will improve. | Reporting & Insight | Management Oversight | High | Emma Grant | EVD-030 | OPP-024 | Validation method: PMO review; Validated: Yes | 43
No | IMP-053 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-014 | Spike | If accessibility issues are prioritised by service risk, then compliance improvements will focus on the right journeys first. | If accessibility issues are prioritised by service risk, then compliance improvements will focus on the right journeys first. | Digital Self-Service | Digital Accessibility | Medium | Sophie Lewis | EVD-029 | OPP-023 | Validation method: Accessibility backlog review; Validated: No
No | IMP-054 | Discovery_Command_Pack_White_Label_v1.xlsx | 19 Hypothesis Backlog | Hypothesis | HYP-015 | Spike | If mandatory field validation is tightened, then downstream MI quality and triage accuracy will improve. | If mandatory field validation is tightened, then downstream MI quality and triage accuracy will improve. | Case Management | Case Creation | High | Priya Nair | EVD-006 | OPP-025 | Validation method: Casework SME review; Validated: No
Yes | IMP-055 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-001 | User Story | Advisers re-key caller details from email summaries into the case system. | Advisers re-key caller details from email summaries into the case system. | Contact Centre | Enquiry Intake | High | Aisha Khan | EVD-001 |  | Root cause: Channel hand-off is not integrated | 44
Yes | IMP-056 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-002 | User Story | Knowledge articles are outdated, so advisers improvise responses. | Knowledge articles are outdated, so advisers improvise responses. | Contact Centre | Enquiry Intake | High | Nadia Shah | EVD-002 |  | Root cause: Content ownership is unclear | 45
Yes | IMP-057 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-003 | User Story | Call queues do not distinguish vulnerable customers consistently. | Call queues do not distinguish vulnerable customers consistently. | Contact Centre | Enquiry Intake | High | Aisha Khan | EVD-003 |  | Root cause: Routing rules are too broad | 46
No | IMP-058 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-004 | User Story | Case categories are interpreted differently across teams. | Case categories are interpreted differently across teams. | Case Management | Case Creation | Medium | Nadia Shah | EVD-004 |  | Root cause: Taxonomy is ambiguous
Yes | IMP-059 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-005 | User Story | Duplicate cases are created when customers follow up through multiple channels. | Duplicate cases are created when customers follow up through multiple channels. | Case Management | Case Creation | High | Aisha Khan | EVD-005 |  | Root cause: No duplicate detection at intake | 47
No | IMP-060 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-006 | User Story | Mandatory data fields are bypassed using free-text workarounds. | Mandatory data fields are bypassed using free-text workarounds. | Case Management | Case Creation | Medium | Nadia Shah | EVD-006 |  | Root cause: Validation rules are incomplete
No | IMP-061 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-007 | User Story | Priority rules are inconsistent between service teams. | Priority rules are inconsistent between service teams. | Case Management | Case Triage | Medium | Aisha Khan | EVD-007 |  | Root cause: Local spreadsheets override standard rules
Yes | IMP-062 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-008 | User Story | Internal hand-offs rely on email and are not visible end to end. | Internal hand-offs rely on email and are not visible end to end. | Case Management | Case Handover | High | Nadia Shah | EVD-008 |  | Root cause: Workflow tasking is not configured | 48
Yes | IMP-063 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-009 | User Story | Agents cannot see real-time slot availability for partner calendars. | Agents cannot see real-time slot availability for partner calendars. | Appointments | Appointment Booking | High | Aisha Khan | EVD-009 |  | Root cause: Partner integration is batch-based | 49
No | IMP-064 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-010 | User Story | Rebooking generates duplicate notifications to citizens. | Rebooking generates duplicate notifications to citizens. | Appointments | Appointment Booking | Low | Nadia Shah | EVD-010 |  | Root cause: Notification logic does not suppress superseded messages
No | IMP-065 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-011 | User Story | Failed bookings are not captured with useful failure reasons. | Failed bookings are not captured with useful failure reasons. | Appointments | Appointment Booking | Medium | Aisha Khan | EVD-011 |  | Root cause: Error handling is generic
No | IMP-066 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-012 | User Story | No-shows are recorded late, affecting slot reuse. | No-shows are recorded late, affecting slot reuse. | Appointments | Appointment Attendance | Low | Nadia Shah | EVD-012 |  | Root cause: Attendance updates depend on manual end-of-day checks
Yes | IMP-067 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-013 | User Story | Agents leave the case screen to take payments in a separate tool. | Agents leave the case screen to take payments in a separate tool. | Payments | Payment Collection | High | Aisha Khan | EVD-013 |  | Root cause: Payment tool is not embedded in workflow | 50
No | IMP-068 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-014 | User Story | Refund approvals are tracked in email, not in the case record. | Refund approvals are tracked in email, not in the case record. | Payments | Payment Collection | Medium | Nadia Shah | EVD-014 |  | Root cause: Approval workflow is off-system
No | IMP-069 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-015 | User Story | Daily reconciliation takes too long because references are inconsistent. | Daily reconciliation takes too long because references are inconsistent. | Payments | Payment Reconciliation | Medium | Aisha Khan | EVD-015 |  | Root cause: Reference data is incomplete
No | IMP-070 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-016 | User Story | Chargeback cases are managed outside the main service process. | Chargeback cases are managed outside the main service process. | Payments | Payment Exceptions | Low | Nadia Shah | EVD-016 |  | Root cause: Exception handling is not integrated
Yes | IMP-071 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-017 | User Story | Customers abandon the portal because the save-and-resume flow is unreliable. | Customers abandon the portal because the save-and-resume flow is unreliable. | Digital Self-Service | Portal Submission | High | Aisha Khan | EVD-017 |  | Root cause: Session persistence is weak | 51
No | IMP-072 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-018 | User Story | Supporting documents can be uploaded only one at a time. | Supporting documents can be uploaded only one at a time. | Digital Self-Service | Portal Submission | Medium | Nadia Shah | EVD-018 |  | Root cause: Upload component is limited
Yes | IMP-073 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-019 | User Story | Citizens cannot see meaningful case progress updates online. | Citizens cannot see meaningful case progress updates online. | Digital Self-Service | Portal Status | High | Aisha Khan | EVD-019 |  | Root cause: Status model is too generic | 52
No | IMP-074 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-020 | User Story | Identity verification failures generate high avoidable contact. | Identity verification failures generate high avoidable contact. | Digital Self-Service | Portal Access | Medium | Nadia Shah | EVD-020 |  | Root cause: Error messages do not explain remediation
Yes | IMP-075 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-021 | User Story | Leaders receive different backlog figures from different teams. | Leaders receive different backlog figures from different teams. | Reporting & Insight | Reporting | High | Aisha Khan | EVD-021 |  | Root cause: Definitions and cut-off rules differ | 53
Yes | IMP-076 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-022 | User Story | Operational MI is refreshed too slowly for daily decision-making. | Operational MI is refreshed too slowly for daily decision-making. | Reporting & Insight | Reporting | High | Nadia Shah | EVD-022 |  | Root cause: Refresh cadence is overnight only | 54
No | IMP-077 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-023 | User Story | Root-cause reporting is manual and inconsistent. | Root-cause reporting is manual and inconsistent. | Reporting & Insight | Reporting | Low | Aisha Khan | EVD-023 |  | Root cause: Case fields do not support consistent coding
Yes | IMP-078 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-024 | User Story | Customers repeat information when moving from web to phone. | Customers repeat information when moving from web to phone. | Contact Centre | Cross-Channel Journey | High | Nadia Shah | EVD-024 |  | Root cause: Interaction context is not shared across channels | 55
No | IMP-079 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-025 | User Story | Supervisors spend too much time answering repeat process questions. | Supervisors spend too much time answering repeat process questions. | Contact Centre | Knowledge & Guidance | Medium | Aisha Khan | EVD-025 |  | Root cause: Guidance is scattered across shared drives
No | IMP-080 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-026 | User Story | Closure reasons are too broad to support meaningful analysis. | Closure reasons are too broad to support meaningful analysis. | Case Management | Case Closure | Low | Nadia Shah | EVD-026 |  | Root cause: Closure taxonomy is under-designed
No | IMP-081 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-027 | User Story | Outbound reminders cannot be tailored by appointment type. | Outbound reminders cannot be tailored by appointment type. | Appointments | Appointment Confirmations | Low | Aisha Khan | EVD-027 |  | Root cause: Template logic is too simple
No | IMP-082 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-028 | User Story | Staff cannot easily see whether a payment relates to multiple cases. | Staff cannot easily see whether a payment relates to multiple cases. | Payments | Payments | Low | Nadia Shah | EVD-028 |  | Root cause: Payment-to-case mapping is one-to-one only
No | IMP-083 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-029 | User Story | Accessibility issues are logged but not prioritised into improvements. | Accessibility issues are logged but not prioritised into improvements. | Digital Self-Service | Digital Accessibility | Low | Aisha Khan | EVD-029 |  | Root cause: Accessibility backlog is not linked to service priorities
No | IMP-084 | Discovery_Command_Pack_White_Label_v1.xlsx | 13 Pain Point Register | Pain Point | PP-030 | User Story | Actions raised in governance meetings are not tracked centrally. | Actions raised in governance meetings are not tracked centrally. | Reporting & Insight | Management Oversight | Medium | Nadia Shah | EVD-030 |  | Root cause: Actions are scattered across decks and emails