## Start_Here
StratForge Requirements Professional
Hybrid requirements management workbook for Agile, Waterfall and governed transformation delivery.
Project Control |  |  | Product Navigation
Workbook version | v2.0 |  | 1 | Configure project and lists | Config
Project name | Example D365 Service Transformation |  | 2 | Capture objectives and outcomes | Objectives_Outcomes
Delivery mode | Hybrid |  | 3 | Capture stakeholders and personas | Stakeholders_Personas
Workbook owner | Lead Business Analyst |  | 4 | Log source evidence | Sources_Evidence
Product owner | Product Owner |  | 5 | Capture requirements | Requirements_Register
Suggested next Requirement ID | REQ-0021 |  | 6 | Add acceptance criteria and NFRs | Acceptance_Criteria / NFR_Catalogue
Total requirements | 20 |  | 7 | Link traceability and tests | Traceability_Matrix / Test_Coverage
Sample rows | 20 |  | 8 | Review quality gates and dashboard | Quality_Gates / Dashboard
Delivery readiness | 25% |  | 9 | Export governance summary | Export_Report
Commercial usage workflow
Step | Activity | Purpose | Output / Check
1 | Select delivery mode and project settings. | Align workbook behaviour and guidance to Agile, Waterfall or Hybrid delivery. | Config and dashboard report context confirmed.
2 | Define objectives, outcomes, stakeholders and sources. | Create the evidence base and accountability model before requirements are captured. | Requirements can be traced to outcomes, sources and owners.
3 | Capture requirements in the master register. | Maintain a single source of truth for all requirement types. | Each requirement has an ID, owner, source, objective, priority and status.
4 | Add acceptance criteria, NFRs, test coverage and traceability. | Convert requirements into verifiable delivery and assurance artefacts. | Delivery readiness and quality gates begin to pass.
5 | Manage changes, RAID and baseline decisions. | Control requirement volatility and make governance decisions explicit. | Open changes and risks are visible before sign-off.
6 | Use Dashboard, Quality Gates and Export Report. | Review readiness with stakeholders and prepare governance packs. | Commercial-ready report pack for client/project use.
Design principle: single source of truth + mode-specific views + governed traceability. Do not maintain separate Agile and Waterfall requirement stores; use Delivery Mode and Requirement Level to control how records are surfaced.

## Dashboard
Executive Requirements Dashboard
Commercial-ready view of requirements quality, delivery readiness, traceability and governance health.
Project | Example D365 Service Transformation | [5 empty] | Delivery Mode | Hybrid | Last Refreshed | 02/06/2026
Total Requirements |  | Active Requirements |  | Average Quality |  | Delivery Ready |  | Traceability Complete | Open Changes |  | Open RAID
20 |  | 20 |  | 88.25 |  | 25% |  | 80% | 2 |  | 4
Lifecycle Status | Count |  | Delivery Mode | Count |  | MoSCoW | Count |  | Exception | Count
Draft | 7 |  | Agile | 7 |  | Must | 11 |  | Missing owner | 0
Analysing | 1 |  | Waterfall | 6 |  | Should | 7 |  | Missing AC | 5
In Review | 5 |  | Hybrid | 7 |  | Could | 2 |  | Missing tests | 5
Approved | 4 |  |  |  |  | Won't | 0 |  | Traceability gaps | 4
Baselined | 1 | [7 empty] | Approval pending | 14
In Delivery | 0 | [7 empty] | Open change | 2
Built | 0
In Test | 0
Done | 0
Rejected | 0
Deferred | 2
Top priority requirements and delivery exceptions
Requirement ID | Title | MoSCoW | Priority Score | Lifecycle Status | Delivery Readiness | Exception Flags
REQ-0001 | Standardise customer case handling | Must | 77 | Approved | Not Ready | No AC; No test; AC required; Test required
REQ-0018 | Define standard service taxonomy | Must | 77 | Approved | Ready for Delivery
REQ-0002 | Capture standard case intake data | Must | 74 | In Review | Not Ready | No AC; No test; AC required; Test required; Approval pending
REQ-0003 | Create case from customer email | Must | 74 | Analysing | Ready for Delivery
REQ-0005 | Maintain case audit history | Must | 74 | Baselined | Ready for Delivery
REQ-0004 | Classify case by service category | Must | 72 | Approved | Ready for Delivery
REQ-0011 | Apply GDPR retention controls | Must | 72 | Approved | Ready for Delivery
REQ-0012 | Notify advisor of SLA risk | Should | 70 | Draft | Not Ready | Approval pending
REQ-0013 | Enforce role-based case access | Must | 70 | In Review | Not Ready | Approval pending
REQ-0014 | Train service advisors before go-live | Must | 70 | Draft | Not Ready | Approval pending

## Requirements_Register
Requirements Register
Single source of truth for all Agile, Waterfall and Hybrid requirement records.
Requirement ID | Parent ID | Delivery Mode | Requirement Level | Requirement Type | Domain | Title | Requirement Statement | User Story | Business Rule / Constraint | Objective ID | Process Area | Persona / User Group | Source ID | Owner | Approver | MoSCoW | Business Value | Urgency | Risk Reduction | Opportunity Enablement | Job Size | Reach | Impact | Confidence % | Effort | WSJF Score | RICE Score | Priority Score | Complexity | Requirement Risk | Dependency Status | Lifecycle Status | Approval Status | Baseline Version | Baseline Date | Release / Sprint | Target Date | AC Count | Test Count | Trace Link Count | Open Change Count | RAID Count | Traceability Status | Quality Score | Review Readiness | Delivery Readiness | Governance Gate | Exception Flags | Last Updated | Sample Flag | Notes | Helper - Exception Raw | Helper - Agile View Seq | Helper - Predictive View Seq | Helper - All View Seq | Helper - Priority Rank | Helper - Exception Seq
REQ-0001 |  | Hybrid | Epic | Business | Customer Service | Standardise customer case handling | The organisation needs a single governed customer case handling approach across service teams to reduce duplicate work and improve service consistency. |  |  | OBJ-001 | Case intake and triage | Service Advisor | SRC-001 | Lead Business Analyst | Product Owner | Must | 10 | 8 | 7 | 8 | 6 | 500 | 2 | 80% | 60 | 5.5 | 13.3 | 77 | 6 | 4 | Internal dependency | Approved | Approved | BL-001 | 2026-05-20 | Release 1 | 2026-08-31 | 0 | 0 | 1 | 0 | 0 | Traced | 75 | Ready for Review | Not Ready | Action Required | No AC; No test; AC required; Test required | 2026-06-02 | Yes | Strategic parent requirement for case transformation. | No AC; No test; AC required; Test required; | 1 | 1 | 1 | 1 | 1
REQ-0002 | REQ-0001 | Agile | Feature | Functional | D365 | Capture standard case intake data | The solution shall capture mandatory case intake fields consistently across all customer service teams. |  |  | OBJ-001 | Case intake and triage | Service Advisor | SRC-002 | Business Analyst | Service Owner | Must | 9 | 8 | 6 | 7 | 4 | 500 | 2 | 75% | 30 | 7.5 | 25 | 74 | 4 | 4 | None | In Review | In Review |  |  | Sprint 1 | 2026-07-15 | 0 | 0 | 1 | 0 | 0 | Traced | 70 | Ready for Review | Not Ready | Action Required | No AC; No test; AC required; Test required; Approval pending | 2026-06-02 | Yes |  | No AC; No test; AC required; Test required; Approval pending; | 2 |  | 2 | 3 | 2
REQ-0003 | REQ-0002 | Agile | User Story | Functional | D365 | Create case from customer email | Customer emails must create a case record with the original email retained as source evidence. | As a service advisor, I want customer emails to create case records so that work can be triaged without manual rekeying. |  | OBJ-001 | Case intake and triage | Service Advisor | SRC-002 | Product Owner | Service Owner | Must | 8 | 9 | 6 | 6 | 3 | 350 | 2 | 70% | 18 | 9.67 | 27.2 | 74 | 3 | 3 | None | Analysing | Not Required |  |  | Sprint 1 | 2026-07-10 | 1 | 1 | 1 | 0 | 0 | Traced | 100 | Ready for Review | Ready for Delivery | Pass |  | 2026-06-02 | Yes |  |  | 3 |  | 3 | 4
REQ-0004 | REQ-0002 | Agile | User Story | Functional | D365 | Classify case by service category | The case form shall require a service category, sub-category and priority before the case can move to triage. | As a service advisor, I want to classify a case using standard categories so that it can be routed and reported consistently. | Priority cannot be blank when case status is submitted for triage. | OBJ-001 | Case intake and triage | Service Advisor | SRC-003 | Business Analyst | Service Owner | Must | 8 | 7 | 7 | 6 | 3 | 400 | 2 | 80% | 16 | 9.33 | 40 | 72 | 3 | 3 | None | Approved | Approved | BL-001 | 2026-05-20 | Sprint 1 | 2026-07-20 | 1 | 1 | 1 | 0 | 0 | Traced | 100 | Ready for Review | Ready for Delivery | Pass |  | 2026-06-02 | Yes |  |  | 4 |  | 4 | 6
REQ-0005 | REQ-0001 | Waterfall | NFR | Non-functional | Compliance | Maintain case audit history | The system shall retain an audit history for case status, owner, priority and SLA changes for a minimum of seven years. |  | Audit records must not be editable by end users. | OBJ-002 | Audit and compliance | Compliance Lead | SRC-004 | Solution Architect | Compliance Lead | Must | 9 | 6 | 10 | 4 | 4 | 100 | 3 | 80% | 30 | 7.25 | 8 | 74 | 5 | 5 | External dependency | Baselined | Baselined | BL-001 | 2026-05-20 | Release 1 | 2026-08-15 | 1 | 1 | 1 | 0 | 0 | Traced | 100 | Ready for Review | Ready for Delivery | Pass |  | 2026-06-02 | Yes | Mapped to security and compliance NFR catalogue. |  |  | 2 | 5 | 5
REQ-0006 | REQ-0001 | Hybrid | Requirement | Data | Data Migration | Migrate active customer cases | The implementation shall migrate active customer cases with current owner, priority, status and latest interaction summary. |  |  | OBJ-003 | Data migration | Data Migration Analyst | SRC-005 | Data Lead | Programme Manager | Should | 7 | 6 | 8 | 5 | 7 | 25000 | 1.5 | 60% | 80 | 3.71 | 281.3 | 60 | 8 | 7 | External dependency | In Review | In Review |  |  | Release 1 | 2026-08-31 | 1 | 1 | 1 | 1 | 1 | Traced | 95 | Ready for Review | Not Ready | Action Required | Approval pending; Open change | 2026-06-02 | Yes |  | Approval pending; Open change; | 5 | 3 | 6 | 16 | 3
REQ-0007 | REQ-0001 | Agile | Feature | Automation | Power Platform | Automate triage routing | The solution shall route cases to the correct queue based on service category, customer segment and priority. |  |  | OBJ-004 | Case routing | Service Manager | SRC-006 | Power Platform Lead | Product Owner | Should | 8 | 6 | 6 | 8 | 5 | 500 | 2 | 70% | 40 | 5.6 | 17.5 | 66 | 6 | 5 | Internal dependency | Draft | Not Started |  |  | Sprint 2 | 2026-08-10 | 0 | 0 | 0 | 0 | 0 | Partial | 60 | Needs Work | Not Ready | Action Required | No AC; No test; No trace link; AC required; Test required; Approval pending | 2026-06-02 | Yes |  | No AC; No test; No trace link; AC required; Test required; Approval pending; | 6 |  | 7 | 12 | 4
REQ-0008 | REQ-0007 | Agile | User Story | Automation | Power Platform | Route cases by SLA priority | High priority cases shall be routed to the priority queue when SLA remaining time is below the configured threshold. | As a service manager, I want high priority cases routed automatically so that SLA breaches are prevented. |  | OBJ-004 | Case routing | Service Manager | SRC-006 | Power Platform Lead | Product Owner | Should | 7 | 6 | 7 | 7 | 4 | 300 | 2 | 70% | 24 | 6.75 | 17.5 | 65 | 5 | 5 | Internal dependency | Draft | Not Started |  |  | Sprint 2 | 2026-08-10 | 1 | 1 | 1 | 0 | 0 | Traced | 95 | Ready for Review | Not Ready | Action Required | Approval pending | 2026-06-02 | Yes |  | Approval pending; | 7 |  | 8 | 13 | 5
REQ-0009 | REQ-0001 | Waterfall | Requirement | Integration | Integration | Integrate account master data | D365 Customer Service shall consume customer account reference data from the enterprise account master. |  | Customer account identifiers must remain consistent with the enterprise master data model. | OBJ-003 | Integration and master data | Integration Lead | SRC-007 | Integration Lead | Solution Architect | Must | 8 | 7 | 8 | 7 | 8 | 50000 | 2 | 65% | 120 | 3.75 | 541.7 | 65 | 9 | 8 | External dependency | In Review | In Review |  |  | Release 1 | 2026-09-15 | 1 | 1 | 1 | 1 | 1 | Traced | 95 | Ready for Review | Not Ready | Action Required | Approval pending; Open change | 2026-06-02 | Yes |  | Approval pending; Open change; |  | 4 | 9 | 14 | 6
REQ-0010 | REQ-0001 | Hybrid | Requirement | Reporting | Reporting | Provide operational case dashboard | The solution shall provide an operational dashboard showing open cases by priority, owner, age and SLA status. |  |  | OBJ-005 | Service performance reporting | Operations Lead | SRC-008 | Reporting Lead | Operations Lead | Should | 7 | 6 | 5 | 7 | 4 | 30 | 2 | 80% | 25 | 6.25 | 1.9 | 62 | 4 | 4 | Internal dependency | Draft | Not Started |  |  | Sprint 3 | 2026-08-25 | 1 | 1 | 1 | 0 | 0 | Traced | 95 | Ready for Review | Not Ready | Action Required | Approval pending | 2026-06-02 | Yes |  | Approval pending; | 8 | 5 | 10 | 15 | 7
REQ-0011 | REQ-0001 | Waterfall | Requirement | Compliance | Compliance | Apply GDPR retention controls | The solution shall support retention and deletion controls for customer case records in line with the agreed data retention policy. |  | Personal data must be retained only for the approved retention period unless legal hold applies. | OBJ-002 | Audit and compliance | Compliance Lead | SRC-004 | Compliance Lead | Data Protection Officer | Must | 8 | 8 | 10 | 4 | 5 | 50000 | 3 | 75% | 70 | 6 | 1607.1 | 72 | 7 | 7 | External dependency | Approved | Approved | BL-001 | 2026-05-20 | Release 1 | 2026-09-30 | 1 | 1 | 1 | 0 | 0 | Traced | 100 | Ready for Review | Ready for Delivery | Pass |  | 2026-06-02 | Yes |  |  |  | 6 | 11 | 7
REQ-0012 | REQ-0007 | Agile | User Story | Automation | Power Platform | Notify advisor of SLA risk | The solution shall notify the assigned advisor when a case is approaching SLA breach. | As a service advisor, I want to be notified when my case is approaching SLA breach so that I can take action before service failure. |  | OBJ-004 | SLA management | Service Advisor | SRC-006 | Power Platform Lead | Service Owner | Should | 7 | 7 | 8 | 6 | 3 | 400 | 2 | 75% | 20 | 9.33 | 30 | 70 | 4 | 4 | Internal dependency | Draft | Not Started |  |  | Sprint 2 | 2026-08-05 | 1 | 1 | 1 | 0 | 0 | Traced | 95 | Ready for Review | Not Ready | Action Required | Approval pending | 2026-06-02 | Yes |  | Approval pending; | 9 |  | 12 | 8 | 8
REQ-0013 | REQ-0001 | Hybrid | NFR | Security | Security | Enforce role-based case access | The solution shall restrict case visibility and update permissions based on role, team and customer segment. |  | Privileged access must be reviewed before production deployment. | OBJ-002 | Security and access | Security Lead | SRC-009 | Security Lead | Solution Architect | Must | 8 | 7 | 9 | 5 | 5 | 500 | 3 | 70% | 55 | 5.8 | 19.1 | 70 | 7 | 6 | Internal dependency | In Review | In Review |  |  | Release 1 | 2026-08-20 | 1 | 1 | 1 | 0 | 1 | Traced | 95 | Ready for Review | Not Ready | Action Required | Approval pending | 2026-06-02 | Yes |  | Approval pending; | 10 | 7 | 13 | 9 | 9
REQ-0014 | REQ-0001 | Waterfall | Requirement | Transition | Change Management | Train service advisors before go-live | All impacted service advisors shall complete process and system training before production go-live. |  |  | OBJ-004 | Change readiness | Service Advisor | SRC-010 | Change Manager | Programme Manager | Must | 7 | 8 | 8 | 5 | 4 | 500 | 2 | 85% | 35 | 7 | 24.3 | 70 | 4 | 4 | Internal dependency | Draft | Not Started |  |  | Release 1 | 2026-09-10 | 1 | 1 | 1 | 0 | 1 | Traced | 95 | Ready for Review | Not Ready | Action Required | Approval pending | 2026-06-02 | Yes |  | Approval pending; |  | 8 | 14 | 10 | 10
REQ-0015 | REQ-0001 | Hybrid | Feature | Analytics | Customer Service | Suggest knowledge articles | The service workspace should suggest relevant knowledge articles based on case category and customer issue description. |  |  | OBJ-005 | Knowledge management | Service Advisor | SRC-011 | Product Owner | Service Owner | Could | 5 | 4 | 3 | 7 | 5 | 350 | 1.5 | 55% | 45 | 3.8 | 6.4 | 45 | 6 | 6 | Internal dependency | Deferred | Not Started |  |  | Release 2 | 2026-11-15 | 0 | 0 | 0 | 0 | 1 | Partial | 60 | Needs Work | Not Ready | Action Required | No AC; No test; No trace link; AC required; Test required; Approval pending | 2026-06-02 | Yes |  | No AC; No test; No trace link; AC required; Test required; Approval pending; | 11 | 9 | 15 | 20 | 11
REQ-0016 | REQ-0015 | Agile | User Story | Analytics | Customer Service | Select suggested knowledge article | The user shall be able to open and apply a suggested knowledge article from the case workspace. | As a service advisor, I want to select a suggested knowledge article so that I can resolve standard enquiries more quickly. |  | OBJ-005 | Knowledge management | Service Advisor | SRC-011 | Product Owner | Service Owner | Could | 5 | 4 | 3 | 7 | 3 | 350 | 1.5 | 55% | 20 | 6.33 | 14.4 | 48 | 5 | 5 | Internal dependency | Deferred | Not Started |  |  | Release 2 | 2026-11-15 | 0 | 0 | 0 | 0 | 0 | Partial | 60 | Needs Work | Not Ready | Action Required | No AC; No test; No trace link; AC required; Test required; Approval pending | 2026-06-02 | Yes |  | No AC; No test; No trace link; AC required; Test required; Approval pending; | 12 |  | 16 | 19 | 12
REQ-0017 | REQ-0006 | Hybrid | Requirement | Data | Data Migration | Apply data quality rules before migration | Source case records shall pass agreed data quality rules before migration into the target solution. |  | Records failing mandatory validation must be remediated or formally excluded with approval. | OBJ-003 | Data migration | Data Migration Analyst | SRC-005 | Data Lead | Programme Manager | Must | 8 | 7 | 9 | 5 | 6 | 25000 | 2 | 65% | 75 | 4.83 | 433.3 | 68 | 8 | 7 | External dependency | In Review | In Review |  |  | Release 1 | 2026-08-15 | 1 | 1 | 1 | 0 | 0 | Traced | 95 | Ready for Review | Not Ready | Action Required | Approval pending | 2026-06-02 | Yes |  | Approval pending; | 13 | 10 | 17 | 11 | 13
REQ-0018 | REQ-0001 | Waterfall | Requirement | Process | Operations | Define standard service taxonomy | The business shall approve a standard taxonomy for case categories, sub-categories, priorities and escalation reasons. |  |  | OBJ-001 | Operating model | Service Manager | SRC-003 | Service Owner | Operations Lead | Must | 9 | 8 | 7 | 8 | 4 | 500 | 2 | 85% | 25 | 8 | 34 | 77 | 4 | 4 | None | Approved | Approved | BL-001 | 2026-05-20 | Release 1 | 2026-07-31 | 1 | 1 | 1 | 0 | 0 | Traced | 100 | Ready for Review | Ready for Delivery | Pass |  | 2026-06-02 | Yes |  |  |  | 11 | 18 | 2
REQ-0019 | REQ-0001 | Hybrid | NFR | Non-functional | D365 | Maintain acceptable form response time | Primary case forms should load within three seconds for users on supported devices and network conditions. |  |  | OBJ-005 | User experience | Service Advisor | SRC-012 | Solution Architect | Product Owner | Should | 6 | 5 | 6 | 6 | 4 | 500 | 1.5 | 70% | 35 | 5.75 | 15 | 57 | 5 | 5 | None | Draft | Not Started |  |  | Release 1 | 2026-08-31 | 1 | 1 | 1 | 0 | 0 | Traced | 95 | Ready for Review | Not Ready | Action Required | Approval pending | 2026-06-02 | Yes |  | Approval pending; | 14 | 12 | 19 | 18 | 14
REQ-0020 | REQ-0001 | Waterfall | Requirement | Reporting | Reporting | Approve service manager dashboard | Service managers require a dashboard that supports workload monitoring, SLA management and team performance review. |  |  | OBJ-005 | Service performance reporting | Service Manager | SRC-008 | Operations Lead | Service Owner | Should | 7 | 5 | 5 | 7 | 4 | 20 | 2 | 75% | 22 | 6 | 1.4 | 60 | 4 | 4 | Internal dependency | Draft | Not Started |  |  | Sprint 3 | 2026-08-25 | 1 | 1 | 0 | 0 | 0 | Partial | 85 | Ready for Review | Not Ready | Action Required | No trace link; Approval pending | 2026-06-02 | Yes |  | No trace link; Approval pending; |  | 13 | 20 | 17 | 15

## Agile_Backlog
Agile Backlog View
Formula-driven view of epics, features and user stories from the master requirements register.
Requirement ID | Parent ID | Level | Type | Title | User Story | MoSCoW | WSJF | Priority Score | Lifecycle Status | Release / Sprint | Review Readiness | Delivery Readiness
REQ-0001 |  | Epic | Business | Standardise customer case handling |  | Must | 5.5 | 77 | Approved | Release 1 | Ready for Review | Not Ready
REQ-0002 | REQ-0001 | Feature | Functional | Capture standard case intake data |  | Must | 7.5 | 74 | In Review | Sprint 1 | Ready for Review | Not Ready
REQ-0003 | REQ-0002 | User Story | Functional | Create case from customer email | As a service advisor, I want customer emails to create case records so that work can be triaged without manual rekeying. | Must | 9.67 | 74 | Analysing | Sprint 1 | Ready for Review | Ready for Delivery
REQ-0004 | REQ-0002 | User Story | Functional | Classify case by service category | As a service advisor, I want to classify a case using standard categories so that it can be routed and reported consistently. | Must | 9.33 | 72 | Approved | Sprint 1 | Ready for Review | Ready for Delivery
REQ-0006 | REQ-0001 | Requirement | Data | Migrate active customer cases |  | Should | 3.71 | 60 | In Review | Release 1 | Ready for Review | Not Ready
REQ-0007 | REQ-0001 | Feature | Automation | Automate triage routing |  | Should | 5.6 | 66 | Draft | Sprint 2 | Needs Work | Not Ready
REQ-0008 | REQ-0007 | User Story | Automation | Route cases by SLA priority | As a service manager, I want high priority cases routed automatically so that SLA breaches are prevented. | Should | 6.75 | 65 | Draft | Sprint 2 | Ready for Review | Not Ready
REQ-0010 | REQ-0001 | Requirement | Reporting | Provide operational case dashboard |  | Should | 6.25 | 62 | Draft | Sprint 3 | Ready for Review | Not Ready
REQ-0012 | REQ-0007 | User Story | Automation | Notify advisor of SLA risk | As a service advisor, I want to be notified when my case is approaching SLA breach so that I can take action before service failure. | Should | 9.33 | 70 | Draft | Sprint 2 | Ready for Review | Not Ready
REQ-0013 | REQ-0001 | NFR | Security | Enforce role-based case access |  | Must | 5.8 | 70 | In Review | Release 1 | Ready for Review | Not Ready
REQ-0015 | REQ-0001 | Feature | Analytics | Suggest knowledge articles |  | Could | 3.8 | 45 | Deferred | Release 2 | Needs Work | Not Ready
REQ-0016 | REQ-0015 | User Story | Analytics | Select suggested knowledge article | As a service advisor, I want to select a suggested knowledge article so that I can resolve standard enquiries more quickly. | Could | 6.33 | 48 | Deferred | Release 2 | Needs Work | Not Ready
REQ-0017 | REQ-0006 | Requirement | Data | Apply data quality rules before migration |  | Must | 4.83 | 68 | In Review | Release 1 | Ready for Review | Not Ready
REQ-0019 | REQ-0001 | NFR | Non-functional | Maintain acceptable form response time |  | Should | 5.75 | 57 | Draft | Release 1 | Ready for Review | Not Ready
0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0

## Predictive_Requirements
Predictive Requirements View
Formal BABOK-style requirements governance view for Waterfall and controlled delivery environments.
Requirement ID | Parent ID | Type | Domain | Title | Requirement Statement | Owner | Approver | MoSCoW | Lifecycle Status | Approval Status | Baseline Version | AC Count | Test Count | Traceability | Quality Score | Governance Gate
REQ-0001 |  | Business | Customer Service | Standardise customer case handling | The organisation needs a single governed customer case handling approach across service teams to reduce duplicate work and improve service consistency. | Lead Business Analyst | Product Owner | Must | Approved | Approved | BL-001 | 0 | 0 | Traced | 75 | Action Required
REQ-0005 | REQ-0001 | Non-functional | Compliance | Maintain case audit history | The system shall retain an audit history for case status, owner, priority and SLA changes for a minimum of seven years. | Solution Architect | Compliance Lead | Must | Baselined | Baselined | BL-001 | 1 | 1 | Traced | 100 | Pass
REQ-0006 | REQ-0001 | Data | Data Migration | Migrate active customer cases | The implementation shall migrate active customer cases with current owner, priority, status and latest interaction summary. | Data Lead | Programme Manager | Should | In Review | In Review |  | 1 | 1 | Traced | 95 | Action Required
REQ-0009 | REQ-0001 | Integration | Integration | Integrate account master data | D365 Customer Service shall consume customer account reference data from the enterprise account master. | Integration Lead | Solution Architect | Must | In Review | In Review |  | 1 | 1 | Traced | 95 | Action Required
REQ-0010 | REQ-0001 | Reporting | Reporting | Provide operational case dashboard | The solution shall provide an operational dashboard showing open cases by priority, owner, age and SLA status. | Reporting Lead | Operations Lead | Should | Draft | Not Started |  | 1 | 1 | Traced | 95 | Action Required
REQ-0011 | REQ-0001 | Compliance | Compliance | Apply GDPR retention controls | The solution shall support retention and deletion controls for customer case records in line with the agreed data retention policy. | Compliance Lead | Data Protection Officer | Must | Approved | Approved | BL-001 | 1 | 1 | Traced | 100 | Pass
REQ-0013 | REQ-0001 | Security | Security | Enforce role-based case access | The solution shall restrict case visibility and update permissions based on role, team and customer segment. | Security Lead | Solution Architect | Must | In Review | In Review |  | 1 | 1 | Traced | 95 | Action Required
REQ-0014 | REQ-0001 | Transition | Change Management | Train service advisors before go-live | All impacted service advisors shall complete process and system training before production go-live. | Change Manager | Programme Manager | Must | Draft | Not Started |  | 1 | 1 | Traced | 95 | Action Required
REQ-0015 | REQ-0001 | Analytics | Customer Service | Suggest knowledge articles | The service workspace should suggest relevant knowledge articles based on case category and customer issue description. | Product Owner | Service Owner | Could | Deferred | Not Started |  | 0 | 0 | Partial | 60 | Action Required
REQ-0017 | REQ-0006 | Data | Data Migration | Apply data quality rules before migration | Source case records shall pass agreed data quality rules before migration into the target solution. | Data Lead | Programme Manager | Must | In Review | In Review |  | 1 | 1 | Traced | 95 | Action Required
REQ-0018 | REQ-0001 | Process | Operations | Define standard service taxonomy | The business shall approve a standard taxonomy for case categories, sub-categories, priorities and escalation reasons. | Service Owner | Operations Lead | Must | Approved | Approved | BL-001 | 1 | 1 | Traced | 100 | Pass
REQ-0019 | REQ-0001 | Non-functional | D365 | Maintain acceptable form response time | Primary case forms should load within three seconds for users on supported devices and network conditions. | Solution Architect | Product Owner | Should | Draft | Not Started |  | 1 | 1 | Traced | 95 | Action Required
REQ-0020 | REQ-0001 | Reporting | Reporting | Approve service manager dashboard | Service managers require a dashboard that supports workload monitoring, SLA management and team performance review. | Operations Lead | Service Owner | Should | Draft | Not Started |  | 1 | 1 | Partial | 85 | Action Required
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Hybrid_Control_View
Hybrid Control View
Combined delivery and governance lens for mixed Agile, Waterfall and enterprise transformation programmes.
Requirement ID | Delivery Mode | Level | Type | Domain | Title | Objective ID | Process Area | Source ID | Owner | Priority Score | Lifecycle Status | Delivery Readiness | Governance Gate | Exception Flags
REQ-0001 | Hybrid | Epic | Business | Customer Service | Standardise customer case handling | OBJ-001 | Case intake and triage | SRC-001 | Lead Business Analyst | 77 | Approved | Not Ready | Action Required | No AC; No test; AC required; Test required
REQ-0002 | Agile | Feature | Functional | D365 | Capture standard case intake data | OBJ-001 | Case intake and triage | SRC-002 | Business Analyst | 74 | In Review | Not Ready | Action Required | No AC; No test; AC required; Test required; Approval pending
REQ-0003 | Agile | User Story | Functional | D365 | Create case from customer email | OBJ-001 | Case intake and triage | SRC-002 | Product Owner | 74 | Analysing | Ready for Delivery | Pass
REQ-0004 | Agile | User Story | Functional | D365 | Classify case by service category | OBJ-001 | Case intake and triage | SRC-003 | Business Analyst | 72 | Approved | Ready for Delivery | Pass
REQ-0005 | Waterfall | NFR | Non-functional | Compliance | Maintain case audit history | OBJ-002 | Audit and compliance | SRC-004 | Solution Architect | 74 | Baselined | Ready for Delivery | Pass
REQ-0006 | Hybrid | Requirement | Data | Data Migration | Migrate active customer cases | OBJ-003 | Data migration | SRC-005 | Data Lead | 60 | In Review | Not Ready | Action Required | Approval pending; Open change
REQ-0007 | Agile | Feature | Automation | Power Platform | Automate triage routing | OBJ-004 | Case routing | SRC-006 | Power Platform Lead | 66 | Draft | Not Ready | Action Required | No AC; No test; No trace link; AC required; Test required; Approval pending
REQ-0008 | Agile | User Story | Automation | Power Platform | Route cases by SLA priority | OBJ-004 | Case routing | SRC-006 | Power Platform Lead | 65 | Draft | Not Ready | Action Required | Approval pending
REQ-0009 | Waterfall | Requirement | Integration | Integration | Integrate account master data | OBJ-003 | Integration and master data | SRC-007 | Integration Lead | 65 | In Review | Not Ready | Action Required | Approval pending; Open change
REQ-0010 | Hybrid | Requirement | Reporting | Reporting | Provide operational case dashboard | OBJ-005 | Service performance reporting | SRC-008 | Reporting Lead | 62 | Draft | Not Ready | Action Required | Approval pending
REQ-0011 | Waterfall | Requirement | Compliance | Compliance | Apply GDPR retention controls | OBJ-002 | Audit and compliance | SRC-004 | Compliance Lead | 72 | Approved | Ready for Delivery | Pass
REQ-0012 | Agile | User Story | Automation | Power Platform | Notify advisor of SLA risk | OBJ-004 | SLA management | SRC-006 | Power Platform Lead | 70 | Draft | Not Ready | Action Required | Approval pending
REQ-0013 | Hybrid | NFR | Security | Security | Enforce role-based case access | OBJ-002 | Security and access | SRC-009 | Security Lead | 70 | In Review | Not Ready | Action Required | Approval pending
REQ-0014 | Waterfall | Requirement | Transition | Change Management | Train service advisors before go-live | OBJ-004 | Change readiness | SRC-010 | Change Manager | 70 | Draft | Not Ready | Action Required | Approval pending
REQ-0015 | Hybrid | Feature | Analytics | Customer Service | Suggest knowledge articles | OBJ-005 | Knowledge management | SRC-011 | Product Owner | 45 | Deferred | Not Ready | Action Required | No AC; No test; No trace link; AC required; Test required; Approval pending
REQ-0016 | Agile | User Story | Analytics | Customer Service | Select suggested knowledge article | OBJ-005 | Knowledge management | SRC-011 | Product Owner | 48 | Deferred | Not Ready | Action Required | No AC; No test; No trace link; AC required; Test required; Approval pending
REQ-0017 | Hybrid | Requirement | Data | Data Migration | Apply data quality rules before migration | OBJ-003 | Data migration | SRC-005 | Data Lead | 68 | In Review | Not Ready | Action Required | Approval pending
REQ-0018 | Waterfall | Requirement | Process | Operations | Define standard service taxonomy | OBJ-001 | Operating model | SRC-003 | Service Owner | 77 | Approved | Ready for Delivery | Pass
REQ-0019 | Hybrid | NFR | Non-functional | D365 | Maintain acceptable form response time | OBJ-005 | User experience | SRC-012 | Solution Architect | 57 | Draft | Not Ready | Action Required | Approval pending
REQ-0020 | Waterfall | Requirement | Reporting | Reporting | Approve service manager dashboard | OBJ-005 | Service performance reporting | SRC-008 | Operations Lead | 60 | Draft | Not Ready | Action Required | No trace link; Approval pending
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0

## Acceptance_Criteria
Acceptance Criteria Register
Reusable acceptance criteria linked to requirements, stories, tests and sign-off evidence.
AC ID | Requirement ID | AC Type | Scenario / Title | Given | When | Then | Acceptance Criterion | Priority | Owner | Status | Linked Test ID | Quality Status | Notes
AC-001 | REQ-0003 | Given / When / Then | Email creates a case | Given a customer email is received in the service mailbox | When the intake process runs | Then a new case record is created with the original email retained |  | Must | Business Analyst | Reviewed | TST-001 | Usable
AC-002 | REQ-0004 | Checklist | Mandatory classification fields |  |  |  | Service category, sub-category and priority must be populated before case triage. | Must | Business Analyst | Approved | TST-002 | Usable
AC-003 | REQ-0005 | Compliance Control | Audit history retained |  |  |  | Case status, owner, priority and SLA changes are retained for at least seven years and are not user-editable. | Must | Compliance Lead | Approved | TST-003 | Usable
AC-004 | REQ-0006 | Checklist | Migration fields retained |  |  |  | Migrated cases include owner, priority, status and latest interaction summary. | Should | Data Lead | Reviewed | TST-004 | Usable
AC-005 | REQ-0008 | Given / When / Then | High priority routing | Given a case is high priority | When SLA remaining time falls below the defined threshold | Then the case is routed to the priority queue |  | Should | Power Platform Lead | Draft | TST-005 | Usable
AC-006 | REQ-0009 | Checklist | Account identifier consistency |  |  |  | Imported account references match the enterprise account master identifier. | Must | Integration Lead | Reviewed | TST-006 | Usable
AC-007 | REQ-0010 | Checklist | Dashboard fields displayed |  |  |  | Dashboard displays open cases by priority, owner, age and SLA status. | Should | Reporting Lead | Draft | TST-007 | Usable
AC-008 | REQ-0011 | Compliance Control | Retention control |  |  |  | Customer case records are retained and deleted according to approved retention policy rules. | Must | Compliance Lead | Approved | TST-008 | Usable
AC-009 | REQ-0012 | Given / When / Then | SLA risk notification | Given a case is assigned to an advisor | When the case approaches SLA breach | Then the advisor receives a notification |  | Should | Power Platform Lead | Draft | TST-009 | Usable
AC-010 | REQ-0013 | Security Control | Role-based access |  |  |  | Users can only view and update cases permitted by their assigned role and team. | Must | Security Lead | Reviewed | TST-010 | Usable
AC-011 | REQ-0014 | Checklist | Training completion |  |  |  | All impacted service advisors complete training before production go-live. | Must | Change Manager | Draft | TST-011 | Usable
AC-012 | REQ-0017 | Checklist | Migration quality rules |  |  |  | Records failing mandatory validation are remediated or formally excluded with approval. | Must | Data Lead | Reviewed | TST-012 | Usable
AC-013 | REQ-0018 | Checklist | Taxonomy approved |  |  |  | The taxonomy is approved by the Service Owner and Operations Lead before configuration. | Must | Service Owner | Approved | TST-013 | Usable
AC-014 | REQ-0019 | NFR Metric | Form load response time |  |  |  | Primary case forms load within three seconds under agreed supported network and device conditions. | Should | Solution Architect | Draft | TST-014 | Usable
AC-015 | REQ-0020 | Checklist | Service manager dashboard approval |  |  |  | Service managers approve the dashboard layout and available dimensions before go-live. | Should | Operations Lead | Draft | TST-015 | Usable

## Traceability_Matrix
Traceability Matrix
End-to-end linkage from objectives and source evidence through requirements, design, test and benefits.
Trace ID | Requirement ID | Requirement Title | Objective ID | Outcome | Source ID | Process Area | Design Reference | Build Item | Test ID | Benefit / KPI ID | Release | Trace Status | Gap Notes
TRC-001 | REQ-0001 | Standardise customer case handling | OBJ-001 | Reduce duplicate customer case handling | SRC-001 | Case intake and triage | HLD-CASE-001 | D365 Case Process | TST-001 | KPI-DUP-001 | Release 1 | Complete
TRC-002 | REQ-0002 | Capture standard case intake data | OBJ-001 | Reduce duplicate customer case handling | SRC-002 | Case intake and triage | FUNC-INTAKE-001 | D365 Case Form | TST-002 | KPI-DUP-001 | Sprint 1 | Complete
TRC-003 | REQ-0003 | Create case from customer email | OBJ-001 | Reduce duplicate customer case handling | SRC-002 | Email-to-case | FUNC-EMAIL-001 | Email to Case Flow | TST-001 | KPI-DUP-001 | Sprint 1 | Complete
TRC-004 | REQ-0004 | Classify case by service category | OBJ-001 | Reduce duplicate customer case handling | SRC-003 | Case classification | FUNC-CLASS-001 | Case Classification Fields | TST-002 | KPI-DUP-001 | Sprint 1 | Complete
TRC-005 | REQ-0005 | Maintain case audit history | OBJ-002 | Improve compliance and auditability | SRC-004 | Audit and compliance | NFR-AUD-001 | Audit Configuration | TST-003 | KPI-AUD-001 | Release 1 | Complete
TRC-006 | REQ-0006 | Migrate active customer cases | OBJ-003 | Enable clean migration to target platform | SRC-005 | Data migration | DATA-MIG-001 | Migration Mapping | TST-004 | KPI-MIG-001 | Release 1 | Complete
TRC-007 | REQ-0008 | Route cases by SLA priority | OBJ-004 | Improve SLA performance | SRC-006 | Routing automation | FLOW-ROUTE-001 | Power Automate Routing Flow | TST-005 | KPI-SLA-001 | Sprint 2 | Complete
TRC-008 | REQ-0009 | Integrate account master data | OBJ-003 | Enable clean migration to target platform | SRC-007 | Integration and master data | INT-ACCT-001 | Account Master Interface | TST-006 | KPI-MIG-001 | Release 1 | Complete
TRC-009 | REQ-0010 | Provide operational case dashboard | OBJ-005 | Improve management visibility | SRC-008 | Service performance reporting | RPT-OPS-001 | Operational Dashboard | TST-007 | KPI-REP-001 | Sprint 3 | Complete
TRC-010 | REQ-0011 | Apply GDPR retention controls | OBJ-002 | Improve compliance and auditability | SRC-004 | Retention controls | NFR-RET-001 | Retention Policy Configuration | TST-008 | KPI-AUD-001 | Release 1 | Complete
TRC-011 | REQ-0012 | Notify advisor of SLA risk | OBJ-004 | Improve SLA performance | SRC-006 | SLA management | FLOW-SLA-001 | SLA Notification Flow | TST-009 | KPI-SLA-001 | Sprint 2 | Complete
TRC-012 | REQ-0013 | Enforce role-based case access | OBJ-002 | Improve compliance and auditability | SRC-009 | Security and access | SEC-ROLE-001 | Security Roles | TST-010 | KPI-AUD-001 | Release 1 | Complete
TRC-013 | REQ-0014 | Train service advisors before go-live | OBJ-004 | Improve SLA performance | SRC-010 | Change readiness | CHG-TRN-001 | Training Pack | TST-011 | KPI-ADOPT-001 | Release 1 | Complete
TRC-014 | REQ-0017 | Apply data quality rules before migration | OBJ-003 | Enable clean migration to target platform | SRC-005 | Data quality | DATA-QUAL-001 | Data Quality Rules | TST-012 | KPI-MIG-001 | Release 1 | Complete
TRC-015 | REQ-0018 | Define standard service taxonomy | OBJ-001 | Reduce duplicate customer case handling | SRC-003 | Operating model | PROC-TAX-001 | Service Taxonomy | TST-013 | KPI-DUP-001 | Release 1 | Complete
TRC-016 | REQ-0019 | Maintain acceptable form response time | OBJ-005 | Improve management visibility | SRC-012 | User experience | NFR-PERF-001 | Performance Test Baseline | TST-014 | KPI-UX-001 | Release 1 | Complete

## Test_Coverage
Test Coverage Register
Requirement-to-test coverage, execution outcome and UAT readiness tracking.
Test ID | Requirement ID | Test Type | Scenario / Test Name | Owner | Test Status | Latest Run Date | Defect / Issue ID | Coverage Status | UAT Sign-off | Evidence Link | Notes
TST-001 | REQ-0003 | SIT | Email received creates case | Test Manager | Designed |  |  | In Progress | No | Test Repository / TST-001
TST-002 | REQ-0004 | UAT | Mandatory classification fields enforced | Test Manager | Ready |  |  | In Progress | No | Test Repository / TST-002
TST-003 | REQ-0005 | UAT | Audit history cannot be edited | Test Manager | Passed | 2026-05-29 |  | Covered | Yes | Test Repository / TST-003
TST-004 | REQ-0006 | Data Migration | Migrated case field completeness | Test Manager | In Progress | 2026-05-30 | DEF-014 | In Progress | No | Test Repository / TST-004 | Data quality defects remain under triage.
TST-005 | REQ-0008 | SIT | Priority routing flow | Test Manager | Not Started |  |  | Planned | No | Test Repository / TST-005
TST-006 | REQ-0009 | Integration | Account master lookup | Integration Lead | Designed |  |  | In Progress | No | Test Repository / TST-006
TST-007 | REQ-0010 | UAT | Operational dashboard fields | Test Manager | Not Started |  |  | Planned | No | Test Repository / TST-007
TST-008 | REQ-0011 | Regression | Retention policy control | Test Manager | Passed | 2026-05-29 |  | Covered | Yes | Test Repository / TST-008
TST-009 | REQ-0012 | SIT | SLA risk notification | Power Platform Lead | Not Started |  |  | Planned | No | Test Repository / TST-009
TST-010 | REQ-0013 | Security | Role-based visibility | Security Lead | Designed |  |  | In Progress | No | Test Repository / TST-010
TST-011 | REQ-0014 | Operational Readiness | Training completion evidence | Change Manager | Not Started |  |  | Planned | No | Test Repository / TST-011
TST-012 | REQ-0017 | Data Migration | Data quality rule exceptions | Data Lead | In Progress | 2026-05-30 |  | In Progress | No | Test Repository / TST-012
TST-013 | REQ-0018 | UAT | Taxonomy approval evidence | Service Owner | Passed | 2026-05-28 |  | Covered | Yes | Test Repository / TST-013
TST-014 | REQ-0019 | Performance | Case form response time | Solution Architect | Not Started |  |  | Planned | No | Test Repository / TST-014
TST-015 | REQ-0020 | UAT | Service manager dashboard approval | Operations Lead | Not Started |  |  | Planned | No | Test Repository / TST-015

## Change_Control
Change Control Log
Governed requirement changes, impact assessment, decisioning and baseline movement.
Change ID | Requirement ID | Change Type | Requested By | Date Raised | Change Description | Impact Level | Impact Score | Decision | Change Status | Baseline Version | Decision Date | Owner | Notes
CHG-001 | REQ-0005 | Scope Clarification | Compliance Lead | 2026-05-24 | Clarify minimum audit retention period and evidence requirements. | Medium | 6 | Approved | Implemented | BL-001 | 2026-05-28 | Solution Architect
CHG-002 | REQ-0006 | Scope Change | Data Lead | 2026-05-27 | Add latest interaction summary to migration scope. | High | 8 | In Review | In Assessment |  |  | Data Lead | Impact on mapping and testing being assessed.
CHG-003 | REQ-0009 | Dependency | Integration Lead | 2026-05-29 | Interface availability delayed by account master programme. | High | 9 | Escalated | Open |  |  | Integration Lead | Dependency must be managed via release plan.
CHG-004 | REQ-0015 | Deferment | Product Owner | 2026-05-30 | Defer knowledge article suggestions to Release 2. | Low | 3 | Approved | Approved |  | 2026-06-01 | Product Owner

## Objectives_Outcomes
Objectives and Outcomes
Business outcomes, KPIs, benefits and requirement coverage.
Objective ID | Outcome | KPI / Measure | Baseline | Target | Benefit Hypothesis | Owner | Priority | Status | Linked Requirement Count | Coverage Status | Notes
OBJ-001 | Reduce duplicate customer case handling | Duplicate case rate | 12% | 5% | Standardised intake and taxonomy will reduce duplicate work and improve triage accuracy. | Service Owner | High | Approved | 5 | Covered | Primary outcome for intake and taxonomy.
OBJ-002 | Improve compliance and auditability | Audit exceptions | Manual checks | Automated audit evidence | Traceable case history and retention controls will reduce compliance risk. | Compliance Lead | High | Approved | 3 | Covered
OBJ-003 | Enable clean migration to target platform | Migration defect rate | Unknown | <2% critical defects | Controlled data quality and integration requirements will reduce deployment risk. | Data Lead | High | In Review | 3 | Covered
OBJ-004 | Improve SLA performance | SLA breach rate | 18% | 8% | Automation and routing will reduce avoidable SLA breaches. | Operations Lead | Medium | Draft | 4 | Covered
OBJ-005 | Improve management visibility | Time to produce service report | 2 days | Same day | Operational dashboards will improve management control and service improvement. | Reporting Lead | Medium | Draft | 5 | Covered

## Stakeholders_Personas
Stakeholders and Personas
Requirement owners, approvers, SMEs, personas and engagement responsibilities.
Stakeholder ID | Name / Role | Function | Persona / User Group | Influence | Interest | Attitude | Engagement Level | Decision Authority | Requirement Ownership | Linked Requirement Count | Notes
STK-001 | Product Owner | Digital Product | Product Owner | High | High | Supportive | Empower | Backlog prioritisation | Owns backlog and delivery trade-offs | 7
STK-002 | Service Owner | Customer Service | Service Owner | High | High | Supportive | Collaborate | Business sign-off | Approves service process requirements | 8
STK-003 | Service Advisor | Customer Service | Service Advisor | Medium | High | Neutral | Involve | User acceptance input | Provides detailed usability and workflow input | 0
STK-004 | Operations Lead | Operations | Operations Lead | High | Medium | Supportive | Collaborate | Operational reporting approval | Owns operational dashboard and performance KPIs | 3
STK-005 | Solution Architect | Technology | Solution Architect | High | High | Supportive | Collaborate | Architecture/design approval | Owns design feasibility and NFR alignment | 4
STK-006 | Data Lead | Data | Data Migration Analyst | High | Medium | Neutral | Collaborate | Data migration approval | Owns migration scope and data quality rules | 2
STK-007 | Integration Lead | Technology | Integration Lead | High | Medium | Neutral | Collaborate | Integration design approval | Owns interface and master data requirements | 1
STK-008 | Security Lead | Security | Security Lead | High | Medium | Supportive | Consult | Security approval | Owns access control and security review | 1
STK-009 | Compliance Lead | Risk and Compliance | Compliance Lead | High | Medium | Supportive | Consult | Compliance approval | Owns retention, audit and policy requirements | 2
STK-010 | Test Manager | Quality Assurance | Test Manager | Medium | High | Supportive | Collaborate | Test readiness approval | Owns test coverage and defect governance | 0
STK-011 | Change Manager | Change | Change Manager | Medium | Medium | Supportive | Consult | Training and change readiness | Owns change impact and training requirements | 1
STK-012 | Power Platform Lead | Technology | Power Platform Lead | High | High | Supportive | Collaborate | Power Platform build approach | Owns Power Platform solution constraints and automation | 3

## Sources_Evidence
Sources and Evidence
Traceable evidence base for requirement origin, confidence and decision support.
Source ID | Source Type | Source Name | Date | Owner | Reliability | Summary / Evidence | Document Link / Location | Linked Requirement Count | Evidence Status | Notes
SRC-001 | Discovery Workshop | Current state case handling workshop | 2026-04-08 | Lead Business Analyst | High | Teams described inconsistent handling and duplicate cases across channels. | SharePoint / Discovery / Workshop 01 | 1 | Used
SRC-002 | Process Walkthrough | Email-to-case walkthrough | 2026-04-12 | Business Analyst | High | Observed manual rekeying from shared inbox to case tracker. | SharePoint / Discovery / Walkthrough 02 | 2 | Used
SRC-003 | Document Review | Service taxonomy draft | 2026-04-18 | Service Owner | Medium | Draft taxonomy lists category hierarchy and escalation reasons. | SharePoint / Operating Model / Taxonomy v0.3 | 2 | Used
SRC-004 | Regulatory Source | Retention and audit policy | 2026-04-20 | Compliance Lead | High | Policy specifies retention and audit requirements for customer interactions. | SharePoint / Compliance / Retention Policy | 2 | Used
SRC-005 | Data Profiling | Legacy case extract profiling | 2026-05-02 | Data Lead | Medium | Profiling identified duplicate customer identifiers and missing priority values. | Data Profiling Workbook | 2 | Used
SRC-006 | Design Workshop | Routing and SLA automation workshop | 2026-05-08 | Power Platform Lead | High | Routing rules and SLA notification needs were agreed in principle. | SharePoint / Design / Automation Workshop | 3 | Used
SRC-007 | System Analysis | Account master integration assessment | 2026-05-10 | Integration Lead | Medium | Integration dependency confirmed; interface pattern still pending. | Architecture Repository | 1 | Used
SRC-008 | Stakeholder Interview | Operations reporting interview | 2026-05-14 | Reporting Lead | High | Operations requires daily case ageing and SLA dashboards. | Interview Notes / OPS-01 | 2 | Used
SRC-009 | Document Review | Security role matrix draft | 2026-05-17 | Security Lead | Medium | Initial role matrix includes advisor, manager and compliance roles. | Security Design Draft | 1 | Used
SRC-010 | Stakeholder Interview | Change readiness interview | 2026-05-20 | Change Manager | Medium | Training and cutover readiness requirements discussed. | Interview Notes / CHG-01 | 1 | Used
SRC-011 | Discovery Workshop | Knowledge management workshop | 2026-05-25 | Product Owner | Low | Idea identified for future knowledge article recommendations. | Discovery Backlog | 2 | Used
SRC-012 | UAT Feedback | Prototype usability feedback | 2026-05-28 | Service Advisor | Medium | Users raised concern about form load performance and navigation. | UAT Feedback Log | 1 | Used

## RAID_Decisions
RAID and Decision Register
Risks, assumptions, issues, dependencies and key decisions linked to requirements.
RAID ID | RAID Type | Related Requirement ID | Description | Probability | Impact | Severity Score | RAG | Owner | Due Date | Status | Decision / Mitigation | Notes
RAID-001 | Risk | REQ-0009 | Account master interface may not be available for Sprint 2 integration testing. | 4 | 5 | 20 | Red | Integration Lead | 2026-06-14 | Open | Escalate dependency and define mocked interface fallback.
RAID-002 | Issue | REQ-0006 | Legacy source data contains missing priority values. | 5 | 4 | 20 | Red | Data Lead | 2026-06-10 | Open | Agree defaulting and remediation rules with Service Owner.
RAID-003 | Assumption | REQ-0013 | Security roles can be aligned to existing team structure. | 3 | 4 | 12 | Amber | Security Lead | 2026-06-21 | Pending Validation | Validate role matrix with Security Lead.
RAID-004 | Decision | REQ-0015 | Knowledge article suggestions deferred to Release 2. | 1 | 2 | 2 | Green | Product Owner | 2026-06-01 | Closed | Approved deferment recorded in CHG-004.
RAID-005 | Dependency | REQ-0014 | Training materials depend on finalised process and role design. | 3 | 4 | 12 | Amber | Change Manager | 2026-07-15 | Open | Schedule content review after process baseline.

## NFR_Catalogue
Non-Functional Requirements Catalogue
Performance, security, data, integration, operational and compliance requirements catalogue.
NFR ID | Linked Requirement ID | NFR Category | Quality Attribute | Metric | Target | Threshold / Tolerance | Measurement Method | Owner | Status | Test ID | Notes
NFR-001 | REQ-0005 | Auditability | Case audit history | Retention period | 7 years | No unauthorised edit/delete | Audit review and configuration inspection | Compliance Lead | Approved | TST-003
NFR-002 | REQ-0011 | Data Retention | Retention control | Retention/deletion policy execution | Policy compliant | Exceptions formally approved | Policy configuration review | Compliance Lead | Approved | TST-008
NFR-003 | REQ-0013 | Security | Role-based access | Unauthorised access attempts | 0 critical access defects | Role matrix test and penetration review | Security Lead | In Review | TST-010
NFR-004 | REQ-0019 | Performance | Case form load time | Load time | <=3 seconds | 95th percentile under supported conditions | Performance test | Solution Architect | Draft | TST-014
NFR-005 | REQ-0009 | Interoperability | Account master integration | Interface success rate | >=99% successful transactions | Critical failures escalated within support SLA | Integration test and monitoring | Integration Lead | Draft | TST-006
NFR-006 | REQ-0006 | Data Quality | Migration field completeness | Mandatory field completeness | >=98% | Critical records remediated or approved exclusion | Migration reconciliation report | Data Lead | In Review | TST-004

## Quality_Gates
Quality Gates and Exception Management
Readiness criteria and exception lists for review, approval, delivery and baseline control.
Gate ID | Gate | Purpose | Direction | Threshold | Current | Status | Action if failed | Owner
QG-001 | Ownership coverage | Requirements should have a named owner. | >= | 95% | 100% | Pass | Assign owners before review. | Lead Business Analyst
QG-002 | Acceptance criteria coverage | Requirements should be testable and accepted. | >= | 90% | 75% | Fail | Add AC for high-priority and in-scope requirements. | Business Analyst
QG-003 | Test coverage | Requirements should be linked to test evidence. | >= | 80% | 75% | Fail | Create or link test scenarios before delivery. | Test Manager
QG-004 | Traceability coverage | Requirements should be linked to objectives, sources and trace records. | >= | 90% | 80% | Fail | Add trace rows and resolve gaps. | Lead Business Analyst
QG-005 | Average quality score | Overall quality score should meet baseline threshold. | >= | 85 | 88.25 | Pass | Review missing fields, AC, test and approvals. | Lead Business Analyst
QG-006 | Delivery readiness | A target proportion of requirements should be ready for delivery. | >= | 70% | 25% | Fail | Resolve readiness blockers before build/test commitment. | Product Owner
QG-007 | Open changes | Open changes should be limited before baseline or release commitment. | <= | 0 | 2 | Fail | Resolve or formally defer open change requests. | Programme Manager
QG-008 | Red RAID items | High-severity open RAID items should not block commitment. | <= | 0 | 2 | Fail | Escalate red RAID items and agree mitigations. | Programme Manager
QG-009 | Must requirement approval | Must requirements should be approved or baselined before delivery. | >= | 90% | 45.45% | Fail | Review Must requirements with approving authority. | Product Owner
Dynamic exception list
Requirement ID | Title | MoSCoW | Quality Score | Exception Flags
REQ-0001 | Standardise customer case handling | Must | 75 | No AC; No test; AC required; Test required
REQ-0002 | Capture standard case intake data | Must | 70 | No AC; No test; AC required; Test required; Approval pending
REQ-0006 | Migrate active customer cases | Should | 95 | Approval pending; Open change
REQ-0007 | Automate triage routing | Should | 60 | No AC; No test; No trace link; AC required; Test required; Approval pending
REQ-0008 | Route cases by SLA priority | Should | 95 | Approval pending
REQ-0009 | Integrate account master data | Must | 95 | Approval pending; Open change
REQ-0010 | Provide operational case dashboard | Should | 95 | Approval pending
REQ-0012 | Notify advisor of SLA risk | Should | 95 | Approval pending
REQ-0013 | Enforce role-based case access | Must | 95 | Approval pending
REQ-0014 | Train service advisors before go-live | Must | 95 | Approval pending
REQ-0015 | Suggest knowledge articles | Could | 60 | No AC; No test; No trace link; AC required; Test required; Approval pending
REQ-0016 | Select suggested knowledge article | Could | 60 | No AC; No test; No trace link; AC required; Test required; Approval pending
REQ-0017 | Apply data quality rules before migration | Must | 95 | Approval pending
REQ-0019 | Maintain acceptable form response time | Should | 95 | Approval pending
REQ-0020 | Approve service manager dashboard | Should | 85 | No trace link; Approval pending
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0

## Export_Report
Export Report
Print-ready governance summary for workshops, steering groups and baseline review packs.
Report Field | Value | Notes
Project | Example D365 Service Transformation | Shown in steering/group reporting
Delivery Mode | Hybrid | Agile / Waterfall / Hybrid
Workbook Version | v2.0 | Commercial product version
Workbook Owner | Lead Business Analyst | Accountable owner
Product Owner | Product Owner | Decision owner
Total Requirements | 20 | Master requirements count
Average Quality Score | 8825% | Quality score across populated requirements
Ready for Delivery | 500% | Count of requirements ready for delivery
Traceability Coverage | 80% | Percentage traced
AC Coverage | 0.75 | Percentage with AC
Test Coverage | 0.75 | Percentage with linked tests
Open Changes | 2 | Must be resolved before baseline
Open RAID Items | 4 | Risk/issue/dependency count
Governance Recommendation | Resolve quality, traceability or governance exceptions before commitment | Automatically generated recommendation
Top exceptions for governance review
Requirement ID | Title | MoSCoW | Quality Score | Exception Flags
REQ-0001 | Standardise customer case handling | Must | 75 | No AC; No test; AC required; Test required
REQ-0002 | Capture standard case intake data | Must | 70 | No AC; No test; AC required; Test required; Approval pending
REQ-0006 | Migrate active customer cases | Should | 95 | Approval pending; Open change
REQ-0007 | Automate triage routing | Should | 60 | No AC; No test; No trace link; AC required; Test required; Approval pending
REQ-0008 | Route cases by SLA priority | Should | 95 | Approval pending
REQ-0009 | Integrate account master data | Must | 95 | Approval pending; Open change
REQ-0010 | Provide operational case dashboard | Should | 95 | Approval pending
REQ-0012 | Notify advisor of SLA risk | Should | 95 | Approval pending
REQ-0013 | Enforce role-based case access | Must | 95 | Approval pending
REQ-0014 | Train service advisors before go-live | Must | 95 | Approval pending
Solution Architect
Test Manager
Programme Manager

## Guidance
Method Guidance
Embedded usage guidance for Agile, Waterfall, Hybrid, D365 and Power Platform delivery contexts.
Area | Guidance | Why it matters | Workbook implementation
Single source of truth | Capture all requirement records in Requirements_Register rather than maintaining separate Agile and Waterfall registers. | Avoids duplication, inconsistent status reporting and broken traceability. | Use Delivery Mode, Requirement Level and Requirement Type to drive views.
Agile requirements | Use epics, features and user stories where requirements are progressively elaborated and delivered iteratively. | Supports backlog refinement, prioritisation and sprint/release planning. | Use Agile_Backlog and fields such as User Story, WSJF Score, Release / Sprint and Review Readiness.
Waterfall / predictive requirements | Use formal requirement records where approval, baseline control and contractual traceability are required. | Supports sign-off, change control and auditability. | Use Predictive_Requirements, Approval Status, Baseline Version, Baseline Date and Change_Control.
Hybrid delivery | Use Hybrid mode when iterative build coexists with formal governance, testing, data migration or release controls. | Most enterprise D365 and Power Platform programmes are hybrid in practice. | Use Hybrid_Control_View to manage delivery readiness and governance gates together.
Requirement quality | A requirement should be clear, necessary, feasible, testable, traceable and owned. | Poor quality requirements increase rework, scope ambiguity and acceptance risk. | Quality Score combines ownership, statement quality, source evidence, AC, test and traceability.
Acceptance criteria | Define observable conditions that demonstrate whether a requirement has been satisfied. | Acceptance criteria make requirements verifiable and reduce interpretation risk. | Use Acceptance_Criteria and link each row to Requirement ID and Test ID.
Traceability | Trace requirements from objective and source evidence through design, build, test and benefit/KPI. | Enables impact analysis, scope control and readiness assurance. | Use Traceability_Matrix and monitor Traceability Status on the register.
Change control | Treat post-baseline changes as governed decisions with explicit impact, owner and status. | Protects baseline integrity and avoids unmanaged scope growth. | Use Change_Control and resolve Open/In Assessment changes before delivery commitment.
RAID linkage | Link risks, assumptions, issues, dependencies and decisions to impacted requirements. | Makes delivery blockers visible at the requirement level. | Use RAID_Decisions and review red/amber items on Dashboard and Quality_Gates.
NFR management | Manage non-functional requirements explicitly, not as hidden design assumptions. | Security, performance, data retention, auditability and supportability are common delivery failure points. | Use NFR_Catalogue and link NFR IDs to requirements and tests.
D365 considerations | Capture requirements for configuration, security roles, business process flows, data model, integrations, reporting and ALM. | D365 delivery requires controlled design choices across platform, process and governance. | Use Domain, Requirement Type, NFR_Catalogue and Traceability_Matrix to distinguish configuration from integration or custom build.
Power Platform considerations | Capture Power Automate, Power Apps, Dataverse, environment, connector and governance requirements explicitly. | Power Platform solutions need guardrails for security, maintainability and ALM. | Use Domain = Power Platform and record automation, security and ALM requirements.
Prioritisation | Use MoSCoW for stakeholder clarity; use WSJF/RICE when value, urgency, risk and effort trade-offs need quantification. | Transparent prioritisation reduces subjective backlog debates. | Scores are calculated from business value, urgency, risk reduction, opportunity, size and confidence.
Definition of Ready | A requirement/story should not enter delivery until it has sufficient detail, owner, priority, AC and traceability. | Reduces churn during build and sprint execution. | Review Readiness indicates whether the record is ready for structured review.
Definition of Done | A requirement should not be considered done until the accepted solution is tested, traceable and sign-off evidence is present. | Prevents premature closure and weak UAT assurance. | Delivery Readiness and Test_Coverage support closure decisions.
Governance reporting | Use the dashboard and export report before baseline, sprint planning, release readiness and steering forums. | Creates a consistent evidence-backed governance pack. | Use Dashboard, Quality_Gates and Export_Report.
Commercial usage | Before distributing the tool, replace or clear sample rows and update Config with client/project-specific values. | Keeps the workbook reusable, professional and implementation-ready. | Sample rows are marked with Sample Flag = Yes in relevant registers.

## Glossary
Glossary
Controlled terminology for requirements management, delivery governance and traceability.
Term | Definition | Used in
Requirement | A usable representation of a need, problem, opportunity, capability or constraint that a solution must address. | Requirements_Register
Business Requirement | A high-level business need or outcome that explains why change is required. | Requirements_Register
Stakeholder Requirement | A requirement describing the needs of a stakeholder or stakeholder group. | Requirements_Register
Solution Requirement | A requirement describing a capability or quality of the solution. | Requirements_Register
Functional Requirement | A requirement describing behaviour, process, interaction or functionality. | Requirements_Register
Non-functional Requirement | A requirement describing quality attributes such as performance, security, availability or auditability. | NFR_Catalogue
Transition Requirement | A temporary capability needed to move from the current to future state. | Requirements_Register
Epic | A large body of work that can be decomposed into features and user stories. | Agile_Backlog
Feature | A coherent capability or product function that contributes to an epic. | Agile_Backlog
User Story | A concise Agile requirement often written as 'As a... I want... so that...'. | Agile_Backlog
Acceptance Criteria | Conditions that must be true for a requirement or story to be accepted. | Acceptance_Criteria
Traceability | The linkage between requirements, objectives, source evidence, design, tests and benefits. | Traceability_Matrix
Baseline | An approved requirements position used for control, change management and delivery commitment. | Change_Control
WSJF | Weighted Shortest Job First, a prioritisation method using value, urgency, risk reduction and job size. | Requirements_Register
RICE | Reach, Impact, Confidence and Effort; a prioritisation method for product decisions. | Requirements_Register
MoSCoW | Prioritisation classification: Must, Should, Could and Won't. | Requirements_Register
RAID | Risks, assumptions, issues and dependencies; this workbook also tracks decisions. | RAID_Decisions
Governance Gate | A control point determining whether a requirement is ready for review, delivery or baseline. | Quality_Gates
Delivery Readiness | An indicator that a requirement has sufficient quality, acceptance criteria, testing and approval to proceed. | Requirements_Register
Hybrid Delivery | A delivery model combining iterative Agile work with formal governance, traceability, testing and release controls. | Hybrid_Control_View

## Config
Configuration
Workbook settings, scoring weights, controlled lists and validation values.
Setting | Description | Value | Metric | Weight | Notes | Delivery Mode | Requirement Level | Requirement Type | Domain | MoSCoW | Lifecycle Status | Approval Status | Change Status | Dependency Status | AC Type | AC Status | Test Type | Test Status | Trace Status | RAID Type | RAG | Source Type | Reliability | Impact Level | NFR Category | Yes / No | Engagement Level | Influence | Interest | Attitude | Owner Roles
Workbook Version | Product version | v2.0 | Business Value | 30% | Expected organisational value | Agile | Outcome | Business | Customer Service | Must | Draft | Not Started | None | None | Checklist | Draft | SIT | Not Started | Complete | Risk | Green | Discovery Workshop | High | Low | Performance | Yes | Inform | Low | Low | Supportive | Lead Business Analyst
Product Tier | Commercial product tier | Professional | Urgency | 20% | Time criticality or external pressure | Waterfall | Epic | Stakeholder | Sales | Should | Analysing | In Review | Open | Internal dependency | Given / When / Then | Reviewed | UAT | Designed | Partial | Assumption | Amber | Stakeholder Interview | Medium | Medium | Availability | No | Consult | Medium | Medium | Neutral | Business Analyst
Client / Project Name | Name shown on dashboards and reports | Example D365 Service Transformation | Risk Reduction | 20% | Risk, control or compliance reduction | Hybrid | Feature | Functional | Finance | Could | In Review | Approved | In Assessment | External dependency | Business Rule | Approved | Regression | Ready | Gap | Issue | Red | Document Review | Low | High | Security |  | Involve | High | High | Resistant | Product Owner
Delivery Mode | Selected workbook mode | Hybrid | Opportunity Enablement | 10% | Enables further value or capability |  | User Story | Non-functional | Operations | Won't | Approved | Baselined | Approved | Blocked | NFR Metric | Rejected | Performance | In Progress | Not Required | Dependency |  | Process Walkthrough |  | Critical | Auditability |  | Collaborate |  |  | Unknown | Service Owner
Primary Prioritisation Method | Default prioritisation method | MoSCoW | Size Efficiency | 10% | Rewards smaller job size |  | Requirement | Transition | Data Migration |  | Baselined | Rejected | Rejected | Dependency resolved | Compliance Control | Superseded | Security | Passed |  | Decision |  | System Analysis |  |  | Usability |  | Empower |  |  |  | Solution Architect
Secondary Prioritisation Method | Optional scoring method | WSJF / RICE | Complexity Efficiency | 5% | Rewards lower complexity |  | Business Rule | Data | Integration |  | In Delivery | Not Required | Implemented |  | UAT Scenario |  | Data Migration | Failed |  |  |  | Data Profiling |  |  | Accessibility | [5 empty] | Data Lead
Requirement ID Prefix | ID prefix for new requirement records | REQ | Requirement Risk Efficiency | 5% | Rewards lower delivery/requirement risk |  | NFR | Integration | Security |  | Built |  | Closed |  |  |  | Integration | Blocked |  |  |  | Regulatory Source |  |  | Scalability | [5 empty] | Integration Lead
Baseline Required | Whether formal approval/baseline controls apply | Yes |  |  |  |  | Constraint | Reporting | Reporting |  | In Test | [5 empty] | Accessibility | Deferred |  |  |  | Decision Log |  |  | Maintainability | [5 empty] | Security Lead
Test Traceability Required | Whether test coverage is mandatory for delivery readiness | Yes | [5 empty] | Compliance | Compliance |  | Done | [5 empty] | Operational Readiness | Signed Off |  |  |  | Design Workshop |  |  | Interoperability | [5 empty] | Compliance Lead
Acceptance Criteria Required | Whether AC coverage is mandatory for delivery readiness | Yes | [5 empty] | Security | Change Management |  | Rejected | [10 empty] | UAT Feedback |  |  | Data Retention | [5 empty] | Test Manager
Macro Automation Enabled | Workbook generated without macros; VBA/Office Scripts optional | No | [5 empty] | Process | Power Platform |  | Superseded | [13 empty] | Compliance | [5 empty] | Change Manager
Workbook Owner | Accountable workbook owner | Lead Business Analyst | [5 empty] | Automation | D365 |  | Deferred | [13 empty] | Operational Support | [5 empty] | Operations Lead
Product Owner | Backlog/product decision owner | Product Owner | [5 empty] | Analytics | ALM / Governance | [21 empty] | Programme Manager
Programme / Delivery Lead | Delivery lead shown in export report | Programme Manager | [28 empty] | Reporting Lead
Last Refreshed | Manual timestamp for report packs | 46175 | [28 empty] | Power Platform Lead
Excel Compatibility | Recommended Excel version | Microsoft 365 / Excel 2021+ | [28 empty] | D365 Consultant
Sample Data Status | Indicates whether sample rows are present | Sample data included
Review Readiness Threshold | Minimum quality score for review readiness | 70
Delivery Readiness Threshold | Minimum quality score for delivery readiness | 85
Baseline Gate Threshold | Minimum quality score for formal baseline | 90
REQ-0016
REQ-0017
REQ-0019

## Release_Notes
Release Notes
Product notes, commercial packaging features and rebuild summary.
Area | Commercial rebuild feature | Benefit
Architecture | Single-workbook model with one master requirements register and three delivery lenses. | Reduces duplication and supports Agile, Waterfall and Hybrid delivery from one source of truth.
Data model | 52-field requirements register with scoring, governance, traceability, readiness and exception formulas. | Makes the workbook a proper product rather than a static tracker.
Agile capability | Dedicated Agile_Backlog view for epics, features, user stories, WSJF, sprint/release planning and readiness. | Supports iterative delivery and backlog refinement.
Waterfall capability | Predictive_Requirements view for approval, baseline, formal requirement classes and traceability. | Supports sign-off and controlled delivery environments.
Hybrid capability | Hybrid_Control_View combining delivery readiness and governance status. | Reflects real enterprise delivery patterns, especially D365 and Power Platform programmes.
Traceability | Linked objectives, sources, AC, tests, design/build references and benefits/KPIs. | Supports impact analysis, UAT assurance and governance reporting.
Quality management | Quality score, review readiness, delivery readiness, governance gate and exception flags. | Highlights gaps before review, build, test or baseline.
Dashboards | Executive dashboard and quality gate scorecard with charts, KPIs and top exceptions. | Creates client-ready reporting for governance forums.
Commercial packaging | Embedded guidance, glossary, export report, controlled lists and sample data. | Improves usability and makes the workbook viable as a StratForge product.
Branding | Structured, enterprise-grade visual style aligned to StratForge product positioning. | Creates a more professional asset for sale or client delivery.
Product note: this workbook is generated without macros to maximise compatibility. Optional VBA/Office Scripts can later add buttons for creating IDs, adding new records, refreshing dashboards, clearing sample data and exporting PDFs.