## Start Here
Northbridge Citizens Services ¦ UAT Delivery Command Workbook
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Welcome. This workbook is a macro-free, white-label UAT command pack with embedded dummy data. Use it to plan, control, evidence, report and close UAT. Start on the Branding & Setup tab, then review User Guidance, Dashboards, and the core input sheets. When ready for live use, duplicate the file and clear the demo data on the input tabs.
Quick Start |  |  |  |  | Workbook Areas |  |  | Data Conventions
1. Update the organisation, programme, release, and report date on Branding & Setup. |  |  |  |  | Dashboards | Live dashboard views for sponsor, operational, quality and readiness reviews. |  | Blue font = user-editable input
2. Review the readiness, status and business-area lists to align to your delivery context. |  |  |  |  | Inputs | Plan, readiness, scenario, execution, defect, issue, risk and sign-off capture. |  | Grey cells = formulas / helper logic
3. Read the guidance tab before editing live data so your team uses the same control model. |  |  |  |  | Guidance | Embedded delivery guidance, conventions and usage notes. |  | Green highlights = positive / complete
4. Use the dashboards to show stakeholders how the dummy data flows through the tool. |  |  |  |  | White Label | Dynamic organisation/programme references and neutral styling. |  | Amber highlights = caution / in progress
5. When ready, duplicate the workbook and clear input tabs for live use. | [7 empty] | Red highlights = blocker / overdue / critical
Quick Navigation
Set Up |  | Dashboards |  | Core Inputs |  | Control Logs | Close Out
Branding & Setup |  | Executive Dashboard |  | UAT Plan |  | Defect Log | Status Report Input
User Guidance |  | Operational Dashboard |  | Readiness Checklist |  | Issue Log | Exit & Sign-Off
UAT Overview |  | Defect & Quality |  | Scenario Register |  | Risk & Assumptions | Lessons Learned
|  | Readiness Dashboard |  | Execution Tracker |  | Decision Log | About & Attribution
How to Demonstrate the Workbook
1. Open Executive Dashboard to show overall readiness, execution, defect and sign-off confidence.
2. Drill into Operational Dashboard to show daily volumes, tester activity and backlog pressure.
3. Open Readiness Checklist and Execution Tracker to show how underlying data feeds the dashboards.
4. Open Defect Log and Risk & Assumptions to show governance control and evidence trail.
5. Finish on Exit & Sign-Off to show how operational data rolls into go / no-go decision support.

## Branding & Setup
White-Label UAT Delivery Command Workbook
Update the highlighted inputs on this tab to personalise the workbook for your organisation. All major title bands and reporting references pull from these cells.
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Purpose: this tab controls workbook identity, reporting dates, thresholds, and dropdown values. Change the organisation, programme, release and report date first. Then review threshold settings and list values before replacing dummy data with live content. This workbook contains no VBA or macros.
Core Identity Inputs |  |  |  |  | White-Label Guidance
Organisation Name | Northbridge Citizens Services |  |  |  | 1. Update cells B9:B17 with your organisation, programme, dates and contacts.
Programme / Project | Service Transformation Programme |  |  |  | 2. Replace the logo placeholder below with your internal logo if required.
Release / Wave | Release 2 - Case Management & Appointments |  |  |  | 3. Recolour the dark title bands and dashboard cards once using your house style, then use Format Painter if you want a fully branded version.
Report Date | 2026-03-12 |  |  |  | 4. Review thresholds and dropdown values on this tab before clearing dummy data.
UAT Start Date | 2026-02-24 |  |  |  | 5. Duplicate the workbook before going live so the demo version remains intact.
Target Sign-Off Date | 2026-03-20
Primary Contact | uat.office@example.org |  |  |  | [Insert organisation logo here]
Business Sponsor | Chloe Morgan
UAT Lead | Aisha Khan
Thresholds and Tolerances |  |  |  |  | Deployment Notes
Readiness Amber Threshold | 80% |  |  |  | Blue-font cells are intended for user input.
Readiness Green Threshold | 95% |  |  |  | Grey cells and most dashboard values are formula-driven.
Execution Amber Threshold | 75% |  |  |  | Use the hidden 'Lists' sheet only if you need to extend dropdown lists.
Execution Green Threshold | 90% |  |  |  | The hidden 'Dashboard Data' sheet stores chart calculations.
Exit Amber Threshold | 80% |  |  |  | No macros, VBA, or external links are included in this workbook.
Exit Green Threshold | 100%
Open Critical Defect Tolerance | 0
Open High Defect Tolerance | 5
Suggested First-Day Actions
Update organisation, release and report date |  |  |  | Done
Confirm readiness categories and business areas |  |  |  | Done
Review threshold settings |  |  |  | Done
Hide About tab if not needed internally |  |  |  | Pending
Clear demo data for live deployment |  |  |  | Pending

## User Guidance
Northbridge Citizens Services ¦ User Guidance
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
This tab embeds best-practice guidance so the workbook can stand alone as a delivery aid. The intent is to help teams run UAT as a controlled business acceptance process rather than a loose testing exercise. Use the sections below during mobilisation, daily control, triage, sign-off preparation, and lessons learned.
UAT Purpose
UAT confirms that the solution supports real business outcomes, operational controls, and acceptable residual risk. It is not a substitute for SIT or technical testing. Business users should execute meaningful journeys, challenge edge cases, and provide evidence that the release is ready to operate.
What Good UAT Looks Like
Good UAT has agreed scope, traceability, named owners, realistic data, clear defect triage, visible dashboards, and explicit entry/exit criteria. Daily control should show what ran, what passed, what failed, what blocked execution, and what decisions are required.
Common Failure Modes
Typical failure patterns include weak readiness criteria, late script preparation, poor business attendance, unclear defect severity definitions, no contingency for data or environment failure, and sign-off discussions starting too late. This workbook is designed to surface those risks early.
Daily Operating Rhythm
Recommended cadence: daily stand-up (execution progress, blockers, action owners), daily defect triage (severity, priority, workaround, fix dates), weekly readiness/governance review, and formal sign-off checkpoint. Use the dashboards to support all of these forums.
Readiness Guidance
Do not treat readiness as a one-off gateway. Review it repeatedly by category, owner and blocker. Mandatory items should be evidenced, not assumed complete. If the workbook shows weak readiness in data, access or tester readiness, expect execution efficiency to degrade.
Defect Triage Guidance
Separate severity (business impact) from priority (delivery urgency). Triage should confirm reproducibility, owner, target fix date, workaround, and whether execution can continue. Avoid leaving defects open without an agreed business containment position.
Execution Guidance
Use the Execution Tracker as the daily operational control point. Record the scenario, tester, status, linked defect/issue, and retest need. If execution volume drops, inspect tester readiness, blocker issues, and environment/data dependencies before simply asking for more effort.
Sign-Off Guidance
Sign-off should be evidence-led. Review mandatory exit criteria, open critical/high defects, residual risks, late milestones, unresolved blockers, and any accepted workarounds. A recommendation can be amber if leadership consciously accepts residual risk.
White-Label / Internal Deployment Guidance
This workbook is intentionally neutral and macro-free. Update the Branding & Setup tab first. If your organisation requires specific colours or logos, apply them to the title bands and dashboard cards after confirming the structure works for your process.
Practical Tips by Role
UAT Lead | Own cadence, thresholds, and escalation. Keep the dashboards honest and do not hide blockers.
Business Analyst | Maintain traceability, clarify acceptance criteria, and support meaningful evidence capture.
Service / Operations Lead | Validate operational realism, business capacity, and workaround acceptability.
PMO / Governance | Track decision dates, overdue actions, and sign-off evidence completeness.

## UAT Overview
Northbridge Citizens Services ¦ UAT Overview
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
This is the operating summary page for the workbook. Use it to orient new users, review the current state, and jump into the detailed dashboards or logs. The sheet blends project context, live KPIs and a simple management summary without requiring users to understand every source tab.
Programme Snapshot |  |  |  |  | Overall Readiness |  | Execution Coverage |  | Exit Readiness
Organisation | Northbridge Citizens Services |  |  |  | 59.65% |  | 80% |  | 37.5%
Programme | Service Transformation Programme
Release | Release 2 - Case Management & Appointments |  |  |  | Pass Rate |  | Open Critical Defects |  | Open Issues
Report Date | 2026-03-12 |  |  |  | 60% |  | 5 |  | 6
UAT Lead | Aisha Khan
Target Sign-Off | 2026-03-20
Management Summary
Use the KPI cards above as the entry point: readiness shows how well the programme is set up, execution coverage shows how much of scope has actually been run, and exit readiness shows how close the programme is to a defensible sign-off recommendation. Use the dashboard tabs for deeper analysis and the control logs for evidence.
Milestone Health | [6 empty] | Latest Reporting Snapshot
Milestone | Planned | Actual | Status | Days Slip | Dependency | Comments | Period | Week 4: 11 Mar - 15 Mar 2026
UAT mobilisation complete | 2026-02-17 | 2026-02-17 | Complete | 0 | None |  | Achievements | Expanded coverage into exception and reporting scenarios.
Entry criteria drafted | 2026-02-19 | 2026-02-19 | Complete | 0 | None |  | Next Steps | Prepare sign-off evidence pack and residual risk summary.
Environment ready | 2026-02-22 | 2026-02-24 | Complete | 2 | None |  | Blockers | Reporting extracts still require validation.
Script pack approved | 2026-02-23 | 2026-02-23 | Complete | 0 | Environment |  | Top Risks | Data refresh timing remains a dependency.
Wave 1 start | 2026-02-24 | 2026-02-24 | Complete | 0 | Business availability |  | Decisions Required | Confirm whether to extend re-test window.
Wave 1 checkpoint | 2026-02-27 | 2026-02-27 | Complete | 0 | None |  | Confidence | Amber
Wave 1 exit | 2026-03-01 | 2026-03-01 | Complete | 0 | Business availability
Wave 2 start | 2026-03-02 |  | At Risk | 10 | Business availability | Dependency requires leadership attention.

## Executive Dashboard
Northbridge Citizens Services ¦ Executive Dashboard
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
This dashboard is designed for sponsors, programme leads and governance forums. It translates detailed UAT control data into a concise view of readiness, execution, defect position, sign-off confidence and current delivery pressure.
Overall Readiness |  |  | Execution Coverage |  | Pass Rate | Open Critical Defects | Exit Readiness
59.65% |  |  | 80% |  | 60% | 5 | 37.5%
Open High Defects |  |  | Open Issues |  | Open Risks | Ready Testers | Late Milestones
6 |  |  | 6 |  | 8 | 88.24% | 3
Executive Commentary
Interpretation guide: high readiness with low execution means the programme is prepared but still early in cycle. High execution with weak pass rate or rising critical defects means control needs to focus on quality and triage throughput. Exit readiness should not move to green while critical blockers, open critical defects or unresolved sign-off conditions remain.
Executive Use Notes
Suggested forum use: Executive dashboard for weekly governance, Operational dashboard for daily control, Defect & Quality for triage, Readiness dashboard for entry/exit reviews. Keep the report date current on Branding & Setup so ageing, overdue and slippage indicators remain accurate.

## Operational Dashboard
Northbridge Citizens Services ¦ Operational Dashboard
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
This dashboard is for the daily UAT control room. It focuses on execution throughput, backlog pressure, tester activity, blocked work and milestone pressure. Use it in stand-ups, triage meetings and end-of-day reviews.
Total Scenarios |  |  | Scenarios Executed |  | Execution Records | Retest Pending | Late Milestones
80 |  |  | 64 |  | 150 | 6 | 3
Passed |  |  | Failed |  | Blocked | Deferred | Overdue Issues
90 |  |  | 28 |  | 17 | 15 | 6
Operational Commentary
Use this page to understand whether the team is moving through scope at the planned pace. Watch retest pending, blocked executions and late milestones together: if all three rise, the defect/decision pipeline is not clearing quickly enough.
Daily Control Questions
Have we executed the critical-path scenarios planned for today? Which blockers prevented progress? Which defects need business or technical triage? Which testers are under-utilised because of readiness or access issues? Are late milestones compressing the remaining execution and retest window?

## Defect & Quality
Northbridge Citizens Services ¦ Defect & Quality Dashboard
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Use this dashboard for defect triage, quality reviews and escalation discussions. It highlights severity mix, open backlog, ageing pressure, root causes and whether the defect pipeline is clearing quickly enough to support sign-off.
Open Defects |  |  | Open Critical |  | Open High | Target Breaches | Pass Rate
20 |  |  | 5 |  | 6 | 15 | 60%
Retest Pending |  |  | Blocked Rate |  | Open Issues | Open Risks | Exit Readiness
6 |  |  | 11.33% |  | 6 | 8 | 37.5%
Quality Commentary
Use this page to check whether defect volume is stabilising and whether the backlog is moving toward an acceptable residual-risk position. Ageing and target-breach indicators matter as much as the raw defect count because they show whether the control process is actually working.
Triage Questions
Which defects genuinely block business acceptance? Which items have workarounds that are acceptable? Where are breaches caused by waiting for triage rather than waiting for fixes? Which root causes point to repeatable delivery problems that should feed lessons learned?

## Readiness Dashboard
Northbridge Citizens Services ¦ Readiness Dashboard
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
This dashboard should be used before execution starts and whenever progress drops unexpectedly. It shows whether planning, data, access, scripts, testers and governance are truly ready. Poor readiness usually appears here before it shows up as blocked execution.
Overall Readiness |  |  | Ready Testers |  | Overdue Readiness Items | Open Risks | Late Milestones
59.65% |  |  | 88.24% |  | 29 | 8 | 3
Open Issues |  |  | Execution Coverage |  | Exit Readiness | Open Critical | Open High
6 |  |  | 80% |  | 37.5% | 5 | 6
Readiness Commentary
When execution slows down, inspect readiness before asking the team to work harder. Weak training, incomplete access, fragile data and poor script ownership almost always surface as blocked or deferred execution later on. This page helps show the upstream cause.
Entry / Exit Review Prompts
What is incomplete, and does it matter? Which incomplete items are mandatory? Which blockers have named owners and realistic dates? Are business users, data and environment all ready for the next wave? Are any 'green' indicators masking evidence gaps or untested workarounds?

## UAT Plan
Northbridge Citizens Services ¦ UAT Plan
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Use this sheet to maintain the master UAT milestone plan. Track planned and actual dates, owners, dependencies, slippage, and whether each milestone is complete, in progress, at risk or not started. The days-slip and late-flag columns are formula-driven using the report date on the Branding & Setup tab.
Phase | Wave / Cycle | Milestone | Description | Planned Date | Actual Date | Owner | Status | Dependency | Comments | Days Slip | Late Flag
Mobilise | Wave 0 | UAT mobilisation complete | Agree governance, scope owners, and planning baseline | 2026-02-17 | 2026-02-17 | Nadia Shah | Complete | None |  | 0 | No
Prepare | Wave 0 | Entry criteria drafted | Baseline readiness criteria and evidence expectations | 2026-02-19 | 2026-02-19 | Chloe Morgan | Complete | None |  | 0 | No
Prepare | Wave 0 | Environment ready | Confirm environment, access, and data readiness | 2026-02-22 | 2026-02-24 | Nadia Shah | Complete | None |  | 2 | No
Prepare | Wave 0 | Script pack approved | Approve critical-path scenarios and evidence model | 2026-02-23 | 2026-02-23 | Nadia Shah | Complete | Environment |  | 0 | No
Execute | Wave 1 | Wave 1 start | Start core journey execution | 2026-02-24 | 2026-02-24 | Nadia Shah | Complete | Business availability |  | 0 | No
Execute | Wave 1 | Wave 1 checkpoint | Review pass/fail/block trends | 2026-02-27 | 2026-02-27 | Jessica Reed | Complete | None |  | 0 | No
Execute | Wave 1 | Wave 1 exit | Close or defer remaining Wave 1 items | 2026-03-01 | 2026-03-01 | Laura Green | Complete | Business availability |  | 0 | No
Execute | Wave 2 | Wave 2 start | Start exception and finance execution | 2026-03-02 |  | Jessica Reed | At Risk | Business availability | Dependency requires leadership attention. | 10 | Yes
Execute | Wave 2 | Wave 2 checkpoint | Review blocked items and retest pipeline | 2026-03-05 | 2026-03-06 | Aisha Khan | Complete | Data |  | 1 | No
Execute | Wave 2 | Wave 2 exit | Stabilise defect backlog for reporting wave | 2026-03-07 | 2026-03-08 | Karl Bennett | Complete | Data |  | 1 | No
Execute | Wave 3 | Wave 3 reporting start | Execute MI and reporting scenarios | 2026-03-08 | 2026-03-09 | Nadia Shah | Complete | Data |  | 1 | No
Execute | Wave 3 | Re-test window | Complete critical retest activity | 2026-03-10 |  | Ibrahim Ali | At Risk | Business availability | Dependency requires leadership attention. | 2 | Yes
Closure | Close Down | Exit criteria review | Validate sign-off evidence and residual risks | 2026-03-12 | 2026-03-13 | Chloe Morgan | In Progress | Business availability |  | 1 | Yes
Closure | Close Down | Business sign-off | Obtain approval from nominated approvers | 2026-03-14 |  | Laura Green | Not Started | None |  | -2 | No
Closure | Close Down | Lessons learned | Run retrospective and improvement capture | 2026-03-16 |  | Ben Carter | Not Started | Business availability |  | -4 | No

## Scope Register
Northbridge Citizens Services ¦ Scope Register
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Define what is and is not in scope for UAT. Keep requirement references, business area ownership, rationale and scope type visible so you can defend test coverage decisions. The Scenarios Linked column shows how many scenarios currently reference each requirement.
Scope ID | Business Process | Requirement ID | Process Area | Business Area | Scope Type | Description | Rationale | Owner | Scenarios Linked | Comments
SCO-001 | Case Intake - Core journey | REQ-001 | Case Intake | Contact Centre | In Scope | Case Intake capability supporting contact centre workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Aisha Khan | 3
SCO-002 | Case Update - Core journey | REQ-002 | Case Update | Case Management | In Scope | Case Update capability supporting case management workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Aisha Khan | 3
SCO-003 | Work Allocation - Exception journey | REQ-003 | Work Allocation | Field Operations | In Scope | Work Allocation capability supporting field operations workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Emily Foster | 3
SCO-004 | Debt Review - Core journey | REQ-004 | Debt Review | Finance & Billing | In Scope | Debt Review capability supporting finance & billing workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Chloe Morgan | 3
SCO-005 | Operational Reporting - Core journey | REQ-005 | Operational Reporting | Reporting & MI | In Scope | Operational Reporting capability supporting reporting & mi workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Chloe Morgan | 3 | High regulatory visibility.
SCO-006 | Identity & Eligibility - Exception journey | REQ-006 | Identity & Eligibility | Contact Centre | In Scope | Identity & Eligibility capability supporting contact centre workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Chloe Morgan | 3
SCO-007 | Complaint Handling - Core journey | REQ-007 | Complaint Handling | Case Management | In Scope | Complaint Handling capability supporting case management workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Aisha Khan | 3
SCO-008 | Mobile Updates - Core journey | REQ-008 | Mobile Updates | Field Operations | In Scope | Mobile Updates capability supporting field operations workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Nadia Shah | 3
SCO-009 | Charges & Payments - Exception journey | REQ-009 | Charges & Payments | Finance & Billing | In Scope | Charges & Payments capability supporting finance & billing workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Aisha Khan | 3
SCO-010 | Regulatory Reporting - Core journey | REQ-010 | Regulatory Reporting | Reporting & MI | In Scope | Regulatory Reporting capability supporting reporting & mi workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Nadia Shah | 3 | High regulatory visibility.
SCO-011 | Call Handling - Core journey | REQ-011 | Call Handling | Contact Centre | In Scope | Call Handling capability supporting contact centre workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Farah Malik | 3
SCO-012 | Escalations - Exception journey | REQ-012 | Escalations | Case Management | In Scope | Escalations capability supporting case management workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Aisha Khan | 3
SCO-013 | Appointment Booking - Core journey | REQ-013 | Appointment Booking | Field Operations | In Scope | Appointment Booking capability supporting field operations workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Aisha Khan | 3
SCO-014 | Adjustments - Core journey | REQ-014 | Adjustments | Finance & Billing | In Scope | Adjustments capability supporting finance & billing workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Aisha Khan | 3
SCO-015 | Dashboard Refresh - Exception journey | REQ-015 | Dashboard Refresh | Reporting & MI | In Scope | Dashboard Refresh capability supporting reporting & mi workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Chloe Morgan | 3 | High regulatory visibility.
SCO-016 | Case Routing - Core journey | REQ-016 | Case Routing | Contact Centre | In Scope | Case Routing capability supporting contact centre workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Chloe Morgan | 3
SCO-017 | Case Creation - Core journey | REQ-017 | Case Creation | Case Management | In Scope | Case Creation capability supporting case management workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Nadia Shah | 3
SCO-018 | Visit Completion - Exception journey | REQ-018 | Visit Completion | Field Operations | In Scope | Visit Completion capability supporting field operations workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Nadia Shah | 3
SCO-019 | Refunds - Core journey | REQ-019 | Refunds | Finance & Billing | In Scope | Refunds capability supporting finance & billing workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Aisha Khan | 3
SCO-020 | Data Reconciliation - Core journey | REQ-020 | Data Reconciliation | Reporting & MI | In Scope | Data Reconciliation capability supporting reporting & mi workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Nadia Shah | 3
SCO-021 | Case Intake - Exception journey | REQ-021 | Case Intake | Contact Centre | In Scope | Case Intake capability supporting contact centre workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Chloe Morgan | 2
SCO-022 | Case Update - Core journey | REQ-022 | Case Update | Case Management | In Scope | Case Update capability supporting case management workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Nadia Shah | 2
SCO-023 | Work Allocation - Core journey | REQ-023 | Work Allocation | Field Operations | In Scope | Work Allocation capability supporting field operations workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Farah Malik | 2
SCO-024 | Debt Review - Exception journey | REQ-024 | Debt Review | Finance & Billing | In Scope | Debt Review capability supporting finance & billing workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Chloe Morgan | 2
SCO-025 | Operational Reporting - Core journey | REQ-025 | Operational Reporting | Reporting & MI | Partial | Operational Reporting capability supporting reporting & mi workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Farah Malik | 2
SCO-026 | Identity & Eligibility - Core journey | REQ-026 | Identity & Eligibility | Contact Centre | Partial | Identity & Eligibility capability supporting contact centre workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Nadia Shah | 2
SCO-027 | Complaint Handling - Exception journey | REQ-027 | Complaint Handling | Case Management | Partial | Complaint Handling capability supporting case management workflows and audit-ready evidence capture. | Included in release scope to support the operating model and target-state process controls. | Emily Foster | 2
SCO-028 | Mobile Updates - Core journey | REQ-028 | Mobile Updates | Field Operations | Out of Scope | Mobile Updates capability supporting field operations workflows and audit-ready evidence capture. | Deferred to a later release because upstream dependencies are not available. | Aisha Khan | 2
SCO-029 | Charges & Payments - Core journey | REQ-029 | Charges & Payments | Finance & Billing | Out of Scope | Charges & Payments capability supporting finance & billing workflows and audit-ready evidence capture. | Deferred to a later release because upstream dependencies are not available. | Chloe Morgan | 2
SCO-030 | Regulatory Reporting - Exception journey | REQ-030 | Regulatory Reporting | Reporting & MI | Out of Scope | Regulatory Reporting capability supporting reporting & mi workflows and audit-ready evidence capture. | Deferred to a later release because upstream dependencies are not available. | Farah Malik | 2

## Tester Register
Northbridge Citizens Services ¦ Tester Register
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Maintain the named tester population, role coverage, training, access and assignment load here. Scripts Executed, readiness score and ready-for-UAT indicator update automatically from this data and the execution tracker. Use this sheet to identify where business participation or access gaps are constraining progress.
Person ID | Name | Role | Business Area | Tester Type | Email | Wave Participation | Training Completed | Access Confirmed | Scripts Assigned | Scripts Executed | Active | Readiness Score | Ready for UAT | Comments
P-001 | Aisha Khan | UAT Lead | Case Management | Operational Lead | aishakhan@example.org | Wave 1 - Core Journeys | No | Yes | 8 | 5 | Yes | 66 | No
P-002 | Ben Carter | Business Analyst | Contact Centre | Operational Lead | bencarter@example.org | Wave 1 - Core Journeys | Yes | Yes | 10 | 5 | Yes | 88 | Yes
P-003 | Chloe Morgan | Service Manager | Case Management | Product Owner | chloemorgan@example.org | Wave 1 - Core Journeys | No | Yes | 6 | 14 | Yes | 75 | Yes
P-004 | Daniel Hughes | SME | Field Operations | SME | danielhughes@example.org | Wave 2 - Exceptions | Yes | Yes | 8 | 6 | Yes | 94 | Yes
P-005 | Emily Foster | Product Owner | Finance & Billing | Product Owner | emilyfoster@example.org | Wave 2 - Exceptions | Yes | Yes | 7 | 0 | Yes | 75 | Yes
P-006 | Farah Malik | Operations Lead | Contact Centre | SME | farahmalik@example.org | Wave 1 - Core Journeys | No | Yes | 8 | 7 | Yes | 72 | No
P-007 | Gareth Evans | Business Analyst | Reporting & MI | Operational Lead | garethevans@example.org | Wave 3 - Reporting & Close Down | Yes | Yes | 5 | 13 | Yes | 100 | Yes
P-008 | Hannah Price | SME | Finance & Billing | SME | hannahprice@example.org | Wave 2 - Exceptions | No | Yes | 10 | 15 | Yes | 75 | Yes
P-009 | Ibrahim Ali | Training Lead | Case Management | Business Tester | ibrahimali@example.org | Wave 1 - Core Journeys | Yes | Yes | 2 | 0 | No | 50 | No | Reserve cover tester.
P-010 | Jessica Reed | PMO Analyst | Reporting & MI | Business Tester | jessicareed@example.org | Wave 3 - Reporting & Close Down | Yes | Yes | 6 | 0 | Yes | 75 | Yes
P-011 | Karl Bennett | Test Coordinator | Field Operations | Operational Lead | karlbennett@example.org | Wave 2 - Exceptions | Yes | Yes | 5 | 23 | Yes | 100 | Yes
P-012 | Laura Green | Business Analyst | Field Operations | Product Owner | lauragreen@example.org | Wave 2 - Exceptions | Yes | Yes | 4 | 11 | Yes | 100 | Yes
P-013 | Marcus Hall | SME | Contact Centre | SME | marcushall@example.org | Wave 1 - Core Journeys | Yes | Yes | 7 | 12 | Yes | 100 | Yes
P-014 | Nadia Shah | Service Manager | Finance & Billing | Product Owner | nadiashah@example.org | Wave 2 - Exceptions | Yes | Yes | 6 | 0 | Yes | 75 | Yes
P-015 | Owen Turner | Operational Lead | Case Management | Operational Lead | owenturner@example.org | Wave 1 - Core Journeys | Yes | Yes | 8 | 5 | Yes | 91 | Yes
P-016 | Priya Singh | Business Tester | Reporting & MI | Business Tester | priyasingh@example.org | Wave 3 - Reporting & Close Down | Yes | No | 5 | 20 | Yes | 75 | Yes
P-017 | Quentin Ross | Business Tester | Contact Centre | Business Tester | quentinross@example.org | Wave 1 - Core Journeys | Yes | Yes | 9 | 10 | Yes | 100 | Yes
P-018 | Ruth Adams | Business Tester | Field Operations | Business Tester | ruthadams@example.org | Wave 2 - Exceptions | Yes | Yes | 7 | 4 | Yes | 89 | Yes

## Env Access & Data
Northbridge Citizens Services ¦ Env Access & Data
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Track readiness dependencies across environment, access, data, integration and tooling. This sheet is especially useful during mobilisation and for investigating blocked execution. Use the blocker flag and due-date logic to make hidden dependencies visible before they slow down daily progress.
Item ID | Category | Item Description | Business Area | Owner | Planned Ready Date | Actual Ready Date | Status | Blocker | Impact | Mitigation | Comments | Overdue
ENV-001 | Environment | Application code deployed | Finance & Billing | Jessica Reed | 2026-02-24 | 2026-02-25 | Complete | No | Low | Re-sequence affected scripts |  | No
ENV-002 | Environment | Batch scheduler available | Field Operations | Chloe Morgan | 2026-02-27 |  | Not Started | No | Medium | Re-sequence affected scripts |  | Yes
ENV-003 | Environment | Background services running | Field Operations | Ben Carter | 2026-03-02 |  | Blocked | Yes | Low | Re-sequence affected scripts |  | Yes
ENV-004 | Environment | Search index refreshed | Reporting & MI | Gareth Evans | 2026-02-28 | 2026-02-28 | Complete | No | Medium | Track via daily control |  | No
ENV-005 | Environment | Interface end-points available | Field Operations | Karl Bennett | 2026-03-01 | 2026-03-02 | Complete | No | Low | Re-sequence affected scripts |  | No
ENV-006 | Access | Tester security roles provisioned | Finance & Billing | Aisha Khan | 2026-02-27 | 2026-02-28 | Complete | No | Low | Use interim workaround |  | No
ENV-007 | Access | Shared mailbox access granted | Field Operations | Aisha Khan | 2026-02-27 |  | In Progress | No | High | Re-sequence affected scripts |  | Yes
ENV-008 | Access | Admin support access confirmed | Case Management | Aisha Khan | 2026-03-02 | 2026-03-04 | Complete | No | High | Re-sequence affected scripts |  | No
ENV-009 | Access | Report folder permissions granted | Field Operations | Ibrahim Ali | 2026-02-24 | 2026-02-24 | Complete | No | Medium | Track via daily control |  | No
ENV-010 | Access | Mobile device access enabled | Finance & Billing | Ibrahim Ali | 2026-03-01 |  | In Progress | No | Medium | Re-sequence affected scripts |  | Yes
ENV-011 | Data | Golden path dataset loaded | Case Management | Laura Green | 2026-02-28 |  | In Progress | No | Medium | Re-sequence affected scripts |  | Yes
ENV-012 | Data | Edge-case data seeded | Contact Centre | Aisha Khan | 2026-02-26 |  | Blocked | Yes | Low | Escalate to supplier |  | Yes
ENV-013 | Data | Historical cases available | Contact Centre | Gareth Evans | 2026-02-27 | 2026-03-01 | Complete | No | Medium | Re-sequence affected scripts |  | No
ENV-014 | Data | Outstanding balance dataset loaded | Finance & Billing | Emily Foster | 2026-02-28 | 2026-03-01 | Complete | No | High | Escalate to supplier |  | No
ENV-015 | Data | Reference tables reconciled | Case Management | Karl Bennett | 2026-02-27 |  | Not Started | No | High | Use interim workaround |  | Yes
ENV-016 | Integration | Notification service connected | Contact Centre | Laura Green | 2026-03-01 |  | In Progress | No | Low | Use interim workaround |  | Yes
ENV-017 | Integration | Payment gateway stub active | Case Management | Chloe Morgan | 2026-03-02 |  | Not Started | No | Medium | Escalate to supplier |  | Yes
ENV-018 | Integration | Document service available | Case Management | Karl Bennett | 2026-02-25 | 2026-02-25 | Complete | No | High | Use interim workaround |  | No
ENV-019 | Integration | Telephony event feed available | Finance & Billing | Laura Green | 2026-02-26 |  | In Progress | No | High | Track via daily control |  | Yes
ENV-020 | Integration | Data warehouse handoff running | Finance & Billing | Laura Green | 2026-02-27 | 2026-03-01 | Complete | No | Medium | Re-sequence affected scripts |  | No
ENV-021 | Tooling | Defect log access enabled | Case Management | Ibrahim Ali | 2026-02-24 |  | Not Started | No | Low | Track via daily control |  | Yes
ENV-022 | Tooling | Execution tracker issued | Field Operations | Chloe Morgan | 2026-03-01 | 2026-03-03 | Complete | No | Low | Escalate to supplier |  | No
ENV-023 | Tooling | Status dashboard published | Finance & Billing | Laura Green | 2026-02-25 |  | In Progress | No | High | Track via daily control |  | Yes
ENV-024 | Tooling | Meeting rooms scheduled | Case Management | Ibrahim Ali | 2026-02-26 | 2026-02-26 | Complete | No | Low | Escalate to supplier |  | No
ENV-025 | Tooling | Evidence repository created | Contact Centre | Gareth Evans | 2026-02-28 | 2026-03-01 | Complete | No | High | Use interim workaround |  | No

## Readiness Checklist
Northbridge Citizens Services ¦ Readiness Checklist
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
This is the primary readiness control sheet. Record status, evidence and blocker position against each criterion. Mandatory items roll directly into readiness KPIs and dashboard reporting. If the sheet shows persistent amber/red conditions, expect the execution and sign-off indicators to weaken.
Checklist ID | Category | Criterion | Guidance | Mandatory | Owner | Due Date | Status | Evidence / Ref | Comments | Blocker | Complete Flag | Overdue
CHK-001 | Governance & Planning | UAT scope baseline agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Emily Foster | 2026-02-28 | Complete | Access request tracker |  | No | 1 | No
CHK-002 | Governance & Planning | UAT governance cadence confirmed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Nadia Shah | 2026-02-28 | Complete | Training attendance log |  | No | 1 | No
CHK-003 | Governance & Planning | Daily control, triage and escalation forums scheduled | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Jessica Reed | 2026-02-27 | Complete | Access request tracker |  | No | 1 | No
CHK-004 | Governance & Planning | Roles and responsibilities agreed with business owners | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Chloe Morgan | 2026-02-27 | Complete | Script pack baseline |  | No | 1 | No
CHK-005 | Governance & Planning | Milestone plan baselined and approved | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Jessica Reed | 2026-03-03 | Complete | Triage Terms of Reference |  | No | 1 | No
CHK-006 | Governance & Planning | Entry and exit criteria socialised | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Laura Green | 2026-02-27 | Complete | Access request tracker |  | No | 1 | No
CHK-007 | Governance & Planning | Defect severity / priority definitions approved | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | No | Jessica Reed | 2026-02-25 | In Progress |  |  | No | 0 | Yes
CHK-008 | Scope & Requirements | In-scope requirements baselined | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ibrahim Ali | 2026-02-25 | Complete | Access request tracker |  | No | 1 | No
CHK-009 | Scope & Requirements | Requirement traceability available for all critical journeys | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Gareth Evans | 2026-03-02 | Complete | Plan v1.2 |  | No | 1 | No
CHK-010 | Scope & Requirements | Process exceptions identified and reviewed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | No | Nadia Shah | 2026-02-26 | Complete | Training attendance log |  | No | 1 | No
CHK-011 | Scope & Requirements | Out-of-scope items clearly documented | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | No | Jessica Reed | 2026-02-25 | In Progress | Plan v1.2 |  | No | 0 | Yes
CHK-012 | Scope & Requirements | Business rules validated with SMEs | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ben Carter | 2026-03-04 | Complete | Training attendance log |  | No | 1 | No
CHK-013 | Scope & Requirements | Reporting outputs mapped to acceptance criteria | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ibrahim Ali | 2026-02-27 | Not Started | Triage Terms of Reference | Monitor closely at readiness review. | Yes | 0 | Yes
CHK-014 | Scope & Requirements | Change control for late scope items agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ibrahim Ali | 2026-02-27 | In Progress | Script pack baseline |  | No | 0 | Yes
CHK-015 | Scripts & Scenarios | Critical-path scripts drafted | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | No | Emily Foster | 2026-02-26 | In Progress | Plan v1.2 |  | No | 0 | Yes
CHK-016 | Scripts & Scenarios | Scenario peer review completed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ben Carter | 2026-02-26 | Complete | Triage Terms of Reference |  | No | 1 | No
CHK-017 | Scripts & Scenarios | Script pack coverage meets target threshold | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Nadia Shah | 2026-03-03 | Blocked | Access request tracker | Monitor closely at readiness review. | Yes | 0 | Yes
CHK-018 | Scripts & Scenarios | Negative and exception scenarios included | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | No | Ibrahim Ali | 2026-03-01 | Complete | Triage Terms of Reference |  | No | 1 | No
CHK-019 | Scripts & Scenarios | Test evidence expectations defined | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Gareth Evans | 2026-02-28 | Complete | Access request tracker |  | No | 1 | No
CHK-020 | Scripts & Scenarios | Retest pack identified for known defect areas | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Karl Bennett | 2026-02-28 | Complete | Training attendance log |  | No | 1 | No
CHK-021 | Scripts & Scenarios | Scenario ownership assigned | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ben Carter | 2026-02-28 | Complete |  |  | No | 1 | No
CHK-022 | Tester Readiness | Business testers nominated and confirmed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | No | Jessica Reed | 2026-03-04 | Not Started | Training attendance log |  | No | 0 | Yes
CHK-023 | Tester Readiness | Backup testers identified | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | No | Karl Bennett | 2026-02-24 | Complete | Access request tracker |  | No | 1 | No
CHK-024 | Tester Readiness | Role-based access approved | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Laura Green | 2026-03-03 | In Progress | Triage Terms of Reference |  | No | 0 | Yes
CHK-025 | Tester Readiness | Business availability confirmed for execution windows | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ben Carter | 2026-03-01 | Blocked | Access request tracker | Monitor closely at readiness review. | Yes | 0 | Yes
CHK-026 | Tester Readiness | Support contact list issued | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Karl Bennett | 2026-03-03 | In Progress | Access request tracker |  | No | 0 | Yes
CHK-027 | Tester Readiness | Execution guide shared with testers | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Gareth Evans | 2026-03-01 | Complete | Training attendance log |  | No | 1 | No
CHK-028 | Tester Readiness | Escalation path explained to testers | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ibrahim Ali | 2026-02-24 | Complete | Plan v1.2 |  | No | 1 | No
CHK-029 | Training & Communications | UAT induction session completed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Gareth Evans | 2026-03-02 | Complete | Script pack baseline |  | No | 1 | No
CHK-030 | Training & Communications | Daily communications template agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ibrahim Ali | 2026-02-26 | In Progress | Plan v1.2 |  | No | 0 | Yes
CHK-031 | Training & Communications | Hypercare / support contacts shared | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Gareth Evans | 2026-03-01 | Complete |  |  | No | 1 | No
CHK-032 | Training & Communications | Business walkthrough completed for new capability | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Gareth Evans | 2026-02-25 | In Progress | Access request tracker |  | No | 0 | Yes
CHK-033 | Training & Communications | Known constraints communicated | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Laura Green | 2026-02-26 | Complete | Plan v1.2 |  | No | 1 | No
CHK-034 | Training & Communications | Training attendance logged | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Aisha Khan | 2026-03-01 | In Progress | Script pack baseline |  | No | 0 | Yes
CHK-035 | Training & Communications | Stakeholder updates scheduled | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | No | Karl Bennett | 2026-03-01 | Complete | Triage Terms of Reference |  | No | 1 | No
CHK-036 | Environment & Access | UAT environment code deployed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Gareth Evans | 2026-02-25 | Complete | Plan v1.2 |  | No | 1 | No
CHK-037 | Environment & Access | Reference data loaded | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Aisha Khan | 2026-03-04 | Complete |  |  | No | 1 | No
CHK-038 | Environment & Access | User security roles provisioned | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Nadia Shah | 2026-02-26 | Complete | Training attendance log |  | No | 1 | No
CHK-039 | Environment & Access | Email / notification services configured | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Karl Bennett | 2026-02-26 | Complete | Plan v1.2 |  | No | 1 | No
CHK-040 | Environment & Access | Batch jobs scheduled for UAT window | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Karl Bennett | 2026-02-27 | Complete | Access request tracker |  | No | 1 | No
CHK-041 | Environment & Access | Environment refresh plan agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Emily Foster | 2026-03-03 | Complete | Access request tracker |  | No | 1 | No
CHK-042 | Environment & Access | Support model for outages agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | No | Emily Foster | 2026-03-03 | Complete | Script pack baseline |  | No | 1 | No
CHK-043 | Test Data | Golden path test data available | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Karl Bennett | 2026-03-03 | In Progress | Script pack baseline |  | No | 0 | Yes
CHK-044 | Test Data | Edge-case data prepared | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Chloe Morgan | 2026-03-02 | In Progress | Triage Terms of Reference |  | No | 0 | Yes
CHK-045 | Test Data | Data refresh cycle agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Aisha Khan | 2026-02-28 | In Progress |  |  | No | 0 | Yes
CHK-046 | Test Data | PII masking controls confirmed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Laura Green | 2026-02-25 | Complete | Plan v1.2 |  | No | 1 | No
CHK-047 | Test Data | Data creation / reset procedure documented | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Karl Bennett | 2026-02-28 | Complete | Access request tracker |  | No | 1 | No
CHK-048 | Test Data | Data defects triage route agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Karl Bennett | 2026-02-27 | Complete | Script pack baseline |  | No | 1 | No
CHK-049 | Test Data | Data ownership confirmed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Laura Green | 2026-03-02 | Not Started | Script pack baseline | Monitor closely at readiness review. | Yes | 0 | Yes
CHK-050 | Support Model | Daily triage attendees confirmed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ibrahim Ali | 2026-02-24 | Blocked | Plan v1.2 | Monitor closely at readiness review. | Yes | 0 | Yes
CHK-051 | Support Model | Developer / vendor support windows agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Chloe Morgan | 2026-02-26 | In Progress | Plan v1.2 |  | No | 0 | Yes
CHK-052 | Support Model | Defect logging standard issued | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | No | Karl Bennett | 2026-02-26 | Complete | Training attendance log |  | No | 1 | No
CHK-053 | Support Model | Escalation SLAs communicated | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | No | Gareth Evans | 2026-02-24 | In Progress | Triage Terms of Reference |  | No | 0 | Yes
CHK-054 | Support Model | Business decision forum defined | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Jessica Reed | 2026-03-04 | In Progress | Plan v1.2 |  | No | 0 | Yes
CHK-055 | Support Model | Weekend / out-of-hours support agreed where needed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Aisha Khan | 2026-02-25 | In Progress | Triage Terms of Reference |  | No | 0 | Yes
CHK-056 | Support Model | War room protocol documented | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ben Carter | 2026-03-03 | Complete | Plan v1.2 |  | No | 1 | No
CHK-057 | Defect Triage & Governance | Defect workflow agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Aisha Khan | 2026-03-04 | In Progress |  |  | No | 0 | Yes
CHK-058 | Defect Triage & Governance | Severity tolerance agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Gareth Evans | 2026-02-26 | Complete | Training attendance log |  | No | 1 | No
CHK-059 | Defect Triage & Governance | Known defect list baselined | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Chloe Morgan | 2026-03-02 | Complete |  |  | No | 1 | No
CHK-060 | Defect Triage & Governance | Re-test ownership defined | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ben Carter | 2026-03-01 | In Progress | Access request tracker |  | No | 0 | Yes
CHK-061 | Defect Triage & Governance | Leadership escalation threshold agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Laura Green | 2026-03-04 | Complete | Plan v1.2 |  | No | 1 | No
CHK-062 | Defect Triage & Governance | Defect reporting dashboard agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ibrahim Ali | 2026-03-02 | Complete | Script pack baseline |  | No | 1 | No
CHK-063 | Defect Triage & Governance | Defect closure evidence expectations defined | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ibrahim Ali | 2026-02-25 | In Progress | Triage Terms of Reference |  | No | 0 | Yes
CHK-064 | Reporting & Sign-Off | Daily dashboard reviewed and accepted | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Chloe Morgan | 2026-03-01 | In Progress | Plan v1.2 |  | No | 0 | Yes
CHK-065 | Reporting & Sign-Off | Status reporting cadence agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Karl Bennett | 2026-02-26 | Complete |  |  | No | 1 | No
CHK-066 | Reporting & Sign-Off | Residual risk process agreed | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Ben Carter | 2026-02-26 | Complete |  |  | No | 1 | No
CHK-067 | Reporting & Sign-Off | Sign-off approvers nominated | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Emily Foster | 2026-02-28 | In Progress | Plan v1.2 |  | No | 0 | Yes
CHK-068 | Reporting & Sign-Off | Go / no-go forum date reserved | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | No | Gareth Evans | 2026-03-01 | In Progress | Access request tracker |  | No | 0 | Yes
CHK-069 | Reporting & Sign-Off | Exit evidence pack structure defined | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | No | Gareth Evans | 2026-03-03 | Complete | Plan v1.2 |  | No | 1 | No
CHK-070 | Reporting & Sign-Off | Lessons learned session scheduled | Evidence should be traceable, owned, and reviewed before the relevant execution window begins. | Yes | Aisha Khan | 2026-03-01 | In Progress |  |  | No | 0 | Yes

## Scenario Register
Northbridge Citizens Services ¦ Scenario Register
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Maintain the master catalogue of UAT scenarios here. This sheet should show scope coverage, ownership and readiness before execution. Execution and defect counts update automatically from the execution tracker and defect log to show which scenarios are active, troublesome or still untouched.
Scenario ID | Scenario Title | Business Process | Business Area | Requirement ID | Priority | Risk Rating | Tester Owner | Wave | Prerequisite | Data Required | Design Status | Execution Count | Pass Count | Fail Count | Blocked Count | Comments
SCN-001 | Create a new case intake record with all mandatory fields | Case Intake | Contact Centre | REQ-001 | High | High | Marcus Hall | Wave 1 - Core Journeys | Reference data loaded | Golden path customer | In Review | 4 | 3 | 0 | 1
SCN-002 | Amend an existing case update record and preserve audit history | Case Update | Case Management | REQ-002 | High | Medium | Karl Bennett | Wave 1 - Core Journeys | Reference data loaded | Multi-case household | Approved | 3 | 1 | 2 | 0
SCN-003 | Complete work allocation using a valid end-to-end happy path | Work Allocation | Field Operations | REQ-003 | Low | Medium | Laura Green | Wave 2 - Exceptions | No specific prerequisite | Outstanding balance account | Approved | 0 | 0 | 0 | 0
SCN-004 | Trigger validation rules during debt review for missing mandatory data | Debt Review | Finance & Billing | REQ-004 | Medium | High | Hannah Price | Wave 2 - Exceptions | Customer record available | Golden path customer | Approved | 0 | 0 | 0 | 0
SCN-005 | Route operational reporting work item to the correct team based on business rules | Operational Reporting | Reporting & MI | REQ-005 | Low | Medium | Quentin Ross | Wave 3 - Reporting & Close Down | Customer record available | Edge-case customer | In Review | 2 | 2 | 0 | 0
SCN-006 | Complete identity & eligibility using an exception or edge-case path | Identity & Eligibility | Contact Centre | REQ-006 | High | Medium | Chloe Morgan | Wave 1 - Core Journeys | No specific prerequisite | Edge-case customer | Approved | 1 | 0 | 0 | 1
SCN-007 | Verify role-based access controls during complaint handling | Complaint Handling | Case Management | REQ-007 | High | Medium | Karl Bennett | Wave 1 - Core Journeys | No specific prerequisite | Edge-case customer | Approved | 1 | 1 | 0 | 0
SCN-008 | Confirm notifications and downstream updates generated by mobile updates | Mobile Updates | Field Operations | REQ-008 | Medium | Low | Hannah Price | Wave 2 - Exceptions | Reference data loaded | Outstanding balance account | Approved | 2 | 2 | 0 | 0
SCN-009 | Recover from a failed attempt and resume charges & payments | Charges & Payments | Finance & Billing | REQ-009 | Critical | Low | Marcus Hall | Wave 2 - Exceptions | User profile provisioned | Multi-case household | In Review | 1 | 0 | 1 | 0 | Regulatory evidence required.
SCN-010 | Validate MI output generated from regulatory reporting | Regulatory Reporting | Reporting & MI | REQ-010 | Low | Medium | Karl Bennett | Wave 3 - Reporting & Close Down | User profile provisioned | Edge-case customer | Approved | 0 | 0 | 0 | 0
SCN-011 | Create a new call handling record with all mandatory fields | Call Handling | Contact Centre | REQ-011 | Medium | Medium | Priya Singh | Wave 1 - Core Journeys | No specific prerequisite | Multi-case household | In Review | 5 | 1 | 3 | 0
SCN-012 | Amend an existing escalations record and preserve audit history | Escalations | Case Management | REQ-012 | Low | High | Ruth Adams | Wave 1 - Core Journeys | Reference data loaded | Golden path customer | Approved | 0 | 0 | 0 | 0
SCN-013 | Complete appointment booking using a valid end-to-end happy path | Appointment Booking | Field Operations | REQ-013 | High | High | Priya Singh | Wave 2 - Exceptions | No specific prerequisite | Golden path customer | In Review | 1 | 0 | 0 | 0
SCN-014 | Trigger validation rules during adjustments for missing mandatory data | Adjustments | Finance & Billing | REQ-014 | Medium | Medium | Karl Bennett | Wave 2 - Exceptions | No specific prerequisite | Golden path customer | Approved | 1 | 0 | 0 | 1
SCN-015 | Route dashboard refresh work item to the correct team based on business rules | Dashboard Refresh | Reporting & MI | REQ-015 | High | Low | Karl Bennett | Wave 3 - Reporting & Close Down | Customer record available | Golden path customer | In Review | 2 | 2 | 0 | 0
SCN-016 | Complete case routing using an exception or edge-case path | Case Routing | Contact Centre | REQ-016 | High | High | Karl Bennett | Wave 1 - Core Journeys | No specific prerequisite | Edge-case customer | Approved | 3 | 2 | 1 | 0
SCN-017 | Verify role-based access controls during case creation | Case Creation | Case Management | REQ-017 | High | Medium | Gareth Evans | Wave 1 - Core Journeys | User profile provisioned | Outstanding balance account | Approved | 3 | 3 | 0 | 0
SCN-018 | Confirm notifications and downstream updates generated by visit completion | Visit Completion | Field Operations | REQ-018 | Medium | Low | Aisha Khan | Wave 2 - Exceptions | No specific prerequisite | Outstanding balance account | Approved | 2 | 0 | 0 | 1
SCN-019 | Recover from a failed attempt and resume refunds | Refunds | Finance & Billing | REQ-019 | High | Medium | Laura Green | Wave 2 - Exceptions | User profile provisioned | Golden path customer | In Review | 3 | 2 | 1 | 0
SCN-020 | Validate MI output generated from data reconciliation | Data Reconciliation | Reporting & MI | REQ-020 | Medium | High | Ruth Adams | Wave 3 - Reporting & Close Down | Reference data loaded | Historic closed case | Approved | 0 | 0 | 0 | 0
SCN-021 | Create a new case intake record with all mandatory fields | Case Intake | Contact Centre | REQ-021 | High | Medium | Farah Malik | Wave 1 - Core Journeys | Customer record available | Historic closed case | Approved | 3 | 2 | 1 | 0
SCN-022 | Amend an existing case update record and preserve audit history | Case Update | Case Management | REQ-022 | Medium | High | Gareth Evans | Wave 1 - Core Journeys | Customer record available | Multi-case household | Approved | 3 | 2 | 0 | 0
SCN-023 | Complete work allocation using a valid end-to-end happy path | Work Allocation | Field Operations | REQ-023 | Medium | Medium | Quentin Ross | Wave 2 - Exceptions | Reference data loaded | Edge-case customer | In Review | 5 | 5 | 0 | 0
SCN-024 | Trigger validation rules during debt review for missing mandatory data | Debt Review | Finance & Billing | REQ-024 | High | Medium | Hannah Price | Wave 2 - Exceptions | No specific prerequisite | Edge-case customer | Ready | 3 | 3 | 0 | 0
SCN-025 | Route operational reporting work item to the correct team based on business rules | Operational Reporting | Reporting & MI | REQ-025 | Medium | High | Chloe Morgan | Wave 3 - Reporting & Close Down | Reference data loaded | Outstanding balance account | Ready | 3 | 1 | 0 | 2
SCN-026 | Complete identity & eligibility using an exception or edge-case path | Identity & Eligibility | Contact Centre | REQ-026 | High | Medium | Gareth Evans | Wave 1 - Core Journeys | No specific prerequisite | Edge-case customer | Approved | 2 | 1 | 1 | 0
SCN-027 | Verify role-based access controls during complaint handling | Complaint Handling | Case Management | REQ-027 | Low | Medium | Hannah Price | Wave 1 - Core Journeys | Inbound interface stub active | Multi-case household | Ready | 0 | 0 | 0 | 0
SCN-028 | Confirm notifications and downstream updates generated by mobile updates | Mobile Updates | Field Operations | REQ-028 | Critical | Medium | Priya Singh | Wave 2 - Exceptions | Inbound interface stub active | Multi-case household | Approved | 2 | 0 | 0 | 1 | Regulatory evidence required.
SCN-029 | Recover from a failed attempt and resume charges & payments | Charges & Payments | Finance & Billing | REQ-029 | Critical | Medium | Daniel Hughes | Wave 2 - Exceptions | Reference data loaded | Multi-case household | Approved | 2 | 1 | 1 | 0 | Regulatory evidence required.
SCN-030 | Validate MI output generated from regulatory reporting | Regulatory Reporting | Reporting & MI | REQ-030 | Medium | High | Gareth Evans | Wave 3 - Reporting & Close Down | User profile provisioned | Historic closed case | Approved | 4 | 3 | 1 | 0
SCN-031 | Create a new case intake record with all mandatory fields | Case Intake | Contact Centre | REQ-001 | Medium | Medium | Hannah Price | Wave 1 - Core Journeys | Reference data loaded | Multi-case household | Approved | 0 | 0 | 0 | 0
SCN-032 | Amend an existing case update record and preserve audit history | Case Update | Case Management | REQ-002 | Low | High | Aisha Khan | Wave 1 - Core Journeys | Reference data loaded | Edge-case customer | Ready | 3 | 3 | 0 | 0
SCN-033 | Complete work allocation using a valid end-to-end happy path | Work Allocation | Field Operations | REQ-003 | Medium | High | Owen Turner | Wave 2 - Exceptions | Reference data loaded | Edge-case customer | In Review | 4 | 1 | 1 | 1
SCN-034 | Trigger validation rules during debt review for missing mandatory data | Debt Review | Finance & Billing | REQ-004 | Low | Medium | Quentin Ross | Wave 2 - Exceptions | Customer record available | Multi-case household | Approved | 1 | 0 | 0 | 0
SCN-035 | Route operational reporting work item to the correct team based on business rules | Operational Reporting | Reporting & MI | REQ-005 | Medium | Low | Ruth Adams | Wave 3 - Reporting & Close Down | User profile provisioned | Edge-case customer | In Review | 3 | 2 | 0 | 1
SCN-036 | Complete identity & eligibility using an exception or edge-case path | Identity & Eligibility | Contact Centre | REQ-006 | Low | Medium | Ben Carter | Wave 1 - Core Journeys | Customer record available | Golden path customer | Ready | 0 | 0 | 0 | 0
SCN-037 | Verify role-based access controls during complaint handling | Complaint Handling | Case Management | REQ-007 | Medium | Low | Farah Malik | Wave 1 - Core Journeys | Reference data loaded | Historic closed case | Ready | 1 | 0 | 1 | 0
SCN-038 | Confirm notifications and downstream updates generated by mobile updates | Mobile Updates | Field Operations | REQ-008 | High | Medium | Hannah Price | Wave 2 - Exceptions | Inbound interface stub active | Golden path customer | Approved | 6 | 3 | 0 | 1
SCN-039 | Recover from a failed attempt and resume charges & payments | Charges & Payments | Finance & Billing | REQ-009 | Medium | Medium | Ben Carter | Wave 2 - Exceptions | No specific prerequisite | Golden path customer | Approved | 0 | 0 | 0 | 0
SCN-040 | Validate MI output generated from regulatory reporting | Regulatory Reporting | Reporting & MI | REQ-010 | Medium | Medium | Karl Bennett | Wave 3 - Reporting & Close Down | User profile provisioned | Outstanding balance account | In Review | 0 | 0 | 0 | 0
SCN-041 | Create a new call handling record with all mandatory fields | Call Handling | Contact Centre | REQ-011 | High | Medium | Laura Green | Wave 1 - Core Journeys | Inbound interface stub active | Outstanding balance account | Approved | 2 | 1 | 0 | 1
SCN-042 | Amend an existing escalations record and preserve audit history | Escalations | Case Management | REQ-012 | Low | High | Daniel Hughes | Wave 1 - Core Journeys | Reference data loaded | Historic closed case | In Review | 1 | 1 | 0 | 0
SCN-043 | Complete appointment booking using a valid end-to-end happy path | Appointment Booking | Field Operations | REQ-013 | High | Low | Chloe Morgan | Wave 2 - Exceptions | User profile provisioned | Outstanding balance account | In Review | 4 | 3 | 0 | 0
SCN-044 | Trigger validation rules during adjustments for missing mandatory data | Adjustments | Finance & Billing | REQ-014 | Medium | Medium | Laura Green | Wave 2 - Exceptions | No specific prerequisite | Historic closed case | Ready | 3 | 2 | 0 | 0
SCN-045 | Route dashboard refresh work item to the correct team based on business rules | Dashboard Refresh | Reporting & MI | REQ-015 | Medium | Medium | Daniel Hughes | Wave 3 - Reporting & Close Down | User profile provisioned | Outstanding balance account | Ready | 1 | 1 | 0 | 0
SCN-046 | Complete case routing using an exception or edge-case path | Case Routing | Contact Centre | REQ-016 | High | Medium | Karl Bennett | Wave 1 - Core Journeys | Customer record available | Historic closed case | In Review | 4 | 2 | 1 | 1
SCN-047 | Verify role-based access controls during case creation | Case Creation | Case Management | REQ-017 | High | Medium | Karl Bennett | Wave 1 - Core Journeys | No specific prerequisite | Multi-case household | In Review | 0 | 0 | 0 | 0
SCN-048 | Confirm notifications and downstream updates generated by visit completion | Visit Completion | Field Operations | REQ-018 | Low | High | Priya Singh | Wave 2 - Exceptions | Customer record available | Golden path customer | Ready | 1 | 0 | 0 | 1
SCN-049 | Recover from a failed attempt and resume refunds | Refunds | Finance & Billing | REQ-019 | Medium | Medium | Karl Bennett | Wave 2 - Exceptions | User profile provisioned | Multi-case household | Approved | 1 | 1 | 0 | 0
SCN-050 | Validate MI output generated from data reconciliation | Data Reconciliation | Reporting & MI | REQ-020 | Medium | High | Chloe Morgan | Wave 3 - Reporting & Close Down | User profile provisioned | Historic closed case | Ready | 1 | 0 | 1 | 0
SCN-051 | Create a new case intake record with all mandatory fields | Case Intake | Contact Centre | REQ-021 | High | Medium | Priya Singh | Wave 1 - Core Journeys | User profile provisioned | Golden path customer | In Review | 5 | 4 | 1 | 0
SCN-052 | Amend an existing case update record and preserve audit history | Case Update | Case Management | REQ-022 | Low | Low | Ben Carter | Wave 1 - Core Journeys | Customer record available | Edge-case customer | Approved | 0 | 0 | 0 | 0
SCN-053 | Complete work allocation using a valid end-to-end happy path | Work Allocation | Field Operations | REQ-023 | Medium | Medium | Priya Singh | Wave 2 - Exceptions | No specific prerequisite | Edge-case customer | Approved | 2 | 2 | 0 | 0
SCN-054 | Trigger validation rules during debt review for missing mandatory data | Debt Review | Finance & Billing | REQ-024 | High | High | Farah Malik | Wave 2 - Exceptions | Inbound interface stub active | Golden path customer | Ready | 1 | 1 | 0 | 0
SCN-055 | Route operational reporting work item to the correct team based on business rules | Operational Reporting | Reporting & MI | REQ-025 | Low | Low | Priya Singh | Wave 3 - Reporting & Close Down | User profile provisioned | Outstanding balance account | Ready | 0 | 0 | 0 | 0
SCN-056 | Complete identity & eligibility using an exception or edge-case path | Identity & Eligibility | Contact Centre | REQ-026 | Medium | Medium | Ben Carter | Wave 1 - Core Journeys | Inbound interface stub active | Edge-case customer | Ready | 0 | 0 | 0 | 0
SCN-057 | Verify role-based access controls during complaint handling | Complaint Handling | Case Management | REQ-027 | Low | Medium | Hannah Price | Wave 1 - Core Journeys | User profile provisioned | Golden path customer | Approved | 0 | 0 | 0 | 0
SCN-058 | Confirm notifications and downstream updates generated by mobile updates | Mobile Updates | Field Operations | REQ-028 | High | Medium | Chloe Morgan | Wave 2 - Exceptions | Customer record available | Outstanding balance account | Approved | 3 | 3 | 0 | 0
SCN-059 | Recover from a failed attempt and resume charges & payments | Charges & Payments | Finance & Billing | REQ-029 | High | Low | Marcus Hall | Wave 2 - Exceptions | Reference data loaded | Golden path customer | Approved | 4 | 3 | 0 | 0
SCN-060 | Validate MI output generated from regulatory reporting | Regulatory Reporting | Reporting & MI | REQ-030 | High | Medium | Karl Bennett | Wave 3 - Reporting & Close Down | Reference data loaded | Golden path customer | Approved | 4 | 1 | 1 | 2
SCN-061 | Create a new case intake record with all mandatory fields | Case Intake | Contact Centre | REQ-001 | High | Low | Priya Singh | Wave 1 - Core Journeys | No specific prerequisite | Historic closed case | Ready | 2 | 1 | 1 | 0
SCN-062 | Amend an existing case update record and preserve audit history | Case Update | Case Management | REQ-002 | Low | High | Ben Carter | Wave 1 - Core Journeys | Inbound interface stub active | Golden path customer | Approved | 2 | 2 | 0 | 0
SCN-063 | Complete work allocation using a valid end-to-end happy path | Work Allocation | Field Operations | REQ-003 | Medium | Medium | Gareth Evans | Wave 2 - Exceptions | Customer record available | Multi-case household | Ready | 1 | 0 | 0 | 1
SCN-064 | Trigger validation rules during debt review for missing mandatory data | Debt Review | Finance & Billing | REQ-004 | Medium | Medium | Marcus Hall | Wave 2 - Exceptions | Reference data loaded | Outstanding balance account | Approved | 3 | 2 | 1 | 0
SCN-065 | Route operational reporting work item to the correct team based on business rules | Operational Reporting | Reporting & MI | REQ-005 | Medium | Medium | Laura Green | Wave 3 - Reporting & Close Down | No specific prerequisite | Edge-case customer | Ready | 1 | 1 | 0 | 0
SCN-066 | Complete identity & eligibility using an exception or edge-case path | Identity & Eligibility | Contact Centre | REQ-006 | Medium | Medium | Farah Malik | Wave 1 - Core Journeys | No specific prerequisite | Historic closed case | In Review | 1 | 0 | 1 | 0
SCN-067 | Verify role-based access controls during complaint handling | Complaint Handling | Case Management | REQ-007 | Medium | High | Laura Green | Wave 1 - Core Journeys | User profile provisioned | Multi-case household | Approved | 2 | 2 | 0 | 0
SCN-068 | Confirm notifications and downstream updates generated by mobile updates | Mobile Updates | Field Operations | REQ-008 | Medium | Medium | Quentin Ross | Wave 2 - Exceptions | Inbound interface stub active | Edge-case customer | Approved | 1 | 1 | 0 | 0
SCN-069 | Recover from a failed attempt and resume charges & payments | Charges & Payments | Finance & Billing | REQ-009 | Medium | Low | Farah Malik | Wave 2 - Exceptions | Reference data loaded | Outstanding balance account | Approved | 1 | 0 | 1 | 0
SCN-070 | Validate MI output generated from regulatory reporting | Regulatory Reporting | Reporting & MI | REQ-010 | Medium | Medium | Hannah Price | Wave 3 - Reporting & Close Down | Customer record available | Edge-case customer | Approved | 4 | 4 | 0 | 0
SCN-071 | Create a new call handling record with all mandatory fields | Call Handling | Contact Centre | REQ-011 | High | High | Ruth Adams | Wave 1 - Core Journeys | No specific prerequisite | Golden path customer | Approved | 1 | 0 | 0 | 1
SCN-072 | Amend an existing escalations record and preserve audit history | Escalations | Case Management | REQ-012 | Low | Medium | Owen Turner | Wave 1 - Core Journeys | Inbound interface stub active | Multi-case household | In Review | 1 | 1 | 0 | 0
SCN-073 | Complete appointment booking using a valid end-to-end happy path | Appointment Booking | Field Operations | REQ-013 | Medium | High | Daniel Hughes | Wave 2 - Exceptions | Inbound interface stub active | Edge-case customer | Ready | 2 | 2 | 0 | 0
SCN-074 | Trigger validation rules during adjustments for missing mandatory data | Adjustments | Finance & Billing | REQ-014 | Low | Medium | Ben Carter | Wave 2 - Exceptions | No specific prerequisite | Edge-case customer | Approved | 3 | 0 | 2 | 0
SCN-075 | Route dashboard refresh work item to the correct team based on business rules | Dashboard Refresh | Reporting & MI | REQ-015 | High | High | Quentin Ross | Wave 3 - Reporting & Close Down | No specific prerequisite | Historic closed case | Approved | 1 | 1 | 0 | 0
SCN-076 | Complete case routing using an exception or edge-case path | Case Routing | Contact Centre | REQ-016 | Low | Low | Priya Singh | Wave 1 - Core Journeys | No specific prerequisite | Multi-case household | Approved | 2 | 1 | 1 | 0
SCN-077 | Verify role-based access controls during case creation | Case Creation | Case Management | REQ-017 | Medium | Medium | Karl Bennett | Wave 1 - Core Journeys | User profile provisioned | Outstanding balance account | Approved | 2 | 1 | 0 | 0
SCN-078 | Confirm notifications and downstream updates generated by visit completion | Visit Completion | Field Operations | REQ-018 | Medium | Medium | Karl Bennett | Wave 2 - Exceptions | Inbound interface stub active | Golden path customer | Approved | 2 | 0 | 1 | 0
SCN-079 | Recover from a failed attempt and resume refunds | Refunds | Finance & Billing | REQ-019 | High | Medium | Chloe Morgan | Wave 2 - Exceptions | User profile provisioned | Edge-case customer | In Review | 2 | 0 | 2 | 0
SCN-080 | Validate MI output generated from data reconciliation | Data Reconciliation | Reporting & MI | REQ-020 | Medium | Medium | Chloe Morgan | Wave 3 - Reporting & Close Down | Inbound interface stub active | Multi-case household | In Review | 0 | 0 | 0 | 0

## Execution Tracker
Northbridge Citizens Services ¦ Execution Tracker
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Use this as the daily control log for actual UAT execution. Record scenario, tester, status, defect/issue links and retest need. Business area and process area are looked up automatically from the scenario register. This sheet feeds execution KPIs, tester activity, pass/fail trends and blocked-work views.
Execution ID | Execution Date | Scenario ID | Tester | Wave | Cycle | Status | Defect ID | Blocker Issue ID | Retest Required | Retest Status | Comments | Business Area | Process Area
EXE-001 | 2026-03-01 | SCN-024 | Hannah Price | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required |  | Finance & Billing | Debt Review
EXE-002 | 2026-02-28 | SCN-058 | Chloe Morgan | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Execution paused pending dependency resolution. | Field Operations | Mobile Updates
EXE-003 | 2026-03-02 | SCN-071 | Ruth Adams | Wave 1 - Core Journeys | Cycle 1 | Blocked |  | ISS-003 | Yes | Complete | Execution paused pending dependency resolution. | Contact Centre | Call Handling
EXE-004 | 2026-03-07 | SCN-051 | Priya Singh | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required | Evidence captured successfully. | Contact Centre | Case Intake
EXE-005 | 2026-03-04 | SCN-021 | Farah Malik | Wave 1 - Core Journeys | Cycle 2 | Failed | DEF-016 |  | Yes | Not Due | Evidence captured successfully. | Contact Centre | Case Intake
EXE-006 | 2026-02-27 | SCN-017 | Gareth Evans | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required | Execution paused pending dependency resolution. | Case Management | Case Creation
EXE-007 | 2026-03-08 | SCN-008 | Hannah Price | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required |  | Field Operations | Mobile Updates
EXE-008 | 2026-03-06 | SCN-013 | Priya Singh | Wave 2 - Exceptions | Cycle 2 | Deferred |  |  | No | Not Required |  | Field Operations | Appointment Booking
EXE-009 | 2026-02-27 | SCN-037 | Farah Malik | Wave 1 - Core Journeys | Cycle 1 | Failed | DEF-004 |  | Yes | Not Due | Awaiting triage outcome. | Case Management | Complaint Handling
EXE-010 | 2026-03-07 | SCN-041 | Laura Green | Wave 1 - Core Journeys | Cycle 2 | Blocked |  | ISS-001 | Yes | Not Due | Awaiting triage outcome. | Contact Centre | Call Handling
EXE-011 | 2026-02-24 | SCN-075 | Quentin Ross | Wave 3 - Reporting & Close Down | Cycle 1 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Reporting & MI | Dashboard Refresh
EXE-012 | 2026-02-24 | SCN-070 | Hannah Price | Wave 3 - Reporting & Close Down | Cycle 1 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Reporting & MI | Regulatory Reporting
EXE-013 | 2026-03-06 | SCN-021 | Farah Malik | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Contact Centre | Case Intake
EXE-014 | 2026-03-03 | SCN-067 | Laura Green | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required | Execution paused pending dependency resolution. | Case Management | Complaint Handling
EXE-015 | 2026-03-07 | SCN-051 | Priya Singh | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required |  | Contact Centre | Case Intake
EXE-016 | 2026-03-05 | SCN-062 | Ben Carter | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required | Execution paused pending dependency resolution. | Case Management | Case Update
EXE-017 | 2026-03-04 | SCN-065 | Laura Green | Wave 3 - Reporting & Close Down | Cycle 2 | Passed |  |  | No | Not Required | Completed within slot. | Reporting & MI | Operational Reporting
EXE-018 | 2026-02-26 | SCN-015 | Karl Bennett | Wave 3 - Reporting & Close Down | Cycle 1 | Passed |  |  | No | Not Required |  | Reporting & MI | Dashboard Refresh
EXE-019 | 2026-03-02 | SCN-001 | Marcus Hall | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required |  | Contact Centre | Case Intake
EXE-020 | 2026-03-07 | SCN-023 | Quentin Ross | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Field Operations | Work Allocation
EXE-021 | 2026-02-24 | SCN-054 | Farah Malik | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Evidence captured successfully. | Finance & Billing | Debt Review
EXE-022 | 2026-03-10 | SCN-074 | Ben Carter | Wave 2 - Exceptions | Cycle 2 | Failed |  |  | Yes | Complete |  | Finance & Billing | Adjustments
EXE-023 | 2026-03-05 | SCN-022 | Gareth Evans | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required | Execution paused pending dependency resolution. | Case Management | Case Update
EXE-024 | 2026-03-05 | SCN-059 | Marcus Hall | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required |  | Finance & Billing | Charges & Payments
EXE-025 | 2026-03-08 | SCN-073 | Daniel Hughes | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Field Operations | Appointment Booking
EXE-026 | 2026-03-06 | SCN-060 | Karl Bennett | Wave 3 - Reporting & Close Down | Cycle 2 | Blocked |  | ISS-002 | Yes | Complete |  | Reporting & MI | Regulatory Reporting
EXE-027 | 2026-03-05 | SCN-007 | Karl Bennett | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required |  | Case Management | Complaint Handling
EXE-028 | 2026-02-27 | SCN-072 | Owen Turner | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Case Management | Escalations
EXE-029 | 2026-03-03 | SCN-068 | Quentin Ross | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Evidence captured successfully. | Field Operations | Mobile Updates
EXE-030 | 2026-03-10 | SCN-038 | Hannah Price | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required |  | Field Operations | Mobile Updates
EXE-031 | 2026-03-04 | SCN-035 | Ruth Adams | Wave 3 - Reporting & Close Down | Cycle 2 | Blocked | DEF-033 | ISS-009 | Yes | Complete | Re-test required after fix deployment. | Reporting & MI | Operational Reporting
EXE-032 | 2026-03-07 | SCN-064 | Marcus Hall | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required | Execution paused pending dependency resolution. | Finance & Billing | Debt Review
EXE-033 | 2026-02-25 | SCN-026 | Gareth Evans | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required |  | Contact Centre | Identity & Eligibility
EXE-034 | 2026-03-03 | SCN-079 | Chloe Morgan | Wave 2 - Exceptions | Cycle 1 | Failed | DEF-005 |  | Yes | Complete |  | Finance & Billing | Refunds
EXE-035 | 2026-03-02 | SCN-051 | Priya Singh | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required |  | Contact Centre | Case Intake
EXE-036 | 2026-03-10 | SCN-034 | Quentin Ross | Wave 2 - Exceptions | Cycle 2 | Deferred |  |  | No | Not Required | Evidence captured successfully. | Finance & Billing | Debt Review
EXE-037 | 2026-03-09 | SCN-011 | Priya Singh | Wave 1 - Core Journeys | Cycle 2 | Failed | DEF-029 |  | Yes | Complete | Awaiting triage outcome. | Contact Centre | Call Handling
EXE-038 | 2026-03-08 | SCN-066 | Farah Malik | Wave 1 - Core Journeys | Cycle 2 | Failed | DEF-017 |  | Yes | Complete | Awaiting triage outcome. | Contact Centre | Identity & Eligibility
EXE-039 | 2026-03-01 | SCN-019 | Laura Green | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Completed within slot. | Finance & Billing | Refunds
EXE-040 | 2026-03-06 | SCN-002 | Karl Bennett | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required |  | Case Management | Case Update
EXE-041 | 2026-02-27 | SCN-001 | Marcus Hall | Wave 1 - Core Journeys | Cycle 1 | Blocked |  | ISS-008 | Yes | Complete |  | Contact Centre | Case Intake
EXE-042 | 2026-02-24 | SCN-019 | Laura Green | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Finance & Billing | Refunds
EXE-043 | 2026-03-08 | SCN-060 | Karl Bennett | Wave 3 - Reporting & Close Down | Cycle 2 | Blocked | DEF-001 | ISS-005 | Yes | Complete | Re-test required after fix deployment. | Reporting & MI | Regulatory Reporting
EXE-044 | 2026-03-10 | SCN-018 | Aisha Khan | Wave 2 - Exceptions | Cycle 2 | Blocked | DEF-018 | ISS-004 | Yes | Not Due | Evidence captured successfully. | Field Operations | Visit Completion
EXE-045 | 2026-03-10 | SCN-070 | Hannah Price | Wave 3 - Reporting & Close Down | Cycle 2 | Passed |  |  | No | Not Required | Evidence captured successfully. | Reporting & MI | Regulatory Reporting
EXE-046 | 2026-03-01 | SCN-038 | Hannah Price | Wave 2 - Exceptions | Cycle 1 | Deferred |  |  | No | Not Required | Evidence captured successfully. | Field Operations | Mobile Updates
EXE-047 | 2026-03-02 | SCN-024 | Hannah Price | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Finance & Billing | Debt Review
EXE-048 | 2026-03-03 | SCN-060 | Karl Bennett | Wave 3 - Reporting & Close Down | Cycle 1 | Failed | DEF-001 |  | Yes | Pending |  | Reporting & MI | Regulatory Reporting
EXE-049 | 2026-03-02 | SCN-044 | Laura Green | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Finance & Billing | Adjustments
EXE-050 | 2026-02-25 | SCN-025 | Chloe Morgan | Wave 3 - Reporting & Close Down | Cycle 1 | Blocked |  | ISS-002 | Yes | Not Due | Execution paused pending dependency resolution. | Reporting & MI | Operational Reporting
EXE-051 | 2026-03-05 | SCN-053 | Priya Singh | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required | Evidence captured successfully. | Field Operations | Work Allocation
EXE-052 | 2026-03-04 | SCN-058 | Chloe Morgan | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Field Operations | Mobile Updates
EXE-053 | 2026-03-10 | SCN-023 | Quentin Ross | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required |  | Field Operations | Work Allocation
EXE-054 | 2026-02-25 | SCN-078 | Karl Bennett | Wave 2 - Exceptions | Cycle 1 | Failed |  |  | Yes | Complete | Awaiting triage outcome. | Field Operations | Visit Completion
EXE-055 | 2026-02-27 | SCN-029 | Daniel Hughes | Wave 2 - Exceptions | Cycle 1 | Failed | DEF-015 |  | Yes | Pending | Re-test required after fix deployment. | Finance & Billing | Charges & Payments
EXE-056 | 2026-03-01 | SCN-023 | Quentin Ross | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Completed within slot. | Field Operations | Work Allocation
EXE-057 | 2026-03-07 | SCN-063 | Gareth Evans | Wave 2 - Exceptions | Cycle 2 | Blocked | DEF-016 | ISS-004 | Yes | Not Due | Awaiting triage outcome. | Field Operations | Work Allocation
EXE-058 | 2026-02-24 | SCN-059 | Marcus Hall | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required |  | Finance & Billing | Charges & Payments
EXE-059 | 2026-03-02 | SCN-045 | Daniel Hughes | Wave 3 - Reporting & Close Down | Cycle 1 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Reporting & MI | Dashboard Refresh
EXE-060 | 2026-03-09 | SCN-028 | Priya Singh | Wave 2 - Exceptions | Cycle 2 | Blocked | DEF-019 | ISS-011 | Yes | Complete | Execution paused pending dependency resolution. | Field Operations | Mobile Updates
EXE-061 | 2026-03-07 | SCN-035 | Ruth Adams | Wave 3 - Reporting & Close Down | Cycle 2 | Passed |  |  | No | Not Required |  | Reporting & MI | Operational Reporting
EXE-062 | 2026-03-10 | SCN-038 | Hannah Price | Wave 2 - Exceptions | Cycle 2 | Deferred |  |  | No | Not Required |  | Field Operations | Mobile Updates
EXE-063 | 2026-03-04 | SCN-077 | Karl Bennett | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required |  | Case Management | Case Creation
EXE-064 | 2026-03-06 | SCN-076 | Priya Singh | Wave 1 - Core Journeys | Cycle 2 | Failed | DEF-014 |  | Yes | Complete | Awaiting triage outcome. | Contact Centre | Case Routing
EXE-065 | 2026-03-04 | SCN-001 | Marcus Hall | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required | Evidence captured successfully. | Contact Centre | Case Intake
EXE-066 | 2026-03-06 | SCN-073 | Daniel Hughes | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required | Evidence captured successfully. | Field Operations | Appointment Booking
EXE-067 | 2026-02-24 | SCN-030 | Gareth Evans | Wave 3 - Reporting & Close Down | Cycle 1 | Passed |  |  | No | Not Required |  | Reporting & MI | Regulatory Reporting
EXE-068 | 2026-03-09 | SCN-001 | Marcus Hall | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required |  | Contact Centre | Case Intake
EXE-069 | 2026-03-10 | SCN-015 | Karl Bennett | Wave 3 - Reporting & Close Down | Cycle 2 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Reporting & MI | Dashboard Refresh
EXE-070 | 2026-02-28 | SCN-048 | Priya Singh | Wave 2 - Exceptions | Cycle 1 | Blocked |  | ISS-005 | Yes | Not Due | Execution paused pending dependency resolution. | Field Operations | Visit Completion
EXE-071 | 2026-02-27 | SCN-035 | Ruth Adams | Wave 3 - Reporting & Close Down | Cycle 1 | Passed |  |  | No | Not Required | Completed within slot. | Reporting & MI | Operational Reporting
EXE-072 | 2026-03-09 | SCN-051 | Priya Singh | Wave 1 - Core Journeys | Cycle 2 | Failed | DEF-025 |  | Yes | Pending | Completed within slot. | Contact Centre | Case Intake
EXE-073 | 2026-03-07 | SCN-050 | Chloe Morgan | Wave 3 - Reporting & Close Down | Cycle 2 | Failed | DEF-006 |  | Yes | Complete |  | Reporting & MI | Data Reconciliation
EXE-074 | 2026-03-09 | SCN-044 | Laura Green | Wave 2 - Exceptions | Cycle 2 | Deferred |  |  | No | Not Required |  | Finance & Billing | Adjustments
EXE-075 | 2026-03-10 | SCN-018 | Aisha Khan | Wave 2 - Exceptions | Cycle 2 | Deferred |  |  | No | Not Required | Completed within slot. | Field Operations | Visit Completion
EXE-076 | 2026-03-06 | SCN-074 | Ben Carter | Wave 2 - Exceptions | Cycle 2 | Deferred |  |  | No | Not Required |  | Finance & Billing | Adjustments
EXE-077 | 2026-02-24 | SCN-044 | Laura Green | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Finance & Billing | Adjustments
EXE-078 | 2026-03-08 | SCN-046 | Karl Bennett | Wave 1 - Core Journeys | Cycle 2 | Blocked | DEF-011 | ISS-002 | Yes | Complete |  | Contact Centre | Case Routing
EXE-079 | 2026-03-10 | SCN-029 | Daniel Hughes | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required |  | Finance & Billing | Charges & Payments
EXE-080 | 2026-03-07 | SCN-062 | Ben Carter | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required |  | Case Management | Case Update
EXE-081 | 2026-03-02 | SCN-005 | Quentin Ross | Wave 3 - Reporting & Close Down | Cycle 1 | Passed |  |  | No | Not Required | Evidence captured successfully. | Reporting & MI | Operational Reporting
EXE-082 | 2026-03-05 | SCN-060 | Karl Bennett | Wave 3 - Reporting & Close Down | Cycle 2 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Reporting & MI | Regulatory Reporting
EXE-083 | 2026-03-03 | SCN-061 | Priya Singh | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required | Execution paused pending dependency resolution. | Contact Centre | Case Intake
EXE-084 | 2026-03-06 | SCN-032 | Aisha Khan | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required |  | Case Management | Case Update
EXE-085 | 2026-02-27 | SCN-022 | Gareth Evans | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Case Management | Case Update
EXE-086 | 2026-03-01 | SCN-059 | Marcus Hall | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Finance & Billing | Charges & Payments
EXE-087 | 2026-03-08 | SCN-033 | Owen Turner | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Field Operations | Work Allocation
EXE-088 | 2026-03-04 | SCN-032 | Aisha Khan | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Case Management | Case Update
EXE-089 | 2026-03-05 | SCN-043 | Chloe Morgan | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Field Operations | Appointment Booking
EXE-090 | 2026-03-08 | SCN-030 | Gareth Evans | Wave 3 - Reporting & Close Down | Cycle 2 | Passed |  |  | No | Not Required |  | Reporting & MI | Regulatory Reporting
EXE-091 | 2026-03-05 | SCN-079 | Chloe Morgan | Wave 2 - Exceptions | Cycle 2 | Failed | DEF-005 |  | Yes | Not Due | Re-test required after fix deployment. | Finance & Billing | Refunds
EXE-092 | 2026-02-25 | SCN-038 | Hannah Price | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Field Operations | Mobile Updates
EXE-093 | 2026-02-25 | SCN-038 | Hannah Price | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required |  | Field Operations | Mobile Updates
EXE-094 | 2026-03-03 | SCN-058 | Chloe Morgan | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Completed within slot. | Field Operations | Mobile Updates
EXE-095 | 2026-02-24 | SCN-011 | Priya Singh | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Contact Centre | Call Handling
EXE-096 | 2026-03-02 | SCN-033 | Owen Turner | Wave 2 - Exceptions | Cycle 1 | Blocked |  | ISS-011 | Yes | Not Due | Evidence captured successfully. | Field Operations | Work Allocation
EXE-097 | 2026-02-27 | SCN-076 | Priya Singh | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Contact Centre | Case Routing
EXE-098 | 2026-03-07 | SCN-022 | Gareth Evans | Wave 1 - Core Journeys | Cycle 2 | Deferred |  |  | No | Not Required |  | Case Management | Case Update
EXE-099 | 2026-02-28 | SCN-025 | Chloe Morgan | Wave 3 - Reporting & Close Down | Cycle 1 | Passed |  |  | No | Not Required | Evidence captured successfully. | Reporting & MI | Operational Reporting
EXE-100 | 2026-03-04 | SCN-016 | Karl Bennett | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required |  | Contact Centre | Case Routing
EXE-101 | 2026-03-07 | SCN-002 | Karl Bennett | Wave 1 - Core Journeys | Cycle 2 | Failed | DEF-021 |  | Yes | Pending |  | Case Management | Case Update
EXE-102 | 2026-03-09 | SCN-006 | Chloe Morgan | Wave 1 - Core Journeys | Cycle 2 | Blocked |  | ISS-007 | Yes | Not Due | Awaiting triage outcome. | Contact Centre | Identity & Eligibility
EXE-103 | 2026-02-26 | SCN-019 | Laura Green | Wave 2 - Exceptions | Cycle 1 | Failed | DEF-031 |  | Yes | Complete | Evidence captured successfully. | Finance & Billing | Refunds
EXE-104 | 2026-03-09 | SCN-074 | Ben Carter | Wave 2 - Exceptions | Cycle 2 | Failed |  |  | Yes | Pending |  | Finance & Billing | Adjustments
EXE-105 | 2026-03-05 | SCN-064 | Marcus Hall | Wave 2 - Exceptions | Cycle 2 | Failed | DEF-016 |  | Yes | Complete | Awaiting triage outcome. | Finance & Billing | Debt Review
EXE-106 | 2026-02-24 | SCN-051 | Priya Singh | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required | Execution paused pending dependency resolution. | Contact Centre | Case Intake
EXE-107 | 2026-03-01 | SCN-078 | Karl Bennett | Wave 2 - Exceptions | Cycle 1 | Deferred |  |  | No | Not Required | Completed within slot. | Field Operations | Visit Completion
EXE-108 | 2026-02-27 | SCN-008 | Hannah Price | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Evidence captured successfully. | Field Operations | Mobile Updates
EXE-109 | 2026-03-01 | SCN-017 | Gareth Evans | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required |  | Case Management | Case Creation
EXE-110 | 2026-03-04 | SCN-046 | Karl Bennett | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Contact Centre | Case Routing
EXE-111 | 2026-02-25 | SCN-030 | Gareth Evans | Wave 3 - Reporting & Close Down | Cycle 1 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Reporting & MI | Regulatory Reporting
EXE-112 | 2026-03-08 | SCN-026 | Gareth Evans | Wave 1 - Core Journeys | Cycle 2 | Failed | DEF-027 |  | Yes | Not Due | Execution paused pending dependency resolution. | Contact Centre | Identity & Eligibility
EXE-113 | 2026-02-28 | SCN-024 | Hannah Price | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required |  | Finance & Billing | Debt Review
EXE-114 | 2026-03-01 | SCN-002 | Karl Bennett | Wave 1 - Core Journeys | Cycle 1 | Failed | DEF-021 |  | Yes | Complete | Awaiting triage outcome. | Case Management | Case Update
EXE-115 | 2026-03-01 | SCN-043 | Chloe Morgan | Wave 2 - Exceptions | Cycle 1 | Deferred |  |  | No | Not Required | Execution paused pending dependency resolution. | Field Operations | Appointment Booking
EXE-116 | 2026-02-26 | SCN-049 | Karl Bennett | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Evidence captured successfully. | Finance & Billing | Refunds
EXE-117 | 2026-03-03 | SCN-070 | Hannah Price | Wave 3 - Reporting & Close Down | Cycle 1 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Reporting & MI | Regulatory Reporting
EXE-118 | 2026-03-08 | SCN-016 | Karl Bennett | Wave 1 - Core Journeys | Cycle 2 | Failed |  |  | Yes | Complete | Re-test required after fix deployment. | Contact Centre | Case Routing
EXE-119 | 2026-02-25 | SCN-016 | Karl Bennett | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required |  | Contact Centre | Case Routing
EXE-120 | 2026-03-06 | SCN-041 | Laura Green | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required | Execution paused pending dependency resolution. | Contact Centre | Call Handling
EXE-121 | 2026-03-01 | SCN-046 | Karl Bennett | Wave 1 - Core Journeys | Cycle 1 | Failed | DEF-011 |  | Yes | Complete |  | Contact Centre | Case Routing
EXE-122 | 2026-03-05 | SCN-023 | Quentin Ross | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Field Operations | Work Allocation
EXE-123 | 2026-02-28 | SCN-009 | Marcus Hall | Wave 2 - Exceptions | Cycle 1 | Failed | DEF-031 |  | Yes | Complete | Evidence captured successfully. | Finance & Billing | Charges & Payments
EXE-124 | 2026-03-02 | SCN-011 | Priya Singh | Wave 1 - Core Journeys | Cycle 1 | Failed | DEF-029 |  | Yes | Complete | Re-test required after fix deployment. | Contact Centre | Call Handling
EXE-125 | 2026-03-01 | SCN-011 | Priya Singh | Wave 1 - Core Journeys | Cycle 1 | Failed | DEF-029 |  | Yes | Not Due | Awaiting triage outcome. | Contact Centre | Call Handling
EXE-126 | 2026-03-04 | SCN-064 | Marcus Hall | Wave 2 - Exceptions | Cycle 2 | Passed |  |  | No | Not Required | Execution paused pending dependency resolution. | Finance & Billing | Debt Review
EXE-127 | 2026-03-09 | SCN-030 | Gareth Evans | Wave 3 - Reporting & Close Down | Cycle 2 | Failed | DEF-030 |  | Yes | Not Due | Re-test required after fix deployment. | Reporting & MI | Regulatory Reporting
EXE-128 | 2026-02-28 | SCN-017 | Gareth Evans | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required | Execution paused pending dependency resolution. | Case Management | Case Creation
EXE-129 | 2026-02-25 | SCN-043 | Chloe Morgan | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Field Operations | Appointment Booking
EXE-130 | 2026-03-08 | SCN-042 | Daniel Hughes | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required |  | Case Management | Escalations
EXE-131 | 2026-03-02 | SCN-043 | Chloe Morgan | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required |  | Field Operations | Appointment Booking
EXE-132 | 2026-02-24 | SCN-023 | Quentin Ross | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Completed within slot. | Field Operations | Work Allocation
EXE-133 | 2026-02-25 | SCN-033 | Owen Turner | Wave 2 - Exceptions | Cycle 1 | Failed | DEF-023 |  | Yes | Complete | Execution paused pending dependency resolution. | Field Operations | Work Allocation
EXE-134 | 2026-02-26 | SCN-014 | Karl Bennett | Wave 2 - Exceptions | Cycle 1 | Blocked |  | ISS-004 | Yes | Complete | Re-test required after fix deployment. | Finance & Billing | Adjustments
EXE-135 | 2026-02-26 | SCN-046 | Karl Bennett | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required | Re-test required after fix deployment. | Contact Centre | Case Routing
EXE-136 | 2026-03-04 | SCN-077 | Karl Bennett | Wave 1 - Core Journeys | Cycle 2 | Deferred |  |  | No | Not Required | Completed within slot. | Case Management | Case Creation
EXE-137 | 2026-03-08 | SCN-011 | Priya Singh | Wave 1 - Core Journeys | Cycle 2 | Deferred |  |  | No | Not Required |  | Contact Centre | Call Handling
EXE-138 | 2026-02-26 | SCN-069 | Farah Malik | Wave 2 - Exceptions | Cycle 1 | Failed | DEF-021 |  | Yes | Not Due |  | Finance & Billing | Charges & Payments
EXE-139 | 2026-03-03 | SCN-053 | Priya Singh | Wave 2 - Exceptions | Cycle 1 | Passed |  |  | No | Not Required | Execution paused pending dependency resolution. | Field Operations | Work Allocation
EXE-140 | 2026-02-25 | SCN-028 | Priya Singh | Wave 2 - Exceptions | Cycle 1 | Deferred |  |  | No | Not Required | Evidence captured successfully. | Field Operations | Mobile Updates
EXE-141 | 2026-03-07 | SCN-059 | Marcus Hall | Wave 2 - Exceptions | Cycle 2 | Deferred |  |  | No | Not Required | Execution paused pending dependency resolution. | Finance & Billing | Charges & Payments
EXE-142 | 2026-02-24 | SCN-025 | Chloe Morgan | Wave 3 - Reporting & Close Down | Cycle 1 | Blocked |  | ISS-002 | Yes | Pending | Re-test required after fix deployment. | Reporting & MI | Operational Reporting
EXE-143 | 2026-03-08 | SCN-067 | Laura Green | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Case Management | Complaint Handling
EXE-144 | 2026-03-01 | SCN-038 | Hannah Price | Wave 2 - Exceptions | Cycle 1 | Blocked |  | ISS-006 | Yes | Not Due | Execution paused pending dependency resolution. | Field Operations | Mobile Updates
EXE-145 | 2026-03-10 | SCN-061 | Priya Singh | Wave 1 - Core Journeys | Cycle 2 | Failed | DEF-030 |  | Yes | Not Due | Awaiting triage outcome. | Contact Centre | Case Intake
EXE-146 | 2026-02-24 | SCN-033 | Owen Turner | Wave 2 - Exceptions | Cycle 1 | Deferred |  |  | No | Not Required | Awaiting triage outcome. | Field Operations | Work Allocation
EXE-147 | 2026-02-28 | SCN-070 | Hannah Price | Wave 3 - Reporting & Close Down | Cycle 1 | Passed |  |  | No | Not Required |  | Reporting & MI | Regulatory Reporting
EXE-148 | 2026-03-06 | SCN-021 | Farah Malik | Wave 1 - Core Journeys | Cycle 2 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Contact Centre | Case Intake
EXE-149 | 2026-03-06 | SCN-005 | Quentin Ross | Wave 3 - Reporting & Close Down | Cycle 2 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Reporting & MI | Operational Reporting
EXE-150 | 2026-02-25 | SCN-032 | Aisha Khan | Wave 1 - Core Journeys | Cycle 1 | Passed |  |  | No | Not Required | Awaiting triage outcome. | Case Management | Case Update

## Defect Log
Northbridge Citizens Services ¦ Defect Log
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Record all UAT defects here with severity, priority, ownership, dates, root cause and workaround. Ageing and breach indicators are formula-driven from the report date. This sheet feeds the quality dashboard, defect trends, severity split and retest prioritisation.
Defect ID | Title | Description | Business Area | Process Area | Linked Scenario ID | Linked Requirement ID | Severity | Priority | Status | Owner | Assigned Team | Identified Date | Target Fix Date | Actual Fix Date | Retest Date | Ageing Days | Target Breach | Root Cause | Workaround | Release / Wave | Comments | Age Band | Open Flag
DEF-001 | Workflow routes to incorrect queue | Workflow routes to incorrect queue during regulatory reporting execution for reporting & mi users. | Reporting & MI | Regulatory Reporting | SCN-060 | REQ-030 | S3 - Medium | P3 | Closed | Gareth Evans | Security Admin | 2026-02-25 | 2026-03-04 | 2026-03-05 | 2026-03-07 | 8 | No | Reporting Logic | Use manual workaround and continue with controlled evidence capture. | Wave 3 - Reporting & Close Down |  | 6-10 days | No
DEF-002 | Notification not generated for downstream team | Notification not generated for downstream team during debt review execution for finance & billing users. | Finance & Billing | Debt Review | SCN-054 | REQ-024 | S2 - High | P2 | In Triage | Gareth Evans | D365 Delivery | 2026-03-08 | 2026-03-15 |  |  | 4 | No | Business Rule Mapping | No practical workaround; blocker remains open. | Wave 2 - Exceptions |  | 3-5 days | Yes
DEF-003 | Validation message does not display correctly | Validation message does not display correctly during mobile updates execution for field operations users. | Field Operations | Mobile Updates | SCN-008 | REQ-008 | S1 - Critical | P1 | Fixed - Pending Retest | Ben Carter | Integration Team | 2026-03-01 | 2026-03-05 | 2026-03-05 |  | 11 | Yes | Configuration | Use manual workaround and continue with controlled evidence capture. | Wave 2 - Exceptions | Escalated at daily defect triage. | 11+ days | Yes
DEF-004 | Appointment slot not released after cancellation | Appointment slot not released after cancellation during complaint handling execution for case management users. | Case Management | Complaint Handling | SCN-027 | REQ-027 | S3 - Medium | P3 | In Triage | Karl Bennett | Vendor Support | 2026-03-03 | 2026-03-05 |  |  | 9 | Yes | Workflow Logic | Proceed with alternate scenario until configuration is corrected. | Wave 1 - Core Journeys |  | 6-10 days | Yes
DEF-005 | Workflow routes to incorrect queue | Workflow routes to incorrect queue during refunds execution for finance & billing users. | Finance & Billing | Refunds | SCN-079 | REQ-019 | S3 - Medium | P3 | Open | Aisha Khan | Data Migration | 2026-03-05 | 2026-03-07 |  |  | 7 | Yes | Configuration | Retest after overnight data refresh. | Wave 2 - Exceptions |  | 6-10 days | Yes
DEF-006 | Appointment slot not released after cancellation | Appointment slot not released after cancellation during data reconciliation execution for reporting & mi users. | Reporting & MI | Data Reconciliation | SCN-050 | REQ-020 | S4 - Low | P4 | Closed | Aisha Khan | Vendor Support | 2026-03-02 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 8 | No | Workflow Logic | Proceed with alternate scenario until configuration is corrected. | Wave 3 - Reporting & Close Down |  | 6-10 days | No
DEF-007 | Access profile prevents valid execution | Access profile prevents valid execution during work allocation execution for field operations users. | Field Operations | Work Allocation | SCN-003 | REQ-003 | S4 - Low | P4 | Closed | Aisha Khan | Data Migration | 2026-02-25 | 2026-02-26 | 2026-02-28 | 2026-03-03 | 3 | No | Reporting Logic | Retest after overnight data refresh. | Wave 2 - Exceptions |  | 3-5 days | No
DEF-008 | Duplicate record created on retry | Duplicate record created on retry during refunds execution for finance & billing users. | Finance & Billing | Refunds | SCN-049 | REQ-019 | S1 - Critical | P1 | Fixed - Pending Retest | Ben Carter | Security Admin | 2026-03-03 | 2026-03-05 | 2026-03-08 |  | 9 | Yes | Integration | No practical workaround; blocker remains open. | Wave 2 - Exceptions | Escalated at daily defect triage. | 6-10 days | Yes
DEF-009 | Report output excludes expected population | Report output excludes expected population during case update execution for case management users. | Case Management | Case Update | SCN-062 | REQ-002 | S3 - Medium | P3 | Rejected | Laura Green | Reporting Team | 2026-02-28 | 2026-03-08 |  |  | 12 | No | Reporting Logic | No practical workaround; blocker remains open. | Wave 1 - Core Journeys |  | 11+ days | No
DEF-010 | Report output excludes expected population | Report output excludes expected population during case intake execution for contact centre users. | Contact Centre | Case Intake | SCN-001 | REQ-001 | S4 - Low | P4 | Closed | Laura Green | Vendor Support | 2026-02-25 | 2026-03-02 | 2026-03-05 | 2026-03-06 | 8 | No | Environment | Use admin-assisted update as an interim control. | Wave 1 - Core Journeys |  | 6-10 days | No
DEF-011 | Audit history not retained after amendment | Audit history not retained after amendment during case routing execution for contact centre users. | Contact Centre | Case Routing | SCN-046 | REQ-016 | S2 - High | P2 | Fixed - Pending Retest | Gareth Evans | Reporting Team | 2026-03-01 | 2026-03-04 | 2026-03-07 |  | 11 | Yes | Workflow Logic | Retest after overnight data refresh. | Wave 1 - Core Journeys |  | 11+ days | Yes
DEF-012 | Audit history not retained after amendment | Audit history not retained after amendment during charges & payments execution for finance & billing users. | Finance & Billing | Charges & Payments | SCN-039 | REQ-009 | S4 - Low | P4 | Closed | Karl Bennett | Data Migration | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2 | No | Security Role | No practical workaround; blocker remains open. | Wave 2 - Exceptions |  | 0-2 days | No
DEF-013 | Notification not generated for downstream team | Notification not generated for downstream team during dashboard refresh execution for reporting & mi users. | Reporting & MI | Dashboard Refresh | SCN-075 | REQ-015 | S3 - Medium | P3 | Closed | Karl Bennett | Vendor Support | 2026-03-03 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 8 | No | Security Role | Proceed with alternate scenario until configuration is corrected. | Wave 3 - Reporting & Close Down |  | 6-10 days | No
DEF-014 | Reference data lookup fails for valid value | Reference data lookup fails for valid value during case routing execution for contact centre users. | Contact Centre | Case Routing | SCN-076 | REQ-016 | S2 - High | P2 | Closed | Gareth Evans | Vendor Support | 2026-03-03 | 2026-03-09 | 2026-03-12 | 2026-03-15 | 9 | No | Business Rule Mapping | Retest after overnight data refresh. | Wave 1 - Core Journeys |  | 6-10 days | No
DEF-015 | Duplicate record created on retry | Duplicate record created on retry during charges & payments execution for finance & billing users. | Finance & Billing | Charges & Payments | SCN-029 | REQ-029 | S2 - High | P2 | In Triage | Laura Green | Vendor Support | 2026-02-25 | 2026-03-01 |  |  | 15 | Yes | Integration | Use manual workaround and continue with controlled evidence capture. | Wave 2 - Exceptions |  | 11+ days | Yes
DEF-016 | Notification not generated for downstream team | Notification not generated for downstream team during work allocation execution for field operations users. | Field Operations | Work Allocation | SCN-063 | REQ-003 | S2 - High | P2 | Closed | Gareth Evans | Integration Team | 2026-02-28 | 2026-03-05 | 2026-03-05 | 2026-03-06 | 5 | No | Workflow Logic | Proceed with alternate scenario until configuration is corrected. | Wave 2 - Exceptions |  | 3-5 days | No
DEF-017 | Reference data lookup fails for valid value | Reference data lookup fails for valid value during identity & eligibility execution for contact centre users. | Contact Centre | Identity & Eligibility | SCN-066 | REQ-006 | S1 - Critical | P1 | Fixed - Pending Retest | Ben Carter | Vendor Support | 2026-02-28 | 2026-03-01 | 2026-03-01 |  | 12 | Yes | Business Rule Mapping | Retest after overnight data refresh. | Wave 1 - Core Journeys | Escalated at daily defect triage. | 11+ days | Yes
DEF-018 | Report output excludes expected population | Report output excludes expected population during visit completion execution for field operations users. | Field Operations | Visit Completion | SCN-018 | REQ-018 | S2 - High | P2 | Open | Gareth Evans | Integration Team | 2026-02-28 | 2026-03-08 |  |  | 12 | Yes | Configuration | No practical workaround; blocker remains open. | Wave 2 - Exceptions |  | 11+ days | Yes
DEF-019 | Record saves without mandatory field completion | Record saves without mandatory field completion during mobile updates execution for field operations users. | Field Operations | Mobile Updates | SCN-028 | REQ-028 | S2 - High | P2 | Closed | Aisha Khan | Integration Team | 2026-02-25 | 2026-02-27 | 2026-03-02 | 2026-03-04 | 5 | No | Integration | Use admin-assisted update as an interim control. | Wave 2 - Exceptions |  | 3-5 days | No
DEF-020 | Record saves without mandatory field completion | Record saves without mandatory field completion during case update execution for case management users. | Case Management | Case Update | SCN-032 | REQ-002 | S4 - Low | P4 | Rejected | Karl Bennett | Data Migration | 2026-02-25 | 2026-03-01 |  |  | 15 | No | Security Role | Use admin-assisted update as an interim control. | Wave 1 - Core Journeys |  | 11+ days | No
DEF-021 | Notification not generated for downstream team | Notification not generated for downstream team during case update execution for case management users. | Case Management | Case Update | SCN-002 | REQ-002 | S3 - Medium | P3 | Fixed - Pending Retest | Laura Green | D365 Delivery | 2026-03-03 | 2026-03-08 | 2026-03-11 |  | 9 | Yes | Data | Use admin-assisted update as an interim control. | Wave 1 - Core Journeys |  | 6-10 days | Yes
DEF-022 | Record saves without mandatory field completion | Record saves without mandatory field completion during operational reporting execution for reporting & mi users. | Reporting & MI | Operational Reporting | SCN-025 | REQ-025 | S4 - Low | P4 | In Triage | Ben Carter | Integration Team | 2026-02-27 | 2026-03-04 |  |  | 13 | Yes | Data | Proceed with alternate scenario until configuration is corrected. | Wave 3 - Reporting & Close Down |  | 11+ days | Yes
DEF-023 | Validation message does not display correctly | Validation message does not display correctly during case update execution for case management users. | Case Management | Case Update | SCN-022 | REQ-022 | S2 - High | P2 | Fixed - Pending Retest | Gareth Evans | Vendor Support | 2026-03-07 | 2026-03-15 | 2026-03-17 |  | 5 | No | Workflow Logic | Proceed with alternate scenario until configuration is corrected. | Wave 1 - Core Journeys |  | 3-5 days | Yes
DEF-024 | Appointment slot not released after cancellation | Appointment slot not released after cancellation during appointment booking execution for field operations users. | Field Operations | Appointment Booking | SCN-043 | REQ-013 | S3 - Medium | P3 | Fixed - Pending Retest | Karl Bennett | D365 Delivery | 2026-03-06 | 2026-03-10 | 2026-03-12 |  | 6 | Yes | Security Role | Proceed with alternate scenario until configuration is corrected. | Wave 2 - Exceptions |  | 6-10 days | Yes
DEF-025 | Validation message does not display correctly | Validation message does not display correctly during adjustments execution for finance & billing users. | Finance & Billing | Adjustments | SCN-044 | REQ-014 | S3 - Medium | P3 | Rejected | Gareth Evans | Data Migration | 2026-02-26 | 2026-02-28 |  |  | 14 | No | Workflow Logic | Proceed with alternate scenario until configuration is corrected. | Wave 2 - Exceptions |  | 11+ days | No
DEF-026 | Reference data lookup fails for valid value | Reference data lookup fails for valid value during case update execution for case management users. | Case Management | Case Update | SCN-052 | REQ-022 | S3 - Medium | P3 | Fixed - Pending Retest | Karl Bennett | Security Admin | 2026-02-28 | 2026-03-07 | 2026-03-09 |  | 12 | Yes | Data | Use admin-assisted update as an interim control. | Wave 1 - Core Journeys |  | 11+ days | Yes
DEF-027 | Record saves without mandatory field completion | Record saves without mandatory field completion during identity & eligibility execution for contact centre users. | Contact Centre | Identity & Eligibility | SCN-026 | REQ-026 | S3 - Medium | P3 | Closed | Laura Green | Data Migration | 2026-03-07 | 2026-03-13 | 2026-03-15 | 2026-03-16 | 8 | No | Configuration | Proceed with alternate scenario until configuration is corrected. | Wave 1 - Core Journeys |  | 6-10 days | No
DEF-028 | Reference data lookup fails for valid value | Reference data lookup fails for valid value during case creation execution for case management users. | Case Management | Case Creation | SCN-047 | REQ-017 | S4 - Low | P4 | Closed | Gareth Evans | Integration Team | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-04 | 2 | No | Environment | No practical workaround; blocker remains open. | Wave 1 - Core Journeys |  | 0-2 days | No
DEF-029 | Access profile prevents valid execution | Access profile prevents valid execution during call handling execution for contact centre users. | Contact Centre | Call Handling | SCN-011 | REQ-011 | S3 - Medium | P3 | Fixed - Pending Retest | Gareth Evans | Vendor Support | 2026-02-25 | 2026-03-05 | 2026-03-07 |  | 15 | Yes | Data | Retest after overnight data refresh. | Wave 1 - Core Journeys |  | 11+ days | Yes
DEF-030 | Notification not generated for downstream team | Notification not generated for downstream team during regulatory reporting execution for reporting & mi users. | Reporting & MI | Regulatory Reporting | SCN-030 | REQ-030 | S4 - Low | P4 | In Triage | Laura Green | D365 Delivery | 2026-03-07 | 2026-03-15 |  |  | 5 | No | Business Rule Mapping | No practical workaround; blocker remains open. | Wave 3 - Reporting & Close Down |  | 3-5 days | Yes
DEF-031 | Reference data lookup fails for valid value | Reference data lookup fails for valid value during charges & payments execution for finance & billing users. | Finance & Billing | Charges & Payments | SCN-009 | REQ-009 | S1 - Critical | P1 | In Triage | Laura Green | Security Admin | 2026-02-25 | 2026-03-04 |  |  | 15 | Yes | Environment | Use manual workaround and continue with controlled evidence capture. | Wave 2 - Exceptions | Escalated at daily defect triage. | 11+ days | Yes
DEF-032 | Validation message does not display correctly | Validation message does not display correctly during regulatory reporting execution for reporting & mi users. | Reporting & MI | Regulatory Reporting | SCN-040 | REQ-010 | S1 - Critical | P1 | Fixed - Pending Retest | Gareth Evans | Data Migration | 2026-03-05 | 2026-03-13 | 2026-03-16 |  | 7 | No | Integration | Proceed with alternate scenario until configuration is corrected. | Wave 3 - Reporting & Close Down | Escalated at daily defect triage. | 6-10 days | Yes
DEF-033 | Validation message does not display correctly | Validation message does not display correctly during operational reporting execution for reporting & mi users. | Reporting & MI | Operational Reporting | SCN-035 | REQ-005 | S4 - Low | P4 | Fixed - Pending Retest | Ben Carter | Vendor Support | 2026-03-07 | 2026-03-15 | 2026-03-15 |  | 5 | No | Integration | Use admin-assisted update as an interim control. | Wave 3 - Reporting & Close Down |  | 3-5 days | Yes
DEF-034 | Audit history not retained after amendment | Audit history not retained after amendment during data reconciliation execution for reporting & mi users. | Reporting & MI | Data Reconciliation | SCN-080 | REQ-020 | S2 - High | P2 | Open | Karl Bennett | D365 Delivery | 2026-03-02 | 2026-03-04 |  |  | 10 | Yes | Integration | Use manual workaround and continue with controlled evidence capture. | Wave 3 - Reporting & Close Down |  | 6-10 days | Yes
DEF-035 | Report output excludes expected population | Report output excludes expected population during complaint handling execution for case management users. | Case Management | Complaint Handling | SCN-067 | REQ-007 | S3 - Medium | P3 | Closed | Karl Bennett | Data Migration | 2026-03-04 | 2026-03-09 | 2026-03-12 | 2026-03-14 | 8 | No | Integration | Proceed with alternate scenario until configuration is corrected. | Wave 1 - Core Journeys |  | 6-10 days | No

## Issue Log
Northbridge Citizens Services ¦ Issue Log
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Use this sheet for non-defect operational issues affecting UAT, such as environment instability, tester availability, reporting delays or support-model gaps. Track owner, due date, mitigation and escalation need. The overdue indicator helps you surface issues that are quietly ageing in the background.
Issue ID | Issue Title | Category | Description | Impact | Severity | Owner | Date Raised | Due Date | Status | Dependency / Ref | Mitigation | Escalation Required | Overdue
ISS-001 | Reporting issue impacting daily UAT execution | Reporting | Reporting issue affecting one or more business areas and requiring coordinated action before the next execution window. | High - blocks multiple testers | High | Jessica Reed | 2026-02-27 | 2026-03-04 | Resolved | Role update request | Reschedule affected scripts to next slot. | No | No
ISS-002 | Integration issue impacting daily UAT execution | Integration | Integration issue affecting one or more business areas and requiring coordinated action before the next execution window. | Low - manageable with workaround | Low | Karl Bennett | 2026-02-24 | 2026-02-27 | Resolved | Environment refresh | Trigger defect triage and agree business containment. | No | No
ISS-003 | Scheduling issue impacting daily UAT execution | Scheduling | Scheduling issue affecting one or more business areas and requiring coordinated action before the next execution window. | Low - manageable with workaround | Medium | Karl Bennett | 2026-03-01 | 2026-03-04 | Resolved | Data load window | Use interim workaround and monitor impact. | No | No
ISS-004 | SME Availability issue impacting daily UAT execution | SME Availability | SME Availability issue affecting one or more business areas and requiring coordinated action before the next execution window. | Medium - delays specific scenarios | High | Jessica Reed | 2026-03-05 | 2026-03-09 | In Progress | Role update request | Trigger defect triage and agree business containment. | Yes | Yes
ISS-005 | Access issue impacting daily UAT execution | Access | Access issue affecting one or more business areas and requiring coordinated action before the next execution window. | Low - manageable with workaround | Medium | Aisha Khan | 2026-03-03 | 2026-03-04 | Open | Role update request | Escalate through daily control and confirm ownership. | No | Yes
ISS-006 | Scheduling issue impacting daily UAT execution | Scheduling | Scheduling issue affecting one or more business areas and requiring coordinated action before the next execution window. | Low - manageable with workaround | High | Aisha Khan | 2026-02-24 | 2026-03-02 | Open | Role update request | Reschedule affected scripts to next slot. | Yes | Yes
ISS-007 | Reporting issue impacting daily UAT execution | Reporting | Reporting issue affecting one or more business areas and requiring coordinated action before the next execution window. | Low - manageable with workaround | Low | Karl Bennett | 2026-03-06 | 2026-03-07 | Closed | Data load window | Trigger defect triage and agree business containment. | No | No
ISS-008 | Environment issue impacting daily UAT execution | Environment | Environment issue affecting one or more business areas and requiring coordinated action before the next execution window. | Low - manageable with workaround | Medium | Farah Malik | 2026-03-05 | 2026-03-06 | In Progress | Daily defect triage | Trigger defect triage and agree business containment. | No | Yes
ISS-009 | Data issue impacting daily UAT execution | Data | Data issue affecting one or more business areas and requiring coordinated action before the next execution window. | High - blocks multiple testers | High | Jessica Reed | 2026-03-03 | 2026-03-05 | Resolved | Daily defect triage | Reschedule affected scripts to next slot. | No | No
ISS-010 | Training issue impacting daily UAT execution | Training | Training issue affecting one or more business areas and requiring coordinated action before the next execution window. | Low - manageable with workaround | Medium | Farah Malik | 2026-03-01 | 2026-03-05 | Open | Environment refresh | Use interim workaround and monitor impact. | Yes | Yes
ISS-011 | Reporting issue impacting daily UAT execution | Reporting | Reporting issue affecting one or more business areas and requiring coordinated action before the next execution window. | Low - manageable with workaround | High | Farah Malik | 2026-03-05 | 2026-03-11 | In Progress | Role update request | Reschedule affected scripts to next slot. | Yes | Yes
ISS-012 | Environment issue impacting daily UAT execution | Environment | Environment issue affecting one or more business areas and requiring coordinated action before the next execution window. | High - blocks multiple testers | High | Karl Bennett | 2026-03-03 | 2026-03-06 | Resolved | Data load window | Reschedule affected scripts to next slot. | No | No

## Risk & Assumptions
Northbridge Citizens Services ¦ Risk & Assumptions
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Capture open risks and assumptions with probability, impact, mitigation and contingency. Score and RAG are formula-driven so the sheet can quickly highlight the riskiest items. This log should support readiness reviews, governance forums and sign-off preparation.
ID | Type | Category | Description | Cause | Consequence | Probability | Impact | Score | RAG | Mitigation | Contingency | Owner | Target Date | Status | Overdue
RSK-001 | Risk | Data | Security role changes may require additional approval steps. | Incomplete configuration | Exit criteria could be delayed | 5 | 4 | 20 | Red | Agree contingency execution windows and reserve business cover. | Move affected scenarios to controlled post-UAT verification. | Nadia Shah | 2026-03-16 | Closed | No
RSK-002 | Risk | Governance | Security role changes may require additional approval steps. | Dependency on external vendor | Exit criteria could be delayed | 4 | 4 | 16 | Red | Increase daily control and escalate early. | Move affected scenarios to controlled post-UAT verification. | Emily Foster | 2026-03-09 | Closed | No
ASM-003 | Assumption | Supplier Dependency | Supplier fix turnaround may be slower than daily triage requires. | Governance bottleneck | More scenarios may be deferred | 3 | 4 | 12 | Amber | Increase daily control and escalate early. | Accept partial execution with formal residual risk. | Emily Foster | 2026-03-12 | Mitigating | No
ASM-004 | Assumption | Business Availability | Supplier fix turnaround may be slower than daily triage requires. | Governance bottleneck | Sign-off confidence may reduce | 2 | 4 | 8 | Green | Agree contingency execution windows and reserve business cover. | Delay sign-off until evidence threshold is met. | Chloe Morgan | 2026-03-20 | Open | No
ASM-005 | Assumption | Reporting | Security role changes may require additional approval steps. | Dependency on external vendor | Defect backlog may remain above tolerance | 4 | 4 | 16 | Red | Increase daily control and escalate early. | Move affected scenarios to controlled post-UAT verification. | Aisha Khan | 2026-03-22 | Open | No
RSK-006 | Risk | Business Availability | Business tester availability may reduce during peak operational periods. | Incomplete configuration | Exit criteria could be delayed | 3 | 5 | 15 | Amber | Prioritise critical-path scenarios and defects. | Accept partial execution with formal residual risk. | Jessica Reed | 2026-03-22 | Closed | No
RSK-007 | Risk | Business Availability | Business tester availability may reduce during peak operational periods. | Governance bottleneck | More scenarios may be deferred | 4 | 5 | 20 | Red | Run targeted triage with supplier and internal owners. | Accept partial execution with formal residual risk. | Nadia Shah | 2026-03-22 | Mitigating | No
ASM-008 | Assumption | Reporting | Security role changes may require additional approval steps. | Governance bottleneck | Defect backlog may remain above tolerance | 4 | 3 | 12 | Amber | Run targeted triage with supplier and internal owners. | Accept partial execution with formal residual risk. | Chloe Morgan | 2026-03-19 | Open | No
RSK-009 | Risk | Data | Reporting extracts may not stabilise in time for sign-off evidence. | Competing business priorities | Sign-off confidence may reduce | 2 | 4 | 8 | Green | Run targeted triage with supplier and internal owners. | Use workaround and capture leadership approval. | Nadia Shah | 2026-03-16 | Open | No
RSK-010 | Risk | Release Management | Reporting extracts may not stabilise in time for sign-off evidence. | Incomplete configuration | Defect backlog may remain above tolerance | 3 | 5 | 15 | Amber | Increase daily control and escalate early. | Use workaround and capture leadership approval. | Chloe Morgan | 2026-03-19 | Open | No
RSK-011 | Risk | Business Availability | Reporting extracts may not stabilise in time for sign-off evidence. | Governance bottleneck | Defect backlog may remain above tolerance | 3 | 4 | 12 | Amber | Increase daily control and escalate early. | Move affected scenarios to controlled post-UAT verification. | Emily Foster | 2026-03-10 | Closed | No
RSK-012 | Risk | Governance | Operational procedures may continue to rely on legacy manual controls. | Late data load | Exit criteria could be delayed | 2 | 5 | 10 | Amber | Increase daily control and escalate early. | Use workaround and capture leadership approval. | Chloe Morgan | 2026-03-10 | Mitigating | Yes

## Decision Log
Northbridge Citizens Services ¦ Decision Log
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Use the decision log to evidence who decided what, when, where, and with what follow-up. Good UAT governance requires a visible record of scope decisions, defect tolerance, schedule changes, and sign-off conditions. The overdue flag highlights decisions whose actions are slipping.
Decision ID | Date | Decision Title | Description | Decision Owner | Forum | Impact Area | Linked Issue / Risk | Outcome | Action Required | Due Date | Status | Overdue
DEC-001 | 2026-02-26 | Escalate environment performance issue to supplier | Governance decision recorded to maintain delivery control, evidence traceability, and decision ownership. | Chloe Morgan | SteerCo | Defects | RSK-001 | Deferred | Track through next governance checkpoint. | 2026-03-03 | In Progress | Yes
DEC-002 | 2026-03-08 | Accept controlled workaround for medium defects | Governance decision recorded to maintain delivery control, evidence traceability, and decision ownership. | Chloe Morgan | SteerCo | Readiness | RSK-001 | Approved | Update status report and notify business testers. | 2026-03-13 | Open | No
DEC-003 | 2026-02-26 | Accept controlled workaround for medium defects | Governance decision recorded to maintain delivery control, evidence traceability, and decision ownership. | Nadia Shah | Readiness Review | Schedule | RSK-001 | Deferred | Update status report and notify business testers. | 2026-02-27 | In Progress | Yes
DEC-004 | 2026-02-26 | Adopt tightened entry criteria for Wave 2 | Governance decision recorded to maintain delivery control, evidence traceability, and decision ownership. | Aisha Khan | Go/No-Go Board | Scope |  | Approved | Evidence acceptance decision in sign-off pack. | 2026-03-02 | Complete | No
DEC-005 | 2026-03-04 | Approve targeted script sequencing change | Governance decision recorded to maintain delivery control, evidence traceability, and decision ownership. | Nadia Shah | Readiness Review | Scope | ISS-001 | Approved | Evidence acceptance decision in sign-off pack. | 2026-03-06 | Complete | No
DEC-006 | 2026-03-09 | Approve targeted script sequencing change | Governance decision recorded to maintain delivery control, evidence traceability, and decision ownership. | Jessica Reed | Go/No-Go Board | Schedule | ISS-001 | Deferred | Track through next governance checkpoint. | 2026-03-13 | In Progress | No
DEC-007 | 2026-02-25 | Adopt tightened entry criteria for Wave 2 | Governance decision recorded to maintain delivery control, evidence traceability, and decision ownership. | Nadia Shah | SteerCo | Readiness | DEF-001 | Deferred | Evidence acceptance decision in sign-off pack. | 2026-02-27 | In Progress | Yes
DEC-008 | 2026-03-04 | Adopt tightened entry criteria for Wave 2 | Governance decision recorded to maintain delivery control, evidence traceability, and decision ownership. | Aisha Khan | SteerCo | Defects | DEF-001 | Approved with conditions | Track through next governance checkpoint. | 2026-03-09 | In Progress | Yes
DEC-009 | 2026-03-02 | Defer non-critical reporting scenarios | Governance decision recorded to maintain delivery control, evidence traceability, and decision ownership. | Jessica Reed | Daily Control | Readiness | DEF-001 | Deferred | Confirm contingency and revised target dates. | 2026-03-05 | Complete | No
DEC-010 | 2026-03-01 | Defer non-critical reporting scenarios | Governance decision recorded to maintain delivery control, evidence traceability, and decision ownership. | Aisha Khan | Daily Control | Schedule | ISS-001 | Approved with conditions | Update status report and notify business testers. | 2026-03-03 | Complete | No

## Status Report Input
Northbridge Citizens Services ¦ Status Report Input
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Use this sheet to capture the narrative layer behind the dashboards: achievements, blockers, planned next steps, decisions needed and confidence status. The top section shows the current reporting snapshot; the table below keeps a period-by-period history you can reuse in reports or steering packs.
Current Period Narrative Snapshot
Reporting Period | Week 4: 11 Mar - 15 Mar 2026
Key Achievements | Expanded coverage into exception and reporting scenarios.
Planned Next Steps | Prepare sign-off evidence pack and residual risk summary.
Key Blockers | Reporting extracts still require validation.
Top Risks | Data refresh timing remains a dependency.
Decisions Required | Confirm whether to extend re-test window.
Confidence Status | Amber
Narrative Summary | Structured daily control is in place. Progress is visible, but exit confidence remains dependent on clearing the remaining critical-path blockers and confirming residual risk acceptance.
Reporting Log History
Reporting Period | Key Achievements | Planned Next Steps | Key Blockers | Top Risks | Decisions Required | Confidence Status | Narrative Summary
Week 1: 24 Feb - 28 Feb 2026 | Stabilised data load process and increased daily execution volume. | Prepare sign-off evidence pack and residual risk summary. | Reporting extracts still require validation. | Residual reporting issues may require conditional acceptance. | Approve deferral of non-critical scenarios. | Green | Structured daily control is in place. Progress is visible, but exit confidence remains dependent on clearing the remaining critical-path blockers and confirming residual risk acceptance.
Week 2: 01 Mar - 05 Mar 2026 | Expanded coverage into exception and reporting scenarios. | Increase retest throughput and close high-priority open defects. | Business tester availability dips during peak operational periods. | Data refresh timing remains a dependency. | Approve deferral of non-critical scenarios. | Green | Structured daily control is in place. Progress is visible, but exit confidence remains dependent on clearing the remaining critical-path blockers and confirming residual risk acceptance.
Week 3: 06 Mar - 10 Mar 2026 | Expanded coverage into exception and reporting scenarios. | Push outstanding scenario design approvals through governance. | Reporting extracts still require validation. | Open critical defect could delay sign-off confidence. | Confirm whether to extend re-test window. | Amber | Structured daily control is in place. Progress is visible, but exit confidence remains dependent on clearing the remaining critical-path blockers and confirming residual risk acceptance.
Week 4: 11 Mar - 15 Mar 2026 | Expanded coverage into exception and reporting scenarios. | Prepare sign-off evidence pack and residual risk summary. | Reporting extracts still require validation. | Data refresh timing remains a dependency. | Confirm whether to extend re-test window. | Amber | Structured daily control is in place. Progress is visible, but exit confidence remains dependent on clearing the remaining critical-path blockers and confirming residual risk acceptance.

## Exit & Sign-Off
Northbridge Citizens Services ¦ Exit & Sign-Off
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
This sheet supports the formal closure decision. Track mandatory and non-mandatory exit criteria, supporting evidence, approvals and comments. The complete-flag column drives the exit readiness KPI on the dashboards. Use comments to explain any residual-risk based acceptance.
Criterion ID | Category | Criterion | Mandatory | Owner | Status | Evidence | Approved By | Approval Date | Comments | Complete Flag
EXT-001 | Execution | Minimum in-scope scenario execution threshold met | Yes | Karl Bennett | Complete | Defect report | Aisha Khan | 2026-03-10 |  | 1
EXT-002 | Defects | No open critical defects remain | Yes | Jessica Reed | In Progress | Signed email |  |  | One critical defect remains in triage. | 0
EXT-003 | Defects | Open high defects within agreed tolerance | Yes | Nadia Shah | In Progress |  |  |  | High defect tolerance still under review. | 0
EXT-004 | Blockers | No unresolved execution blockers remain | Yes | Laura Green | Complete | Decision log | Chloe Morgan | 2026-03-09 |  | 1
EXT-005 | Business Acceptance | Business approvers reviewed evidence pack | Yes | Aisha Khan | Complete | Dashboard review | Emily Foster | 2026-03-09 |  | 1
EXT-006 | Business Acceptance | Residual risks formally accepted | Yes | Laura Green | Not Started | Decision log |  |  |  | 0
EXT-007 | Support Model | Operational support model agreed | Yes | Emily Foster | Not Started | Signed email |  |  |  | 0
EXT-008 | Support Model | Known issues and workarounds documented | No | Karl Bennett | Complete | Signed email | Aisha Khan | 2026-03-10 |  | 1
EXT-009 | Governance | Lessons learned captured | No | Karl Bennett | Not Started | Readiness pack |  |  |  | 0
EXT-010 | Governance | Sign-off recommendation submitted to board | Yes | Ben Carter | In Progress | Decision log |  |  |  | 0

## Lessons Learned
Northbridge Citizens Services ¦ Lessons Learned
Service Transformation Programme ¦ Release 2 - Case Management & Appointments ¦ Report date: 12-Mar-2026
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
Capture closure insights that can be reused in future releases. Focus on what improved control and what caused friction. Assign owners and dates if you intend to convert lessons into delivery standards, process changes or reusable accelerators.
Item ID | Category | What Worked | What Did Not Work | Recommendation | Owner | Priority | Target Date | Status | Reusable Pattern
LL-001 | Governance | Using a single workbook improved transparency for business users. | Late data changes caused avoidable retest effort. | Baseline entry criteria earlier and track them weekly. | Aisha Khan | High | 2026-04-10 | In Progress | No
LL-002 | Governance | Using a single workbook improved transparency for business users. | Some sign-off criteria were not socialised early enough. | Introduce a dedicated data readiness cut-off before execution. | Ibrahim Ali | Low | 2026-03-29 | Open | No
LL-003 | Governance | Named backup testers reduced execution downtime. | Access provisioning remained too manual. | Run mini-readiness reviews per wave instead of one large checkpoint. | Nadia Shah | Medium | 2026-04-03 | Open | No
LL-004 | Execution | Daily control with clear ownership kept issues visible. | Exception scenarios were prepared later than ideal. | Pre-agree defect tolerance and sign-off evidence thresholds. | Aisha Khan | Low | 2026-04-03 | In Progress | Yes
LL-005 | Data | Daily control with clear ownership kept issues visible. | Exception scenarios were prepared later than ideal. | Introduce a dedicated data readiness cut-off before execution. | Laura Green | Low | 2026-04-11 | Complete | No
LL-006 | Readiness | Traceability between requirements and scenarios improved triage quality. | Late data changes caused avoidable retest effort. | Baseline entry criteria earlier and track them weekly. | Emily Foster | High | 2026-04-02 | In Progress | No
LL-007 | Readiness | Using a single workbook improved transparency for business users. | Some sign-off criteria were not socialised early enough. | Run mini-readiness reviews per wave instead of one large checkpoint. | Laura Green | Low | 2026-04-03 | Complete | Yes
LL-008 | Data | Traceability between requirements and scenarios improved triage quality. | Some sign-off criteria were not socialised early enough. | Pre-agree defect tolerance and sign-off evidence thresholds. | Karl Bennett | Low | 2026-03-31 | In Progress | Yes
LL-009 | Defects | Named backup testers reduced execution downtime. | Access provisioning remained too manual. | Pre-agree defect tolerance and sign-off evidence thresholds. | Nadia Shah | Medium | 2026-03-25 | Open | No
LL-010 | Governance | Named backup testers reduced execution downtime. | Some sign-off criteria were not socialised early enough. | Pre-agree defect tolerance and sign-off evidence thresholds. | Gareth Evans | Low | 2026-03-25 | Complete | No

## About & Attribution
About this workbook
Keep or hide this tab depending on your internal deployment preference.
Start Here | Overview | Exec Dashboard | Ops Dashboard | Inputs
This workbook is intentionally designed as a white-label, macro-free UAT command pack. It includes dummy data, embedded guidance, dashboards and control logs so teams can see all features in action before deploying it live.
Minimal attribution / licensing note
Source / original concept: StratForge.
This reference is intentionally isolated to a single tab so the workbook can be white-labelled for internal use.
The workbook contains no VBA, no macros, and no external links.
Before live use, replace demo data, review thresholds, and confirm internal policy / legal requirements for redistribution.
If your licence terms permit, this tab may be hidden for internal deployment.

## Lists (hidden)
YesNo | ScopeType | ReadinessStatus | ExecutionStatus | DesignStatus | DefectSeverity | DefectPriority | DefectStatus | IssueStatus | RiskType | RiskStatus | DecisionStatus | ConfidenceStatus | PlanStatus | Waves | BusinessAreas | Roles | TesterTypes | Owners | ReadinessCategories | EnvCategories | ScenarioPriority | RiskRating | RetestStatus | IssueCategories | AssignedTeams | Forums | SimpleProgress | ActionPriority | RootCauses
Yes | In Scope | Complete | Passed | Ready | S1 - Critical | P1 | Open | Open | Risk | Open | Open | Green | Complete | Wave 1 - Core Journeys | Contact Centre | UAT Lead | Business Tester | Aisha Khan | Governance & Planning | Environment | Critical | High | Not Required | Environment | D365 Delivery | Daily Control | Complete | High | Business Rule Mapping
No | Partial | In Progress | Failed | In Review | S2 - High | P2 | In Triage | In Progress | Assumption | Mitigating | In Progress | Amber | In Progress | Wave 2 - Exceptions | Case Management | Business Analyst | SME | Ben Carter | Scope & Requirements | Access | High | Medium | Not Due | Data | Integration Team | Defect Triage | In Progress | Medium | Configuration
| Out of Scope | Not Started | Blocked | Approved | S3 - Medium | P3 | Fixed - Pending Retest | Resolved |  | Closed | Complete | Red | At Risk | Wave 3 - Reporting & Close Down | Field Operations | Service Manager | Operational Lead | Chloe Morgan | Scripts & Scenarios | Data | Medium | Low | Pending | Access | Reporting Team | Readiness Review | Not Started | Low | Data
|  | Blocked | Deferred |  | S4 - Low | P4 | Closed | Closed |  |  |  |  | Not Started |  | Finance & Billing | SME | Product Owner | Daniel Hughes | Tester Readiness | Integration | Low |  | Complete | SME Availability | Security Admin | Go/No-Go Board |  |  | Environment
|  | Not Applicable | In Progress |  |  |  | Rejected | [7 empty] | Reporting & MI | Product Owner |  | Emily Foster | Training & Communications | Tooling |  |  |  | Integration | Data Migration | SteerCo |  |  | Integration
[16 empty] | Operations Lead |  | Farah Malik | Environment & Access |  |  |  |  | Training | Vendor Support |  |  |  | Reporting Logic
[16 empty] | Training Lead |  | Gareth Evans | Test Data |  |  |  |  | Reporting |  |  |  |  | Security Role
[16 empty] | PMO Analyst |  | Hannah Price | Support Model |  |  |  |  | Scheduling |  |  |  |  | Workflow Logic
[16 empty] | Test Coordinator |  | Ibrahim Ali | Defect Triage & Governance
[18 empty] | Jessica Reed | Reporting & Sign-Off
Karl Bennett
Laura Green
Marcus Hall
Nadia Shah
Owen Turner
Priya Singh
Quentin Ross
Ruth Adams

## Dashboard Data (hidden)
Overall readiness % | 0.59649 | Category | Complete % | Mandatory Complete | Severity | Total Defects | Open Defects | Status | Count | Execution Date | Executed | Passed | Failed | Blocked | Tester | Executions | Age Band | Count | Category | Complete % | Blockers | Plan Status | Count | Business Area | Executions | Blocked | RAG | Count | Root Cause | Count
Execution coverage % | 0.8 | Governance & Planning | 0.85714 | 6 | S1 - Critical | 5 | 5 | Open | 3 | 2026-02-24 | 12 | 10 | 0 | 1 | Aisha Khan | 5 | 0-2 days | 2 | Environment | 0.6 | 1 | Complete | 10 | Contact Centre | 35 | 5 | Red | 4 | Business Rule Mapping | 4 | Contact Centre | 5
Pass rate % | 0.6 | Scope & Requirements | 0.57143 | 3 | S2 - High | 9 | 6 | In Triage | 6 | 2026-02-25 | 11 | 7 | 2 | 1 | Ben Carter | 5 | 3-5 days | 7 | Access | 0.6 | 0 | In Progress | 1 | Case Management | 22 | 0 | Amber | 6 | Configuration | 4 | Case Management | 5
Blocked rate % | 0.11333 | Scripts & Scenarios | 0.71429 | 4 | S3 - Medium | 12 | 6 | Fixed - Pending Retest | 11 | 2026-02-26 | 6 | 3 | 2 | 1 | Chloe Morgan | 14 | 6-10 days | 14 | Data | 0.4 | 1 | At Risk | 2 | Field Operations | 38 | 6 | Green | 2 | Data | 4 | Field Operations | 5
Open critical defects | 5 | Tester Readiness | 0.42857 | 2 | S4 - Low | 9 | 3 | Closed | 12 | 2026-02-27 | 9 | 6 | 2 | 1 | Daniel Hughes | 6 | 11+ days | 12 | Integration | 0.4 | 0 | Not Started | 2 | Finance & Billing | 29 | 1 |  |  | Environment | 3 | Finance & Billing | 5
Open high defects | 6 | Training & Communications | 0.57143 | 3 |  |  |  | Rejected | 3 | 2026-02-28 | 7 | 5 | 1 | 1 | Emily Foster | 0 |  |  | Tooling | 0.6 | 0 |  |  | Reporting & MI | 26 | 5 |  |  | Integration | 7 | Reporting & MI | 5
Exit readiness % | 0.375 | Environment & Access | 1 | 6 | [5 empty] | 2026-03-01 | 12 | 5 | 3 | 1 | Farah Malik | 7 | [12 empty] | Reporting Logic | 3
Open issues | 6 | Test Data | 0.42857 | 3 | [5 empty] | 2026-03-02 | 10 | 7 | 1 | 2 | Gareth Evans | 13 | [12 empty] | Security Role | 4
Open risks | 8 | Support Model | 0.28571 | 1 | [5 empty] | 2026-03-03 | 8 | 6 | 2 | 0 | Hannah Price | 15 | [12 empty] | Workflow Logic | 6
Ready testers % | 0.88235 | Defect Triage & Governance | 0.57143 | 4 | [5 empty] | 2026-03-04 | 11 | 8 | 1 | 1 | Jessica Reed | 0
Overdue readiness items | 29 | Reporting & Sign-Off | 0.42857 | 2 | [5 empty] | 2026-03-05 | 10 | 8 | 2 | 0 | Karl Bennett | 23
Overdue issues | 6 | [8 empty] | 2026-03-06 | 11 | 7 | 1 | 1 | Laura Green | 11
Late milestones | 3 | [8 empty] | 2026-03-07 | 12 | 6 | 2 | 2 | Marcus Hall | 12
[10 empty] | 2026-03-08 | 12 | 6 | 3 | 2 | Nadia Shah | 0
Total scenarios | 80 | [8 empty] | 2026-03-09 | 8 | 1 | 4 | 2 | Owen Turner | 5
Scenarios executed | 64 | [8 empty] | 2026-03-10 | 11 | 5 | 2 | 1 | Priya Singh | 20
Execution records | 150 | [13 empty] | Quentin Ross | 10
Passed executions | 90 | [13 empty] | Ruth Adams | 4
Failed executions | 28
Blocked executions | 17
Deferred executions | 15
Retest pending | 6
Defect target breaches | 15
Open defects | 20